## State_trans_utility_wise_prt1
REPORT INDICATING STATUS OF CONSTRUCTION OF TRANSMISSION LINES (220 kV & ABOVE) DURING- 2021-22
As on 31-AUG-2021
Sl No | Name of Transmission Lines | Ckts (S/C) & (D/C) | Voltage Level (kV) | Total Length (cKm) | Progress Status of Transmission |  |  |  | Target Date |  | Remarks
[5 empty] | Total Locations (Nos) | Foundation completed (Nos) | Tower Erected (Nos) | Stringing completed (CKm) | Schedule | Revised/ Anticipated
1. | 2. | 3. | 4. | 5. | 6. | 7. | 8. | 9. | 10. | 11. | 12.
DAMODAR VALLEY CORPORATION(DVC)
1 | LILO of Mejia-Kalyaneswari at Burnpur S/S | D/C | 220 | 37 | 79 | 55 | 0 | 0 |  |  | Line is not possible to be constructed due to severe ROW problem and Severe local resistance and issues, so further action has been initiated for short closure.
2 | MTPS - Ramgarh (Bypassing Gola SS) | D/C | 220 | 207 | 687 | 682 | 679 | 203.05 | JUL-21 | DEC-21 | Severe RoW encountered in a section of 3.4km at Village: Metala Dist: Purulia, WB. Already taken up with Administration, which is expected to be resolved soon. Revised line length is 207.5 CKM
3 | MTPS- Ranchi (PG) (Bypassing Gola SS) | S/C | 220 | 228 | 784 | 779 | 776 | 224.05 | JUL-21 | DEC-21 | Severe RoW encountered in a section of 3.4km at Village: Metala Dist: Purulia, WB. Already taken up with Administration, which is expected to be resolved soon. Revised Line Length is 228.5 CKM.
4 | Parulia - Burdwan line | S/C | 220 | 204 | 337 | 322 | 304 | 117 | JUL-19 | SEP-21 | Work in Progress after getting clearance from IAF. Clearance from Railways is awaited and continuos persuasion with Railway Authority is being done. Revised Line Length is 204 CKM
5 | Ramgarh - Ranchi (PG) (Bypassing Gola SS) (Balance portion) | S/C | 220 | 95 | 355 | 355 | 355 | 95 | JUL-21 | SEP-21 | Commissioned 08/21.
NHPC LIMITED(NHPC)
1 | LILO of Lakhwar HEP- Muzaffarnagar at Vyasi HEP | D/C | 220 | [5 empty] | JAN-17
POWERGRID (Consultancy Work)(PGCONSULTANCY)
1 | (J&K) LILO of Leh - Kharu line | S/C | 66 | 16.19 | 97 | 55 | 16 | 1 | MAY-17 | MAY-17
2 | (J&K) LILO of Leh - Nimmo line | S/C | 66 | 2.15 | 13 | 13 | 9 | 1 | MAY-17 | MAY-17
3 | (Sikkim) Chungthang - Lachen line | D/C | 66 | 44 | 126 |  |  |  | DEC-18 | APR-19
4 | (Sikkim) Chungthang - LILO point of Rabon - Malting line | D/C | 66 | 8 | 23 |  |  |  | DEC-18 | SEP-17
5 | (Sikkim) Dikchu Pool - Makha line | D/C | 66 | 18 | 114 |  |  |  | DEC-18 | MAR-19
6 | (Sikkim) Khamdong - Makha line | S/C | 66 | 4 | 86 |  |  |  | DEC-18 | MAR-19
7 | (Sikkim) Khamdong - Temi line | S/C | 66 | 8 | 69 |  |  |  | DEC-18 | MAR-19
8 | (Sikkim) Kumrek - Rorathang line | D/C | 66 | 10 | 103 |  |  |  | DEC-18 | MAR-19
9 | (Sikkim) Parbing - Pangthang line | D/C | 66 | 14 | 86 |  |  |  | DEC-18 | MAR-19
10 | (Sikkim) Parbing - Sichey line | S/C | 66 | 6 | 40 |  |  |  | DEC-18 | MAR-19
11 | (Sikkim) Parbing - Tadong line | S/C | 66 | 4 | 67 |  |  |  | DEC-18 | MAR-19
12 | (Sikkim) Rorathang - LILO point on Pakyong - Rongli line | D/C | 66 | 10 | 29 |  |  |  | DEC-18 | MAR-19
13 | (Sikkim) Samardong - Kumrek line | D/C | 66 | 22 | 103 |  |  |  | DEC-18 | MAR-19
14 | (Sikkim) Samardong - Mamring line | S/C | 66 | 10 | 45 |  |  |  | DEC-18 | MAR-19
15 | (Sikkim) Samardong - Namthong line | S/C | 66 | 7 | 86 |  |  |  | DEC-18 | MAR-19
16 | (Sikkim) Singhik - Mangan line | S/C | 66 | 10 | 57 |  |  |  | DEC-18 | MAY-18
17 | (Sikkim) Singhik - Passidong line | S/C | 66 | 20 | 114 |  |  |  | DEC-18 | MAR-19
18 | (Assam) Rangia - Amingaon line | D/C | 220 | 33 |  |  |  |  | DEC-18 |  | Yet to be awarded.
19 | (Assam) Tinsukia - Behiating (new Dibrugarh) | D/C | 220 | 55 |  |  |  |  | DEC-18 |  | Yet to be awarded.
20 | (Maghalaya) Byrnihat (Killing) - Mawngap - New Shillong line | D/C | 220 | 244 | 369 |  |  |  | DEC-18 | SEP-19
21 | (Nagaland) New Kohima - Mokokchung (PG) | S/C on D/C | 220 | 92 |  |  |  |  | DEC-18 |  | Yet to be awarded.
22 | (PMDP - Jammu) LILO of Hiranagar - Gladni at Chowadhi | S/C | 220 | 16 | 0 | 0 | 0 |  | MAR-19 | NOV-19 |  Contract awarded. Chowadhi Substation land yet to be handed over to POWERGRID.
23 | (PMDP - Jammu) LILO of Thein - Hiranagar at Kathua-II (Ghatti) | D/C | 220 | 12 | 14 | 8 | 0 |  | MAR-19 | NOV-19 |  Tower foundation work in progress and 08/14 locations completed. Land acquisition matter taken up with concerned revenue authorities & JKPDD regarding framing of land papers of all 14 locations.
24 | (PMDP - Jammu) Samba(JK) - Jatwal(PG) | D/C | 220 | 11 | 25 | 15 | 0 |  | MAR-19 | NOV-19 |  Tower foundation work in progress and 15/25 locations completed. Land acquisition matter taken up with concerned revenue authorities & JKPDD. Preparation of land papers yet to start.
25 | (Sikkim) Dikchu Pool - Rangpo (Samardong) (twin) | D/C | 220 | 50 |  |  |  |  | DEC-18 | SEP-18
26 | (Sikkim) Dikchu Pool - Singhik | D/C | 220 | 46 |  |  |  |  | DEC-18 | JUN-19
27 | (Sikkim) Rangpo (PG) - Samardong | D/C | 220 | 4 | 34 |  |  |  | DEC-18 | SEP-18
28 | (Sikkim) Singhik - Chungthang | D/C | 220 | 44 | 83 |  |  |  | DEC-18 | APR-19
29 | (Arunachal Pradesh) Along - Kambang line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
30 | (Arunachal Pradesh) Along - Yingkiong line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
31 | (Arunachal Pradesh) Changlang - Jairampur line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
32 | (Arunachal Pradesh) Chimpu (Itanagar) - Holongi line | S/C on D/C | 132 | 20 |  |  |  |  | DEC-18 |  | Yet to be awarded.
33 | (Arunachal Pradesh) Daporijo - Nacho line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
34 | (Arunachal Pradesh) Deomali - Khonsa line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
35 | (Arunachal Pradesh) Gerukamukh - Likabali line | S/C on D/C | 132 | 60 | 0 | 0 | 0 |  | DEC-18 |  | Yet to be awarded.
36 | (Arunachal Pradesh) Jairampur - Miao line | S/C | 132 | 40 |  |  |  |  | DEC-18
37 | (Arunachal Pradesh) Kambang - Mechuka line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
38 | (Arunachal Pradesh) Khonsa - Changlang line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
39 | (Arunachal Pradesh) Khonsa - Longding line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
40 | (Arunachal Pradesh) Khupi - Seppa line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
41 | (Arunachal Pradesh) Likabali - Niglok line | S/C on D/C | 132 | 75 | 293 | 0 | 0 |  | DEC-18 | NOV-19 | Yet to be awarded.
42 | (Arunachal Pradesh) LILO of Daporijo - Along 132 KV S/C at Basar | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
43 | (Arunachal Pradesh) Miao - Namsai (PG) line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
44 | (Arunachal Pradesh) Naharlagun - Banderdewa line | S/C on D/C | 132 | 25 |  |  |  |  | DEC-18 |  | Yet to be awarded.
45 | (Arunachal Pradesh) Naharlagun - Gerukamukh line | S/C on D/C | 132 | 90 |  |  |  |  | DEC-18 |  | Yet to be awarded.
46 | (Arunachal Pradesh) Niglok - Pasighat New (Napit) | S/C on D/C | 132 | 30 |  |  |  |  | DEC-18 |  | Yet to be awarded.
47 | (Arunachal Pradesh) Palin - Koloriang line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
48 | (Arunachal Pradesh) Pasighat New (Napit) - Pasighat Old | S/C on D/C | 132 | 15 |  |  |  |  | DEC-18
49 | (Arunachal Pradesh) Pasighat Old - Mariyang line | S/C on D/C | 132 | 80 |  |  |  |  | DEC-18 |  | Yet to be awarded.
50 | (Arunachal Pradesh) Rilo - Sagali line | S/C on D/C | 132 | 55 |  |  |  |  | DEC-18 |  | Yet to be awarded.
51 | (Arunachal Pradesh) Rilo - Seijosa line | S/C on D/C | 132 | 85 |  |  |  |  | DEC-18 |  | Yet to be awarded.
52 | (Arunachal Pradesh) Roing (PG) - Anini line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
53 | (Arunachal Pradesh) Roing (PG) - Dambuk line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
54 | (Arunachal Pradesh) Sagali - Naharlagun line | S/C on D/C | 132 | 45 |  |  |  |  | DEC-18 |  | Yet to be awarded.
55 | (Arunachal Pradesh) Seppa - Rilo line | S/C on D/C | 132 | 55 |  |  |  |  | DEC-18 |  | Yet to be awarded.
56 | (Arunachal Pradesh) Tawang - Lumla line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
57 | (Arunachal Pradesh) Tezu (PG) - Halaipani line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
58 | (Arunachal Pradesh) Yingkiong - Tuting line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
59 | (Arunachal Pradesh) Ziro (PG) - Palin line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
60 | (Arunachal Pradesh) Ziro (PG) - Ziro New line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
61 | (Arunachal Prades) Seppa - Bameng line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
62 | (Assam) Amingaon - Hazo line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
63 | (Assam) Dhemaji - Silapathar line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
64 | (Assam) Kahilipara - Guwahati Medical college ( Including 2 km cable) | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
65 | (Assam) Kamakhya - Paltan Bazar | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Awarded.
66 | (Assam) LILO of Golaghat - Bokajan line at Sarupathar | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
67 | (Assam) LILO of Jorhat (Gormur) - Nazira at Teok. | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
68 | (Assam) LILO of Kamalpur - Sishugram line at Amingaon S/S | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
69 | (Assam) LILO of one circuit of Rangia - Rowta line at Tangla | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
70 | (Assam) Rupai - Chapakhowa line (including 2 km cable) | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
71 | (Assam) Sonabil - Tezpur (New) line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
72 | (Maghalaya) LILO of both circuits of MLHEP - Khliehriat line at Mynkre | D/C | 132 | 34 | 99 |  |  |  | DEC-18 | SEP-19
73 | (Maghalaya) Phulbari - Ampati line | D/C | 132 | 138 | 239 |  |  |  | DEC-18 | SEP-19
74 | (Manipur) Imphal (PG) - Ningthoukhong line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
75 | (Manipur) Kakching - Churachandpur (2nd ckt) line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
76 | (Manipur) Kakching - Kongba (2nd Ckt) line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
77 | (Manipur) LILO of one circuit of Kongba - Kakching line at Thoubal S/S | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
78 | (Manipur) LILO of Yurembam (Imphal-State) - Karong line at Gamphajol | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
79 | (Manipur) Rengpang - Tamenlong line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
80 | (Manipur) Yaingangpokpi - Kongba (2nd Ckt) line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
81 | (Manipur) Yuremum - Karong - Mao (Manipur - Nagaland border) section of Yuremum-Karong-Kohima line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
82 | (Mizoram) Chawngte - S. Bungtlang line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
83 | (Mizoram) Lungsen - Chawngte line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
84 | (Mizoram) W. Phaileng - Marpara line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
85 | (Nagaland) LILO of Kohima - Meluri (Kiphire) at New Kohima | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
86 | (Nagaland) LILO of Kohima - Wokha line at New Kohima | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
87 | (Nagaland) LILO of Mokokchung (Nagaland) - Mariani (Assam) line at Longnak | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
88 | (Nagaland) New Kohima (Zadima) - New Secretariat Complex Kohima line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
89 | (Nagaland) Tuensang - Longleng line | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
90 | (Nagaland) Wokha (Doyang River) - Zunheboto - Mokokchung (Nagaland) | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
91 | (PMDP - Kashmir) Waganpora - Khanyar (Cable) | D/C | 132 | 10 | 0 | 0 | 0 |  | MAR-20 | NOV-19 | Route survey completed and report approved. Cable received at site.
92 | (Sikkim) Dikchu Pool - Parbing line | D/C | 132 | 42 | 96 |  |  |  | DEC-18 | MAR-19
93 | (Sikkim) LILO of Rangit - Melli (Power Deptt. Sikkim) 132 kV S/C at Manpur line | D/C | 132 | 4 |  |  |  |  | DEC-18 |  | Yet to be awarded.
94 | (Sikkim) LILO of Rangit - Melli (Power Deptt. Sikkim) 132 kV S/C at Namchi line | D/C | 132 | 4 |  |  |  |  | DEC-18 |  | Yet to be awarded.
95 | (Tripura) Bagafa - Belonia line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
96 | (Tripura) Bagafa - Satchand (utilizing the corridor of existing Bagafa - Satchanda 66 kV line) | S/C on D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
97 | (Tripura) Belonia - Sabroom line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
98 | (Tripura) Kailasahar - Dharmanagar line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
99 | (Tripura) LILO of Agartala (79 Tilla) - Dhalabil (Khowai) line | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
100 | (Tripura) LILO of Ambassa - P.K. Bari at Manu | S/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
101 | (Tripura) LILO of one circuit of Surajmaninagar - Rokhia line at Gokulnagar | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
102 | (Tripura) Rabindra Nagar - Belonia line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
103 | (Tripura) Rabindra Nagar - Rokhia line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
104 | (Tripura) Udaipur - Amarpur line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
105 | (Tripura) Udaipur - Bagafa line | D/C | 132 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
106 | (Assam) LILO of Kamalpur - Kamakhya line at Amingaon S/S | S/C | 120 | 0 |  |  |  |  | DEC-18 |  | Yet to be awarded.
POWER GRID CORPORATION OF INDIA LIMITED(PGCIL)
1 | Ajmer (PG) - Phagi line | D/C | 765 | 268 | 0 | 0 | 0 | 268 |  | MAY-21 | Commissioned 04/21.
2 | Aurangabad - III - Aurangabad (PG) | 2xS/C | 765
3 | Fatehgarh-II PS - Bhadla-II section (PGCIL-RTM) | D/C | 765 | 374 | 508 | 508 | 508 | 374 | JUN-21 | SEP-21 | Commissioned 08/21.
4 | Kurnool-III - Kurnool (New) (PGCIL-RTM) | D/C | 765 | 0 | 0 | 0 | 0 |  |  | DEC-19 | Length of the line is to be provided.
5 | Kurnool - III - Maheshwaram (PG) (PGCIL-RTM) | D/C | 765 | 0 | 0 | 0 | 0 |  |  | DEC-19 | Length of the line is to be provided.
6 | LILO of both Ckts. of Ajmer - Bikaner line at Bhadla-II PS (PGCIL-RTM) | D/C | 765 | 527 | 722 | 722 | 722 | 527 | JUL-21 | JUL-21 | Line Test Charged
7 | LILO of both Ckts. of Fatehgarh (TBCB) - Bhadla (PG) line at Fatehgarh-II PS (PGCIL-RTM) | D/C | 765 | 158 | 215 | 215 | 215 | 156 | JUL-21 | AUG-21
8 | LILO of Mainpuri -Gr. Noida S/C line at Jawaharpur TPS (J-FTL-TBCB) | S/C | 765 | 0
9 | LILO of Tilaiya - Balia line at Gaya | D/C | 765
10 | Medinipur - Jeerat (New) (PM-JTL-TBCB) | D/C | 765 | 338 | 461 | 461 | 461 | 338 | MAY-21 | AUG-21 | Physical work of the line completed. Commissioning matching with the completion of Jeerat substation.
11 | Reconfiguration of BhujPS- Lakadia PS as to establish Bhuj-II-Lakadia line as well as Bhuj-II-Bhuj-II line | D/C | 765 | 212 | 284 | 209 | 167 | 40 | JAN-22 | AUG-21 | Work has been affected due to COVID-19 pandemic. Progress also affected because of very heavy rain fall in Gujarat in Aug/Sep'20. Severe RoW because of delay in finalization of compensation rate by local administration. Recently compensation orders issued by local administration after joint hearing with POWERGRID & Villagers. Due to serious RoW, survey of 16 km line route spreaded in two villages near Bhuj-II Substation are still balance, affecting 45 nos. locations.
12 | Vindhyachal - Varansai line | D/C | 765 | 379 | 0 | 0 | 0 | 379 |  | AUG-21 | Commissioned 07/21.
13 | Vindhyanchal PS - Varanasi line ( WR-NR PTL -TBCB) | D/C | 765 | 379 | 521 | 521 | 520 | 368 | JUL-21 | JUL-21 | Stage -I forest clearance of UP portion obtained on 14.09.20. Working permission for Mirzapur division received on 29.10.20. Wildlife proposal cleared by NBWL. NBWL in their clearance advised to cross river using 765 kV U/G Cable. Technology is not available world wide. Matter was taken up with SBWL/ NBWL and clarification in this regard issued on 17th June'20. In MP portion, delay in tree felling by forest deptt. also affected foundation works. Presently tree felling in stringing stretches are in progress.
14 | Leh-Kharu (And LILO of Leh-Nimmo) | D/C | 66 | 17 | 0 | 0 | 0
15 | Bhadla-II PS-Bhadla (PG) (Twin HTLS) (PGCIL-RTM) | D/C | 400 | 97 | 135 | 135 | 135 | 95 | JUL-21 | AUG-21 | Length of the line: 97 Ckm.
16 | Darbhanga - Sitamarhi (New) line (Ckt-II) line | D/C | 400 | 80 | 0 | 0 | 0 | 80 |  | MAY-21 | Commissioned 04/21.
17 | Diversion of Dhauliganga - Bareilly line (operated at 220kV) at Bareilly end from Bareilly (UP) to Bareilly (PG) line | D/C | 400 | 17 | 27 | 27 | 27 | 15 | DEC-19 | DEC-21 | All works completed except stringing at tapping point. Commissioning of line through contingency arrangement was discussed in the NRPC -TP meeting held in Feb'21, same has not been agreed by NRPC-TP from commercial point of view, hence line will be commissioned matching with 220 KV arrangement between Jauljivi & Pithoragarh.
18 | Edayarpalayam (TANTRANSCO)- Udumulpet line (Q) | D/C | 400 | 94 | 137 | 137 | 137 | 94 | FEB-20 | AUG-21 | Commissioned 07/21.
19 | Farakka - Malda (Reconductoring) | D/C | 400 | 86 | 0 |  |  | 86 | NOV-16 | MAR-16 | Line charged in Mar'16.
20 | Jawaharpur TPS-Firozabad 400kV D/C (Q) line (J-FTL-TBCB) | D/C | 400 | 0
21 | Jeerat (New) - Jeerat (WBSETCL) (PM-JTL-TBCB) | D/C | 400 | 51 | 81 | 81 | 81 | 51 | MAY-21 | AUG-21 | Physical work of the line completed. Commissioning matching with the completion of Jeerat substation.
22 | Jeerat (New) - Subhasgram (PM-JTL-TBCB) | D/C | 400 | 214 | 312 | 261 | 222 | 66 | JUL-20 | OCT-21 | Severe ROW being faced.
23 | Jigmeling - Alipurdauar line (Q) (India Side) | D/C | 400 | 326 | 466 | 466 | 466 | 326 | JAN-21 | JUL-21 | Commissioned 06/21 (Late Reported).
24 | Khetri - Sikar (PG) line | D/C | 400 | 156 | 207 | 207 | 207 | 154 | SEP-21 | AUG-21 | Work affected due to heavy raining
25 | Kishenpur - Ratle, (Dulhasti- Kishenpur Second Ckt stringing extending up to Ratle HP) | S/C | 400 |  | 0 | 0 | 0
26 | LILO of both ckt. Dhauliganga - Bareilly (PG) line at Jauljivi | D/C | 400 | 7 | 13 | 13 | 13 | 4.2 | DEC-19 | DEC-21 | All works completed except stringing at tapping point. Commissioning of line through contingency arrangement was discussed in the NRPC meeting held in Feb'21, same has not been agreed by NRPC, hence line will be commissioned matching with 220 KV arrangement between Jauljivi & Pithoragarh.
27 | LILO of both Ckt. Kishanganj - Patna (Q) line Saharsa (ERSS XXITL - TBCB) | D/C | 400 | 150 | 211 | 211 | 211 | 149.4 | AUG-21 | SEP-21 | Progress is getting severely affected due to water logging. Work has also been affected due to COVID-19 pandemic.
28 | LILO of Both Ckt of Bawana - Mandola at Rajghat | D/C | 400 | 116 |  |  |  |  | MAY-17 |  | Rajgath S/s annulled. Bays now constructed at Maharanibagh
29 | LILO of both Ckt. of RAPP - Shujalpur at Jeerapur PS (GEC-II) | D/C | 400 | 0
30 | LILO of both ckts of Bawana - Mandola at Maharanibagh | D/C | 400 | 104 | 89 | 82 | 79 | 93.4 | JUL-21 | OCT-21 | Working permission under FCA received in Mar'21. DPTA clearance yet to receive. Proposal pending with Minister (F), Delhi since Nov19. Foundation work was started but stopped due to COVID lockdown in Delhi, now re-started.
31 | LILO of Gaya-Chandwa(existing) at North Karanpura STPP (Interim) | M/C | 400 | 38 |  |  |  |  | DEC-18
32 | LILO of Jeerat (WBSETCL)  Subhasgram (PG) | D/C | 400 | 1 |  |  |  |  | JUL-20
33 | LILO of Jeerat (WBSETCL) - Subhasgram (PG) 400kV at Rajarhat (PM-JTL-TBCB) | D/C | 400 | 24 | 37 | 0 | 0 |  |  | JUL-20 | Line deleted from scope.
34 | LILO of Kishanganj (POWERGRID) - Darbhanga (DMTCL) (QUAD) line at Saharsa (New) | D/C | 400 | 78 | 114 | 98 | 81 | 2.8 | AUG-21 | OCT-21 | Severe RoW being faced in the Saharsa distt.
35 | LILO of one circuit of Dulhasti - Kishenpur at Ratle HEP. | D/C | 400
36 | LILOof one Ckt. of Agra South-Fatehabad (765kV) D/C line at 400kV at Firozabad (J-FTL-TBCB) | D/C | 400 | 0
37 | LILO of One Ckt of Bamnauli - Jhattikara at Dwarka-I | D/C | 400 | 17 | 41 | 35 | 28 | 0 | MAY-17 | OCT-21 | Working permission under FCA received in May'21. DPTA Proposal pending with Minister (F), Delhi since Apr20. Work in progress.
38 | LILO of Sagardighi - Subhasgram line at Jeerat | S/C | 400 | 2 | 8 | 8 | 8 | 2 |  | JUL-21 | Commissioned 06/21.
39 | LILO OUT of Teesta-III - Kishanganj at Rangpo | D/C | 400 | 15 | 35 | 35 | 35 | 23 | JUN-20 | AUG-21 | Work affected due to RoW in stringing at one section due to Tashi Choling trust. Progress also affected due to COVID-19 restrictions. Lockdown extended upto 14.07.2021.
40 | Lower Subhansiri - Biswanath Chariyali line -I | D/C | 400 | 359 | 480 | 374 | 257 | 0 | AUG-13 | AUG-22 | Initially work was stalled on a/c of local disturbance/ agitation against big dams. Contract was short closed as generation was not coming. Balance work of line awarded in Dec'20. As per communication dated 27.05.21 from NHPC 1st & 2nd Unit schedule preponed from May'23 to Aug'22.
41 | Lower Subhansiri - Biswanath Chariyali line -II | D/C | 400 | 371 | 515 | 376 | 227 | 0 | AUG-13 | MAY-23 | Initially work was stalled on a/c of local disturbance/ agitation against big dams. Contract was short closed as generation was not coming. Balance work of line awarded in Dec'20. As per communication dated 27.05.21 from NHPC 1st & 2nd Unit schedule preponed from May'23 to Aug'22.
42 | Mohindergarh - Bhiwani line | D/C | 400 | 122 | 181 | 181 | 179 | 86 | OCT-20 | SEP-21 | ROW Tower Erection: 1 no. in Bhiwani & 1 no. in Charkhi Dadri district. ROW Stringing: 9.662 km in Bhiwani, 4.98 km in Charkhi Dadri & 1 km in Mohindergarh district. District administration help required for resolving ROW.
43 | New Mariani - Misa | D/C | 400 | 2 | 0 | 0 | 0 | 2 |  | JUN-21 | Commissioned 05/21.
44 | New Neyveli TPP - Ariyalur (Villupuram) | D/C | 400 | 156 | 213 | 213 | 213 | 147 | JUL-19 | AUG-21 | Line charged in Jul'20 by connecting to one ckt of LILO section of Pugalur - Kalivandapattu 400 kV D/C line near Ariyalur S/s (as bays by TANTRANCO on Deposit work Basis are expected by Aug'21) .
45 | Neyveli TS-II - Neyveli TS-I | D/C | 400 | 14 | 0 | 0 | 0 |  | JUL-15
46 | Palatana - Surajmaninagar | D/C | 400 | 24 | 43 | 43 | 43 | 24 |  | AUG-21 | Commissioned 07/21.
47 | Pugalur HVDC-Edayarpalayam (TANTRANSCO) line (Q) | D/C | 400 | 105 | 149 | 149 | 14 | 105 | FEB-20 | AUG-21 | Commissioned 07/21.
48 | Pugalur HVDC - Thiruvalam line (Q) | D/C | 400 | 780 | 1109 | 1109 | 1109 | 750 | FEB-20 | AUG-21 | Severe ROW issue in Kalaikurchi & Tiruvannamalai districts in Tamil Nadu. Being resolved with the support of district administration. However progress is slow due to COVID Pandemic situation.
49 | Rajarhat - Purnea (excl. Farakka-Gokarna portion) | D/C | 400 | 645 | 1219 | 1219 | 1219 | 645 | APR-16 | JUL-20 | 400 KV S/C New Purnea-Gokarna line & 400 KV S/C New Purnea-Farakka line charged on 10.11.19 (both lines are section of 400 KV D/C Rajarhat-Purnea line). Farakka - Gokarna portion of 400KV D/C Rajarhat - Purnea line (236 Ckm) including both LILO's at Farakka & Gokarna commissioned in Mar'17. Balance portion of line is commissioned on 12.07.20.
50 | Re-conductoring of Maithon RB - Maithon line | D/C | 400 | 63 | 0 | 0 | 0 | 42 | AUG-21 | NOV-21 | Shutdown contraints from WBPTCL/ERLDC.
51 | Siliguri - Purnea | D/C | 400 |  | 0 | 0 | 0 |  | SEP-13 | MAY-20
52 | Sitamarhi (New) - Motihari line (Triple Snowbird) (ERSS XXITL-TBCB) | D/C | 400 | 171 | 230 | 230 | 230 | 171 | MAR-21 | MAY-21 | Commissioned 04/21.
53 | Tirunelveli PS - Tuitcorin PS (Quad) line-1 and 2 line | D/C | 400 | 48 | 33 | 33 | 33 | 24 | APR-17 | MAR-18 | Erection completed. Work has been slowed-down to match with Generation (ant. by Mar'18).
54 | Chandigarh S/s - Panchkula (PG) (incl. 10 KMs underground cable). | D/C | 220 | 52 | 56 | 53 | 51 | 43 | FEB-19 | SEP-21 | Work of downstream system (66 KV Cable) under progress by UT Chandigarh. 220 KV Underground cable laying completed. Work held up at 5 locations due to ROW issues. DM, SAS NAGAR issued orders u/s 16 of Indian telegraph act for removal of ROW on 09.11.2020. High Court stayed works on 16.11.2020. Next hearing on 20.08.2021 after repeated adjournments.
55 | Disconnection of LILO arrangement of Dhauliganga - Bareilly at Pithoragarh and connecting it to Jauljive | D/C | 220 | 50 | 74 | 72 | 70 | 42.08 | JUL-21 | DEC-21 | Stage-I forest clearance received on 31.10.19. Working permission received on 23.12.19. 5 no. locs. were affected due to pending Civil Aviation clearance. Revised proposed route submitted to AAI on 14.10.20. AAI vide letter dated 01.12.2020 has issued NOC with restricted height. Appeal under shielding clause was filed on 02.12.2020. Appellate Committee on Clearance, AAI in its meeting held on 17.12.2020 Appellate Committee, AAI in its meeting held on 17.12.2020 agreed to issue NOC for balance restricted 5 locations with the condition that conductor in span AP5 to AP6 should be replaced by underground cable. Accordingly, contract for cabling work awarded on 04.06.2021 with the completion schedule of 6 months.
56 | LILO of 220kV Firozabad (220kV)- Agra (765kV PG) line at 400kV Firozabad (J-FTL-TBCB) | D/C | 220 | 0
57 | Purnea - Purnea (New) | D/C | 220 | 2 | 0 | 0 | 0 | 2 | MAY-20 | DEC-19 | Re-conductoring work completed & charged.
58 | 132kV Firozabad (400kV)- Narkhi D/C line (J-FTL-TBCB) | D/C | 132 | 0 | 0 | 0 | 0
59 | LILO of 132kV Atmadpur -Barhan S/C line at 400kV Firozabad (J-FTL-TBCB) | S/C | 132 | 0
60 | LILO of Aizwol (PG) - Zemabawk at Melriat (PG) | D/C | 132 | 30 | 17 | 17 | 17 | 10 | DEC-12 | NOV-18 | Line commissioned in Nov'18.
61 | LILO of Gangtok - Melli at Rangpo | S/C | 132 | 19
62 | LILO of Ranganadi - Nirjuli at Pare HEP | D/C | 132 | 3 | 10 | 10 | 10 | 3 |  | FEB-18 | Line work completed. Test charged on 03.03.2018.
63 | Melriat (New) - Sihmui line | D/C | 132 | 12 | 20 | 20 | 20 | 12 | DEC-12 | NOV-18 | Line commissioned in Nov'18.
64 | Pasighat - Roing line. | S/C on D/C | 132 | 102 | 347 | 347 | 347 | 104 | DEC-12 | JUN-17 | Line commissioned in Jun'17.
65 | Re-conductoring of Agartala GBPP - Agartala (State) with HTLS conductor | D/C | 132 | 16 | 0 | 0 | 0 | 16 | MAY-18 | FEB-18 | Line commissioned in Feb'18.
66 | Re-conductoring of Imphal (PG) - Yurembam with HTLS conduuctor. | S/C | 132 | 1 | 0 | 0 | 0 | 1 | JUL-18 | APR-18 | Line commissioned in Apr'18.
67 | Roing - Tezu line | S/C on D/C | 132 | 73 | 244 | 244 | 244 | 72 | APR-12 | JUN-17 | Line commissioned in Jun'17.
68 | Silchar - Hailakandi (Contingency arrangement) | D/C | 132 | 60 | 110 | 110 | 110 | 60 |  | NOV-17 | Part line commissioned (35Ckm) through contingency in Jun'12. Balance line commissioned in Nov'17.
69 | Tezu - Namsai line. | S/C on D/C | 132 | 96 | 332 | 332 | 332 | 95 | DEC-12 | JUL-18 | Line commissioned in Jul'18.
REC Transmission Projects Company limited(RECTPCL)
1 | (PMDP - Jammu) LILO of Barn - Kishanpur at Nagrota | S/C | 220 | 10 | 0 | 0 | 0 |  | MAR-19 |  | Due to non-availability of land, work could not commence though agency is ready for mobilization.
2 | (PMDP - Leh) Drass - Padum (Zanaskar) line | S/C | 220 | 207 | 0 | 0 | 0 |  | MAR-19 |  | Tender shall be published immediately after getting clearance from the JKPDD/PGCIL & sanction of additional fund requirement by MoP.
3 | (PMDP - Leh) Phyang (PGCIL) - Diskit (Nubrai) line | S/C | 220 | 100 | 0 | 0 | 0 |  | MAR-19 |  | Tender shall be published immediately after getting clearance from the JKPDD/PGCIL & sanction of additional fund requirement by MoP.
ASSAM ELECTRICITY GRID CORP. LIMITED(AEGCL)
1 | Sonabil - Biswanath Chariali | S/C | 220 | 40 | 136 | 133 | 62 | 0.2 | MAR-21 | MAR-21 | RoW issues at many locations.
2 | Agia-Sonapur (Hatchingmari) S/C line D/C tower | S/C | 132 | 102.51 | 387 | 363 | 284 | 0 |  | NOV-19 | RoW issues many locations. Change in scope of work due to technical issues.
3 | Amguri solar park - Mariani line (GEC-II) | D/C | 132 | 0 | 5 | 0 | 0 |  |  | MAR-20 | Re-survey done due to requirement of additional tower, additional financial implication involved which was submitted to APGCL for deposit
4 | Barnagar-Barpeta line on D/C tower | D/C | 132 | 68 | 0 | 0 | 0 | 0 |  | AUG-19 | The scope was changed to LILO of Shaligaon- Nalbari line at Barpeta GSS.
5 | BTPS - Kokrajhar line | S/C on D/C | 132 | 10 | 39 | 39 | 39 | 10 | DEC-13 | JUN-16 | Line charged on 30.06.2016.
6 | BTPS (salakati)-APM line S/C on D/C tower | S/C | 132 | 42 | 163 | 115 | 84 | 0 |  | MAR-20 | RoW issues at many locations. Change in scope of work due to technical issues.
7 | Hailakandi-Karimganj line on D/C tower | S/C | 132 | 26 | 93 | 13 | 0 | 0 |  | DEC-20 | 1. Contract agreement cancelled due to contractual failure. 2. Work order issued for supply of stub, superstructure,
8 | Kokrajhar - Bilashipara - Gauripur | S/C on D/C | 132 | 63 | 203 | 203 | 203 | 63 | SEP-13 | NOV-19 | Kokrajhar to Bilashipara charged on 24.06.16 and Bilashipara to Gauripur charged on 14.06.2016
9 | Kukurmara - Azara line | S/C on D/C | 132 | 5 | 29 | 29 | 29 | 6 | DEC-11 | NOV-19 | Court case pending at Loc-19. Stringing of Railway and Highway crossing left to be done.
10 | Kukurmara(Mirza)-Boko | S/C on D/C | 132 | 6 | 0 | 0 | 0 |  |  |  | Proposal was dropped.
11 | LILO of both ckt of Depota - Gohapur at Sonabil S/S | 2xD/C | 132 | 3 | 6 | 6 | 6 | 3 | NOV-13 | JUN-16 | Charged on 31.08.2015.
12 | LILO of Dhaligaon- Bornagar line at Barpeta GSS (Package-A) | D/C | 132 | 23.6 | 96 | 63 | 33 | 0 |  | APR-20 | ROW issues at many locations. change in scope of work due to technical issues. (LILO to Barpeta GSS is from Dhaligaon- Nalbari line, not from Dhaligaon-Barnagar line)
13 | LILO of one ckt of Rowta-Depota at Dhekiajuli | S/C | 132 | 2.07 | 8 | 0 | 0 | 0 |  | JUL-17 | One tower excavation work completed
14 | LILO of one ckt. of Rowta-Depota line-1 at Dhekiajuli (Pkg B) | D/C | 132 | 2 | 8 | 8 | 8 | 2 |  | MAY-18 | Test Charged on 30.01.18.
15 | LILO to Barpeta GSS from 132 kV Dhaligaon-Bornagar line | D/C | 132 | 23.6
16 | Sonapur - Chandrapur line | D/C | 132 | 28 | 55 | 53 | 51 | 20 | NOV-13 | MAR-18 | Completed and Charged on 10.03.2018.
17 | Sonapur - Jagirod line | D/C | 132 | 52 | 107 | 107 | 107 | 24 | NOV-13 | DEC-20 | Due to ROW issues stringing is not completed. (Forest clearance issues).
BIHAR STATE POWER TRANSMISSION COMPANY LIMITED(BSPTCL)
1 | LILO of ckt. III&IV (Quad) Patna - Balia at Naubatpur (New) | D/C | 400 | 6 | 0 | 0 | 0 |  |  |  | M/s BGCL
2 | LILO of Nabinagar -II - Patna (PG) at Jakkanpur (New) | D/C | 400 | 7 | 0 | 0 | 0 |  |  |  | M/s BGCL
3 | LILO of (Quad) Barh - Patna at Bakhtiyarpur (New) | D/C | 400 | 10 | 61 | 49 | 43 |  | APR-21 | APR-21 | ROW issues.
4 | 2nd Circuit stringing of 220kV Darbhanga (400/220)-Samastipur (New) line | D/C | 220 | 48 | 0 | 0 | 0 | 7.5 | OCT-19 | OCT-20 | Work under progress
5 | Amnour- Digha | D/C | 220 | 48 | 0 | 0 | 0 |  | JAN-22 | JAN-22
6 | Bakhtiyarpur (New) - Fatuha (BSPTCL) | D/C | 220 | 45 | 157 | 142 | 107 | 0 | APR-21 | APR-21 | Work under progress.
7 | Bakhtiyarpur (New) - Hathidah (New) | D/C | 220 | 31 | 109 | 68 | 35 | 0 | APR-21 | APR-21 | Work under progress.
8 | Bakhtiyarpur (New) - Sheikhpura (New) | D/C | 220 | 43 | 157 | 125 | 86 | 0 | APR-21 | APR-21 | work under progress.
9 | Biharsharif - Asthawan (New) | D/C | 220 | 40 | 0 | 0 | 0 |  | MAY-21 | MAY-21
10 | Bihta (New) - Bihta | D/C | 220 | 36 | 74 | 74 | 70 | 32 | JUL-15 |  | charged
11 | Bihta-Sipara (New) | D/C | 220 | 118 | 146 | 146 | 143 | 78 |  |  | This is the Same line as mentioned in Sr. no.7 -Gaurichak-Bihta(New) .This may be deleted.
12 | Karmnasa (New) - Pusauli (BSPTCL) (TM) | D/C | 220 | 60 | 127 | 52 | 26 | 0 |  | AUG-20 | NOA issued and Work under progress.
13 | LILO of Ara (PG) - Pusauli (PG) at Dumraon GIS | D/C | 220 | 50 | 0 | 0 | 0 |  |  |  | M/s BGCL
14 | LILO of Begusarai - Biharsarif at Mokama line | D/C | 220 | 6 | 0 | 0 | 0 |  | OCT-19 |  | M/s BGCL
15 | LILO of Gaya (PG) - Sonenagar at both Bodhgaya (BSPTCL) and Chadauti (New) | D/C | 220 | 41 | 157 | 128 | 21 | 0.95 | MAY-20 | MAY-21 | NOA issued on 21.01.2019 and work under progress.
16 | LILO of Khagaul (BSPTCL) - Sipara (BSPTCL) at Jakkanpur (New) | S/C | 220 | 10 | 0 | 0 | 0 |  |  |  | M/s BGCL
17 | LILO of Purnea (PG) - Khagaria (New) at Korha (New) | D/C | 220 | 28 | 0 | 0 | 0 |  | JAN-20 | MAR-22 | land not finalised yet
18 | LILO of Sasaram - Sahupuri at Karmnasa (New) | D/C | 220 | 8 | 5 | 0 | 0 | 0 | APR-21 | APR-21 | Work in Progress.
19 | LILO of Sipara (BSPTCL) - Bihta (BSPTCL) at Jakkanpur (New) | D/C | 220 | 7 | 0 | 0 | 0 |  |  |  | M/s BGCL
20 | LILO oof Ara (PG) - Khagaul (BSPTCL) at Naubatpur (New) | D/C | 220 | 11 | 0 | 0 | 0 |  |  |  | M/s BGCL
21 | Muzaffarpur (PG) - Chhapra (New) | D/C | 220 | 65 | 207 | 134 | 123 | 8.5 | MAY-21 | MAY-21 | Work under progress.
22 | Muzaffarpur (PG) - Gouraul line | D/C | 220 | 20 | 70 | 55 | 55 | 3.14 | MAY-21 | MAY-21 | Work in Progress.
23 | Naubatpur (New) - Bhusaula (New) | D/C | 220 | 18 | 0 | 0 | 0 |  |  |  | M/s BGCL
24 | Naubatpur (New) - Bhusaula (New) | D/C | 220 | 18 | 0 | 0 | 0 |  |  |  | M/s BGCL
25 | Naubatpur (New) - Bihta (BSPTCL) | D/C | 220 | 25 | 0 | 0 | 0 |  |  |  | M/s BGCL
26 | Pusouli (New) - Dehri | D/C | 220 | 62 | 159 | 135 | 110 | 18 | JUN-21 | JUN-21 | work under progress
27 | Raxaul (New) - Gopalganj (TM/ Single Zebra) | D/C | 220 | 130 | 201 | 118 | 64 | 0 |  | JUN-20 | NOA issued on 21.01.2019 and work under progress.
28 | Saharsa (New) - Begusarai | D/C | 220 | 186 | 289 | 178 | 136 | 0 | AUG-21 | AUG-21 | NOA issued on 21.01.2019 and work under progress.
29 | Saharsa (New) - Khagaria (New) | D/C | 220 | 80 | 236 | 152 | 90 | 0 | JUL-21 | JUL-21 | NOA issued on 21.01.2019.Work under progress.
30 | Sheiikhopursarai-Asthawan (New) | D/C | 220 | 37 | 0 | 0 | 0 |  | MAY-21 | MAY-21
31 | Sitamarhi (New) - Motihari (New) | D/C | 220 | 120 | 0 | 0 | 0 |  |  |  | This is the Same line as mentioned in Sr. no.34-Sitamarhi(New)-Raxual
32 | Sitamarhi(New) - Motipur | D/C | 220 | 140 | 162 | 113 | 100 | 15 | APR-21 | APR-21 | NOA issued on 21.01.2019.Route survey completed and work under progress.
33 | Sitamarhi (New) - Raxaul (New) (Twin Moose) | D/C | 220 | 160 | 271 | 203 | 160 | 18 | JUL-21 | JUL-21 | NOA issued on 21.01.2019.Work under progress.
34 | Betia-Raxaul (2nd circuiting) | D/C | 132 |  | 0 | 0 | 0 |  |  |  | Completed
35 | Motihari-Bettia | D/C | 132 | 79 | 143 | 143 | 143 | 79 |  | MAY-17 | completed
36 | Motihari-Motihari | D/C | 132 | 78 | 142 | 142 | 142 | 78 |  | JUL-17 | Completed
37 | Motihari-Raxaul | D/C | 132 | 119 | 215 | 215 | 215 | 119 |  | OCT-17 | Completed
CHHATTISGARH STATE POWER TRANSMISSION CO. LTD.(CSPTCL)
1 | Bilaspur - Mopka DCDS line | D/C | 220 | 80 | 0 | 0 | 0 |  | MAR-22 |  | This line was re-planned as LILO of 220 KV Mopka -Bhatapara circuit & 220 KV Mopka- Siltara circuit on multi circuit tower at 220 KV S/s Dhardehi (Bilaspur) and these line were charged on dtd 25.09.2019
2 | Bilaspur - Suhela DCDS line | D/C | 220 | 220 | 0 | 0 | 0 |  | MAR-22 |  | This line was re-planned as LILO of 220 KV Mopka -Bhatapara circuit & 220 KV Mopka- Siltara circuit on multi circuit tower at 220 KV S/s Dhardehi (Bilaspur) and these line were charged on dtd 25.09.2019
3 | DCDS Raita - Parsada | D/C | 220 | 110 | 0 | 0 | 0 |  | MAR-20 |  | land for substation not finalized
4 | Dhamtari - Gurur DCDS line | D/C | 220 | 50 | 0 | 0 | 0 |  | MAR-19 | AUG-19 | This line is re-planned as Gurur-Kurud(Bangoli) , S.No. 7
5 | Janjgir Champa Ps - Mopka (GEC-II) | D/C | 220 | 0 | 0 | 0 | 0 |  |  |  | work not approved till date
6 | LILO of Bhatapara - Doma at Rita ( 400kV S/s) | D/C | 220 | 30 | 0 | 0 | 0 |  | MAR-22 |  | Estimate sanctioned
7 | LILO of Korba (E) - Siltara at DSPM | D/C | 220 | 3 | 7 | 7 | 7 | 2 | APR-21 | APR-21 | Work in Progress.
8 | LILO of Mopka - Siltara line at Raita. | D/C | 220 | 30 | 0 | 0 | 0 |  | MAR-22 |  | Estimate sanctioned
9 | Raita - Rakhi DCDS line on multi ckt tower | D/C | 220 | 140 | 0 | 0 | 0 |  | MAR-22 |  | work not approved till date
10 | Rajnandgaon Ps - Bhilai (GEC-II) | D/C | 220 | 0 | 0 | 0 | 0 |  |  |  | work not approved till date
DELHI TRANSCO LIMITED(DTL)
1 | Bawana - Kanjhawala at Barwala | D/C | 220 | 1 | [5 empty] | MAR-23
2 | Budella - Zakhira | D/C | 220 | 20 |  |  |  |  | MAR-20
3 | Dev Nagar - Subzi Mandi (U/G Cable) | D/C | 220 | 10 |  |  |  |  | MAR-22
4 | Harsh Vihar - Preet Vihar | D/C | 220 |  | 0 | 0 | 0 |  | FEB-16
5 | IP-Park Street-Electric Lane (Cable) | S/C | 220 | 18 | 0 | 0 | 0 |  | MAR-22 | MAR-22 | Work in Progress.
6 | Kashmiri Gate - Rajghat line | D/C | 220 | 10 | 0 | 0 | 0 |  |  |  | PGCIL yet to start the work.
7 | Kashmirigate - Timer Pur (U/G Cable) | D/C | 220 | 10 | 0 | 0 | 0 |  | DEC-21 | MAR-21 | 1. CPG has been submitted on 15.10.2019. 2. L2 Network has been approved on 15.10.2019. 3. Contract Agreement has been executed on 15.10.2019. 4. Cable route has been approved on 05.02.20. 5. PWD has granted Road Cutting Permission for 03 sections (1440 Mtrs) vide letter dated 19.02.2021 from Kashmere gate FOB to Chandgi Ram Akhada Red Light. 6. ROW Permission from Traffic Police has been received on 02.03.2021. 7. NMCD Road Cutting permission has been received on 02.03.2021. 8. The case file has been sent to Finance for making online payment towards ROW on 19.05.21 for the stretch Vikash Bhawan to Majnu Ka Tilla. However, Payment has been made online at GSDL Portal on 27.05.2021 by Finance Department. 9. PWD has granted Road Cutting Permission for 03 sections (1775 Meters - Section No 04,05,& 06 ) for the stretch between Vikash Bhawan II Bus Stop to Majnu Ka Tilla on 02/06/2021. 10. Cable has been laid in 03 sections (i.e in Section No.1,2&3) out of 09 section
8 | LILO of 2nd Ckt Kanjhawala - Njafgarh at Mundka | D/C | 220 | 7 | [5 empty] | MAR-21
9 | LILO of AIIMS - Ridge Valley at R.K.Puram | D/C | 220 | 5 | 0 | 0 | 0 |  |  | NOV-21 | 1. Preliminary Joint Survey has been carried out on 18.12.19. 2. CPG has been submitted on 20.12.2019. 3. Contract Agreement has been executed on 23.12.19. 4. L-2 network has been approved on 07.01.2020. 5. Drum length has been approved for all eight sections. 6. R.K.Puram-AIIMS Ckt-II (Bay No 206) has been charged on 29.03.2021 and thereafter R.K.Puram Ridge Valley Ckt-II (Bay No-212) has been charged on 30.03.2021 7. R.K.Puram-AIIMS Ckt-I (Bay no 207) has been charged on 31.03.2021 and thereafter R.K.Puram Ridge Valley Ckt-I (Bay No 211) has been charged on 31.03.2021. 8. Installation of Route markers has been completed.
10 | LILO of Bamnauli to DIAL D/C at Bhartal | D/C | 220 | 4 |  |  |  |  | MAR-20
11 | LILO of Electric Lane to Park Street at Dev Nagar (U/G Cable) | D/C | 220 | 10 | 0 | 0 | 0 |  | MAR-20 | NOV-21 | 1. CPG has been submitted on 20.12.2019. 2. Contract Agreement has been executed on 23.12.2019. 3. L-2 network has been approved on 06.01.2020. 4. Cable laying has been completed in 10 sections (section 2, 3, 4, 5, 6, 7, 8, 9, 10, 11) out of 12 sections. 5. Jointing work has been completed at 7 JBs (JB 3,4,5,6, 7, 8 & 9) out of 12 JBs. 6. JB 11 to JB12: Laying of Cable and back filling has been completed. 7. Laying of Optical fiber cable has been completed from JB# 2 to JB#12.
12 | LILO of first ckt of double ckt of Pragati - Sarita Vihar at maharani Bagh | D/C | 220 | [5 empty] | MAR-15
13 | LILO of Maharanibagh - Gazipur at Mayur Vihar | D/C | 220 | 0.2 | [5 empty] | MAR-22
14 | LILO of Maharanibagh - Masjid Moth at Nehru Place | D/C | 220 | 0.2 | [5 empty] | MAR-21
15 | LILO of Mandola - Gopalpur at Budhpur/Nathupura | D/C | 220 | 2 | [5 empty] | MAR-22
16 | LILO of Narela - Mandola at Tikri Khurd | D/C | 220 | 3 | 10 | 5 | 5 |  | JUN-19 | MAR-19
17 | LILO of one ckt of Bamnauli - Naraina Ckt-I at Pappankalan-I | S/C | 220 |  | 2 | 2 | 2 | 0.2 | MAR-15 | NOV-17 | Work completed
18 | LILO of Pragati - Sarita Vihar at Maharanibagh | D/C | 220 | 1
19 | Maszid Moth - Tughlakabad (U/G) Cable | D/C | 220 | 16 | 0 | 0 | 0 |  | DEC-19 | APR-22 | 1. M/s UCL has been submitted CPG for supply and service contract. 2. An agreement of contract documents has been completed between DTL and M/s Universal Cables Ltd successfully on dated 22.02.2021. 3. L-2 network has been approved on dated 23.02.2021 4. M/s Universal Cable have submitted the GPR report and revised Route Drawings on 27.05.2021 for approval. 5.The Route Drawing is approved by Competent authority on dated 31.05.2021 6.Letter towards approval of Drum length schedule has been issued on 07.06.2021. 7. Letter has been sent to DDA (Horticulture) to provide the estimate for open cutting for the area in DDA park at Tughlakabad on dated 24.06.2021. 8. Road cutting permission has been applied on GSDL portal for stretch between 220kV Masjid moth S/stn to Local shopping centre GK-II near Bikanerwala. 9. Road cutting permission has been applied on GSDL portal for stretch between Majeediya Hospital to Alkhnanda Market
20 | Tughlakabad - R.K.Puram (U/G Cable) | D/C | 220 | 12 | 0 | 0 | 0 |  | MAR-20 | JUL-22 | 1. CPG has been submitted on 04.02.2021. 2. Contract Agreement has been executed on 11.02.2021. 3. L2 network has been approved on 02/03/2021. 4. Route drawing has been approved on 02/03/2021. 5. Drum length schedule has been approved on 02/03/2021. 6. Revised Route Drawing has been approved on 23.04.2021. 7. Revised Drum Length Schedule has been approved on 23.04.2021. 8. HDD work between section 10 and section 11 is in progress on Badarpur-Mehrauli road.
21 | Zakhira - Devnagar D/C U/G | D/C | 220 | 10 |  |  |  |  | MAR-21
DEPARTMENT OF POWER ARUNACHAL PRADESH(null)
1 | LILO of Ranganadi - Itanagar at Pare HEP | D/C | 132 | 5 | 12 | 12 | 12 | 5 |  | MAR-18 | Line work completed. a) RHEP Section: Charged on 06.07.2018. b) Itanagar Section: Charged on 07.07.2018.
2 | Pasighat-Roing -Tezu - Namsai 132kV S/c line (2nd ckt. stringing) (GEC-II) | S/C | 132 | 0
3 | Tezu pool - Tezu line (GEC-II) | D/C | 132 | 0
ELECTRICITY DEPARTMENT, GOVT. OF MANIPUR(ED, Manipur)
1 | Kakching - Churachandpur | S/C on D/C | 132 | 35 | 0 | 0 | 0 |  | OCT-17 |  | Work almost completed except two spans of 700 m due to forest clearance.
2 | Leimatak PH (NHPC) - Ningthoukhong 132 s/s 2nd ckt | S/C on D/C | 132 | 11 | 0 | 0 | 0 |  | NOV-17 |  | 35% work completed
3 | Moreh Line | S/C | 132 | 45 | 181 | 158 | 70 | 3 | SEP-17
4 | Thanlon line | S/C | 132 | 66 | 242 | 234 | 224 | 52 | SEP-17 | SEP-17
5 | Thoubal 400kV s/s - Kongba Yaingangpokpi , Hundung | D/C | 132 | 22 | 44 | 43 | 34 | 9 | AUG-17 | SEP-17
6 | Thoubal 4ookV s/s - Moreh 132kV s/s | D/C | 132 | 170 | 0 | 0 | 0 |  | MAR-18 |  | WIP
7 | Tipaimukh Line | S/C | 132 | 10 | 24 | 12 | 0 |  | DEC-17
8 | Yurembam S/S (State) 132kV- YurembamS/S(PGCIL) 132kVS/S 3rd ckt | S/C on D/C | 132 | 2 | 0 | 0 | 0 |  | NOV-17 |  | 35% work completed
ENERGY & POWER DEPARTMENT,GOVT. OF SIKKIM(SPD)
1 | Dikchu -Singhik | D/C | 220 | 22 |  |  |  |  | NOV-21
2 | Samardong - Dikchu Pool | D/C | 220 | 23 |  |  |  |  | OCT-21
GOA ELECTRICITY DEPARTMENT(ED-GOA)
1 | Colvale - Kadamba - Verna - Cuncolim line | D/C | 220 | 120 | [5 empty] | MAR-19 | Proposals have been forwarded to Government. The approcal is awaited from Finance Department.
2 | Colvale-Saligao | D/C | 220 | 80 |  |  |  |  | JUL-19
3 | Colvale - Tuem | D/C | 220 | 20 | [5 empty] | MAR-19 | Letter of Intent will be issued to RECTPCL shortly, who has been appointed as Project Management consultant(PMC). Necessary approvals have been obtatined from the Government.
4 | Ponda - Verna | M/C | 220 | 84 |  | 0 | 0 | 0 |  | MAR-19 | Proposals have been forwarded to Government. The approcal is awaited from Finance Department.
GUJARAT ENERGY TRANSMISSION CORP. LIMITED(GETCO)
1 | Dhuvaran-Chharodi Line | D/C | 765 | 240 | 0 | 0 | 0 |  |  | MAR-22
2 | Amreli - Kasor line | D/C | 400 | 460 | 680 | 633 | 591 | 222.83 |  | JUN-19 | W I P / Severe RoW problems
3 | Bhachunda - Bhuj Pool (PG) line | D/C | 400 | 220 | 0 | 0 | 0 |  |  | MAR-21 | Yet to award.
4 | Bhachunda - Varsana line (Twin AL-59) | D/C | 400 | 280 | 430 | 256 | 218 | 28.11 |  | DEC-21 | WIP
5 | Bhogat-Kalavad | D/C | 400 | 270 | 409 | 315 | 301 | 127.51 |  | DEC-21 | WIP.
6 | dhuvaran - Fedra (Quad) line | D/C | 400 | 140 | [5 empty] | MAR-22
7 | Hadala - Shapar line (Twin AL-59) | D/C | 400 | 124 | 200 | 195 | 180 | 99.65 | JUL-21 | JUN-21 | Severe ROW, COVID-19 and heavy rain.
8 | Kosamba- Achhalia | D/C | 400 | 140 | 0 | 0 | 0 | 0 |  | MAR-21 | Yet to award
9 | LILO of both ckt. Kakrapar - Vapi (PG) line at Chikhli S/s (Twin Moose) | D/C | 400 | 80 | [5 empty] | MAR-22
10 | LILO of Kasor-Amerli line at Fedra | D/C | 400 | 80 | [5 empty] | OCT-22
11 | LILO of Mundra - Hadala at Halvad. | D/C | 400 | 89 | 128 | 128 | 128 | 88.86 |  | OCT-21 | WIP (Repeated)
12 | LILO of one ckt Halvad - Vadavi line at Chharodi S/s (ACSR Twin Moose) | D/C | 400 | 60 | 411 | 336 | 225 | 139.89 |  | MAR-21 | WIP
13 | LILO of one ckt Kosamba-Chorania line at Fedra | D/C | 400 | 46 | 66 | 55 | 48 | 0 |  | MAR-19 | WIP
14 | LILO of one ckt. of planned Ukai - Kosamba line at new s/s near Chikhli | D/C | 400 | 120 | [5 empty] | MAR-22
15 | LILO of SSP- Asoj & SSP -Kasor lines at Achhalia S/S | D/C | 400 | 80 | 0 | 0 | 0 | 0 |  | MAR-21 | Yet to award
16 | Mundra (Adani) - Zerda line 1 | D/C | 400 | 640 | 997 | 491 | 293 | 0 |  | JUN-19 | W I P / Severe RoW problems
17 | Pipavav-Amreli | D/C | 400 | 150 | 0 | 0 | 0 | 0 |  | MAR-21 | Yet to award
18 | Sankhari-Prantij | D/C | 400 | 200 |  | 0 | 0 | 0 |  | MAR-21 | Yet to award
19 | Shapar - Pachham (Fedra) line (Twin AL-59) | D/C | 400 | 200 | 346 | 195 | 158 | 0 |  | JUN-21 | WIP
20 | Shapoorji Pallonji generating station | D/C | 400 | 220 | 0 | 0 | 0 | 0 |  | DEC-16 | Generation not coming
21 | Soja -erda line (Pkg-2) with Twin AL-59 Conductor | D/C | 400 | 135 | 200 | 198 | 197 | 126.53 | AUG-21 | DEC-21
22 | Soja - Zerda line (Pkg-1) with Twin AL-59 conductor | D/C | 400 | 134 | 198 | 198 | 198 | 128.87 | AUG-21 | DEC-21 | WIP/Severe RoW issue
23 | Vadinar(Essar)- Amreli (Balance) | D/C | 400 | 180 | 533 | 490 | 447 | 235.11 | NOV-09 | DEC-18 | WIP
24 | Varsana-halvad | D/C | 400 | 237 | 358 | 302 | 273 | 58.66 |  | MAR-19 | Tender to be invited at Risk & Cost of EPC Contractor.
25 | Wanakbori-Soja line (Pkg-2) with Twin AL-59 conductor | D/C | 400 | 91 | 139 | 138 | 135 | 54.28 | AUG-21 | DEC-21 | Work in Progress.
26 | Wanakbori TPS-Soja | D/C | 400 | 212 | 343 | 272 | 271 | 144.09 | DEC-19 | MAR-19 | WIP
27 | Amreli - Babara line (AL-59) | D/C | 220 | 50 | 84 | 84 | 84 | 49.25 |  | JUN-21 | Re-tender on 17-07-2018; Price bid under acceptence
28 | Amreli - Maglana line | D/C | 220 | 400 | 0 | 0 | 0 |  |  | MAR-21 | Tender to be done
29 | Babara - Gondal - II line | D/C | 220 | 320 | 0 | 0 | 0 |  |  | MAR-20 | Tender to be done
30 | BECL (Padva) - Botad line | D/C | 220 | 188 | 310 | 233 | 177 | 33.79 |  | MAR-21 | Tender on website and last date is 10.12.2018. (Risk & cost for Balance work).
31 | Bhachau - Radhanpur | D/C | 220 | 340 | 0 | 0 | 0 | 0 |  | MAR-22 | Yet to award.
32 | Bhatia - Kalavad line | D/C | 220 | 238 | 373 | 176 | 127 | 10.51 |  | MAR-20 | Tender on website and last date is 17.12.2018. (Risk & cost for Balance work).
33 | Bhogat - Moti Gop line (AL-59) | D/C | 220 | 140 | 225 | 129 | 116 | 2.02 |  | MAR-22 | WIP
34 | Bhogat - Ranavav line (AL-59) | D/C | 220 | 150 | 216 | 111 | 96 | 0 |  | DEC-21 | WIP.
35 | Chhatral - Dhanaj | D/C | 220 | 40 | 0 | 0 | 0 | 0 |  | MAR-22 | Yet to award
36 | Chikhli - Bhilad | D/C | 220 | 170 | 0 | 0 | 0 | 0 |  | MAR-22 | Yet to award
37 | Chorania - Botad | D/C | 220 | 104 | 172 | 143 | 135 | 19.68 |  | MAR-19 | WIP
38 | Chorania - Salejada line (AL-59) | D/C | 220 | 135 | 216 | 194 | 181 | 43.06 |  | DEC-21 | WIP .
39 | Fedra (Pachchham) - Dholera AA line with Twin AL-59 Conductor | D/C | 220 | 61 | 112 | 89 | 84 | 26.51 | JUN-21 | JUN-21
40 | Gavasad - Salejada line with AL-59 conductor | D/C | 220 | 194 | 327 | 295 | 243 | 80.76 | JUN-19 | JUN-19 | W I P / Severe RoW problems
41 | Hadala - Rajkot-II | D/C | 220 | 25 | 0 | 0 | 0 | 0 |  | MAR-23 | Yet to award
42 | Halvad - Sadla line with AL-59 conductor | D/C | 220 | 76 | 125 | 125 | 125 | 75.76 | JUL-21 | JUL-21 | Work in Progress.
43 | Hazaira (GSEC) - Mota | D/C | 220 | 111 | 182 | 111 | 96 | 41.82 |  | JUN-19 | Inter connection of Utran-Kosamba charged under stop gap arrangement (Kosamba-Mota & Utran-Mota) on 16.06.2018 as per system requirement.
44 | Jasdan - Gondal | D/C | 220 | 100 | 0 | 0 | 0 | 0 |  | MAR-22 | Yet to award
45 | Kalavad - Kangasiali line | D/C | 220 | 112 | 196 | 182 | 176 | 87.83 |  | DEC-20 | Tender under acceptance.
46 | Keshod - Keshod | D/C | 220 | 60 | 0 | 0 | 0 | 0 |  | MAR-24 | Yet to award
47 | Keshod - Veraval line | D/C | 220 | 180 | [5 empty] | MAR-21
48 | Keshod - Visavadar | D/C | 220 | 120 | 0 | 0 | 0 | 0 |  | MAR-22 | Yet toaward
49 | LILO f one ckt. Chandrapura - Godhara line at Halol | D/C | 220 | 20 | [5 empty] | MAR-20
50 | LILO of 220kV GSEG - Mora - Kim line at 220kV Velanja | M/C | 220 | 7 | 13 | 8 | 5 | 0 | JAN-18 | DEC-21 | WIP.
51 | LILO of Achhaliya-Jambuva line at Vyankatpura (Jarod) S/S | D/C | 220 | 125 | 130 | 130 | 130 | 72 |  | AUG-20
52 | LILO of Bhatia - Kalav ad - Kangasiyali at Khambhalia - II | D/C | 220 | 50 |  | 0 | 0 | 0 |  | MAR-21 | Yet to award
53 | LILO of both ckt. Kawas - Navsari (PG) line at Vesu S/s (2220kVu/g cable) | D/C | 220 | 5 | 0 | 0 | 0 |  |  | MAR-25
54 | LILO of both ckt Kawas - Nvasari (PG) line at Khajod S/s | D/C | 220 | 20 | 0 | 0 | 0 |  |  | MAR-21
55 | LILO of both Ckts. Otha - Sagapara line at Talaja | D/C | 220 | 21 | 36 | 36 | 36 | 4.46 | JUL-21 | JUL-21 | Severe ROW, COVID-19 and heavy rain.
56 | LILO of both ckt. Visavadar- Timbdi line at Keshod S/s | D/C | 220 | 100 | [5 empty] | MAR-21
57 | LILO of Chorania - Gondal at Rajkot-II | D/C | 220 | 25 | 0 | 0 | 0 | 0 |  | MAR-20 | Yet to award
58 | LILO of Chorania - Gondal at Shapar | D/C | 220 | 40 | 0 | 0 | 0 | 0 |  | MAR-21 | Yet to award
59 | LILO of Gavasad - Salejda line at Bil | D/C | 220 | 120 | [5 empty] | MAR-20
60 | LILO of Godhra -Kadana line at Lunawada | D/C | 220 | 5 | 223 | 223 | 214 | 80.09 |  | DEC-18 | WIP
61 | LILO of Jamnagar - Jetpur line-I at Sikka | D/C | 220 | 116 | 178 | 0 | 0 | 0 |  | MAR-21 | Yet to be awarded.
62 | LILO of Jetpur - Rajkot at Metoda | D/C | 220 | 5 | 0 | 0 | 0 | 0 |  | MAR-21 | yet to award
63 | LILO of Jetpur - Sardargadh line at Shapur s/s | D/C | 220 | 12 | 24 | 23 | 17 | 7.26 | SEP-21 | OCT-21 | Severe ROW, COVID-19 and heavy rain.
64 | LILO of Keshod - Timbdi line at Veraval | S/C | 220 | 8 | [5 empty] | MAR-20
65 | LILO of Lalpar - Sartanpar line at Wankaner S/s on M/C tower by dismentalling of existing 132 kv S/C Lalpar - Wankaner line | D/C | 220 | 40 | 70 | 65 | 56 | 60.98 |  | AUG-21 | WIP
66 | LILo of Morbi - Hadala line at Makansar S/s | D/C | 220 | 20 | [5 empty] | MAR-21
67 | LILO of of both ckt. GSEG - Kosamba line at Olpad S/s | D/C | 220 | 16 | [5 empty] | MAR-21
68 | LILO of one ckt Kasor - Gavasad line at Gotri S/s | D/C | 220 | 44 | 85 | 69 | 48 | 51.99 |  | DEC-21 | WIP
69 | LILO of one ckt. Wanakbori - Asoj line at Balsinor | D/C | 220 | 40 | [5 empty] | MAR-21
70 | LILO of pm ckt. GPPC- Savarkumdla line at Rajula S/s (ACSR Zerba) | D/C | 220 | 10 | 0 | 0 | 0 |  |  | MAR-23
71 | LILO of pne ckt GPEC - Karamsad lani at Bil | D/C | 220 | 20 | 0 | 0 | 0 |  |  | MAR-21
72 | LILO of Sartanpar - Wankaner line at Makansar S/s | D/C | 220 | 2 | [5 empty] | MAR-22
73 | LILO of Savarkundla - Visavadar at Bagasara S/s | D/C | 220 | 16 | 0 | 0 | 0 | 0 |  | MAR-20 | Yet to award
74 | LILo of Tarapur - Bhilad line at Umargaon | D/C | 220 | 10 | 33 | 12 | 6 | 0 |  | SEP-19 | WIP
75 | LILO of Tarapur - Vapi line at Umargaon | S/C | 220 | 10 | [5 empty] | MAR-20
76 | LILo of Ukai (Thermal) -Achhalia line - III at Virpore | D/C | 220 | 15 | 0 | 0 | 0 |  |  | MAR-21
77 | LILO of Ukat (Th) - Achhalia at Achhalia | D/C | 220 | 10 | 0 | 0 | 0 | 0 |  | MAR-20 | Yet to award
78 | LILO of Vadavi -Chatral at Santej (Dhanaj) | D/C | 220 | 51 | 88 | 69 | 60 | 0.6 |  | MAR-20 | "Tender re-invited for balance work at Risk & Cost of Contractor and last date of tender is 28.02.2018. Tender under acceptance."
79 | LILO of Vadavi - Chhatral line at Santej S/s | D/C | 220 | 51 | 91 | 91 | 91 | 50.27 | AUG-13 | MAR-20 | Tender under acceptance.
80 | LILO of Vadavi - Chhatral & Vadavi - Ganndhinagar TPS at Dhanaj S/s | D/C | 220 | 60 | [5 empty] | MAR-21
81 | LILo of Vapi - Bhilad line at Chikhli s/s | D/C | 220 | 150 | 0 | 0 | 0 |  |  | MAR-21
82 | LILO of Vapi - Chikhli & Bhilad - Chikhli lines at Chikhli | D/C | 220 | 150 | [5 empty] | MAR-20
83 | LILO of Wanakbori TPS - Zalod line at Savdasna Muvada | D/C | 220 | 270 | [5 empty] | MAR-22
84 | LLO of 220 kv Vadavi - Chhatral line at Santej S/s | D/C | 220 | 43 | 91 | 91 | 91 | 50 | MAR-14 | SEP-21 | Commissioned 08/21.
85 | Mitha - Katosan TSS line | D/C | 220 | 33 | 66 | 66 | 66 | 33 | JUN-21 | AUG-21 | Commissioned 07/21.
86 | Pipava - Bagasara line | D/C | 220 | 160 | [5 empty] | MAR-21
87 | Pipavav - Otha line | D/C | 220 | 100 | [5 empty] | MAR-21
88 | Pipavav - Rajula line | D/C | 220 | 80 | [5 empty] | MAR-21
89 | Pirana (PG) - Barejadi line | D/C | 220 | 50 | 88 | 86 | 80 | 25.92 |  | JUN-19 | WIP/ Severe RoW issue
90 | Pirana (PG) - Gatrad | D/C | 220 | 50 | 0 | 0 | 0 | 0 |  | MAR-22 | Yet to award
91 | Prantij - Agiyol | D/C | 220 | 60 | 0 | 0 | 0 | 0 |  | MAR-22 | Yet to award
92 | Prantij - Dhansura | D/C | 220 | 70 | 0 | 0 | 0 | 0 |  | MAR-24 | Yet to award
93 | Radhanesda - Vav (Khimanvas) line with AL-59 Conductor | D/C | 220 | 73 | 115 | 115 | 115 | 73 | MAY-21 | AUG-21 | Commissioned 07/21.
94 | Shapar - Babara line (AL-59) | D/C | 220 | 120 | 235 | 235 | 226 | 57.84 |  | MAR-20 | WIP
95 | Suva - Achhalia | D/C | 220 | 140 | 0 | 0 | 0 | 0 |  | MAR-23 | Yet to award
96 | Termination of GPEC - Haldarva at Achhalia | D/C | 220 | 90 | 0 | 0 | 0 | 0 |  | MAR-24 | Yet to award
97 | Utran - Kosamba Line-II | D/C | 220 | 86 |  |  |  |  | DEC-09
98 | Vadavi - Sanand (DFCC) line | D/C | 220 | 61 | 106 | 63 | 46 | 0 | APR-15 | MAR-22 | WIP
99 | Vadodara (PG) - Vyankatpura line | D/C | 220 | 30 | 60 | 57 | 57 | 28 |  | FEB-18 | WIP
100 | Vataman (PG) - Bagodara line | D/C | 220 | 160 | [5 empty] | MAR-21
101 | Virpore - Chikhli line | D/C | 220 | 120 | [5 empty] | MAR-20
102 | Vondh - Radhanpur line | D/C | 220 | 340 | [5 empty] | MAR-21
103 | Vyankatpura - Halol line | D/C | 220 | 100 | [5 empty] | MAR-20
104 | LILO of both circuits Sitac WF - Jasdan at Babara (GEC-I) | 2xD/C | 132 | 0 | 0 | 0 | 0 |  |  | JUN-20 | Price Bid Opened & amp; under approval
HARYANA VIDYUT PRASARAN NIGAM LIMITED(HVPNL)
1 | Bagun - Hisar (IA) line (GEC-II) | D/C | 220 | 0 | 0 | 0 | 0
2 | Barula - Mahindergarh line (GEC-II) | D/C | 220 | 0 | 0 | 0 | 0
3 | Bhiwani - Bhiwani | D/C | 220 | 15 | 104 | 27 | 2 | 0 |  | AUG-21 | The contract has been terminated .Work is awarded to M/s Skipper on dated 09.07.2019
4 | Bhiwani - Isharwal line | D/C | 220 | 100 | 218 | 186 | 164 | 50.19 | JUN-21 | AUG-21 | Work in Progress.
5 | Daukhera - Rewari line (GEC-II) | D/C | 220 | 0 | 0 | 0 | 0
6 | Dhanonda- Deroli Ahir | D/C | 220 | 57 | 118 | 118 | 118 | 57 | MAY-21 | AUG-21 | Commissioned 07/21.
7 | LILO of both ckt. Narwana-Mund line at Khatkar (Jind) PGCIL S/s | D/C | 220 | 44 | 130 | 130 | 128 | 41.5 |  | FEB-21 | Commissioned on 01.02.2021
8 | LILO of both Ckts. of Pali-Sector-56 at Kadarpur | D/C | 220 | 26 | 0 | 0 | 0 |  |  | DEC-21 | NIT floated on 05.03.2019.
9 | LILO of Dhanoda - Daultabad line at Farukhnagar S/s | D/C | 220 | 10 | 0 | 0 | 0 |  |  | AUG-21 | work awarded to M/S RS infra and Work in progress.
10 | LILO of gurgaon Sec -72 - Sector 52 (A) at Sector 57 | D/C | 220 | 1 | 1 | 1 | 0 |  |  | AUG-21 | Work awarded to M/S Infra and work in progress
11 | LILO of Kunihar - PGCIL Naggal line at Pinjore S/s | M/C | 220 | 5.5 | 46 | 46 | 46 | 5 |  | DEC-21 | Work in progress
12 | LILO of Madnpur - Kunihar line at Panchkula sector-32 | D/C | 220 | 5 | 1 | 1 | 1 | 4.5 |  | DEC-21 | work awarded to M/S Feeder and Work in progress.
13 | LILO of one ckt. Badshapur - IMT Manesar line at Gurgaon Sector- 77 S/s | D/C | 220 |  | 4 | 4 | 4 |  |  | NOV-18 | Line Commissioned on 01.11.2018
14 | LILO of Sector-72- Rangla Raipur at Roj-Ka-Meo | D/C | 220 | 7 | 0 | 0 | 0 |  | JUN-21 | AUG-21 | material supply affected due to COVID-19 pandemic.
15 | LILO of Sector- 72 -Ranglarajpur line at Sohna Road | D/C | 220 | 9 | 0 | 0 | 0 | 9 |  | SEP-21 | Commissioned 08/21.
16 | Nuna Majra - Nuna Majra | D/C | 220 | 2 | 0 | 0 | 0 |  |  | DEC-21 | NIT yet to be floated
17 | Panchgaon 400 kV - Panchgaon 220 kV | D/C | 220 | 1 | 2 | 2 | 0 | 0 | JUN-21 | OCT-21 | Work in Progress.
18 | Panchgaon (PGCIL) - Panchgaon (HVPNL) line | MC+D/C | 220 | 10 | 2 | 2 | 0 |  |  | OCT-21 | Work re-awarded to M/s Skipper JV M/s SoluxGalfab Ltd on 08.07.2019
19 | Panchkula (PGCIL)- Panchkula Sector-32 | D/C | 220 | 40 | 72 | 53 | 43 | 14.5 | DEC-21 | DEC-21 | ROW & Forest clearance issue.
20 | Singhani - Mahindergarh line (GEC-II) | D/C | 220 | 0 | 0 | 0 | 0
HIMACHAL PRADESH POWER TRANSMISSION CORP. LTD.(HPPTCL)
1 | Sunda - Andhra Line (GEC-I) | D/C | 66 | 0
2 | Lahal GISS - Chamera (PS) | D/C | 400 | 71 | 114 | 90 | 39 | 0 | SEP-21 | DEC-21 | Work in Progress and all efforts have been made to complete the work by Dec-21.
3 | LILO of Wangtoo - Abdullapur line at Wangtoo | D/C | 400 | 1 | 8 | 8 | 8 | 1 |  | SEP-19 | Line Commissioned
4 | Nalagarh -Kunihar | S/C | 400 | 33 | [5 empty] | MAR-17
5 | Shongtong Karcham HEP - Wangtoo (Quad) | D/C | 400 | 18 |  | 0 | 0 |  |  | DEC-21 | Preliminert Survey has been carried out and is under tendering process for the detailed Survey of the route.
6 | Palchan-Prini line (GEC-I) | N/A | 33 | 0 | 60 | 23 | 9 | 0 |  | JUN-20
7 | Bajoli Holi - Lahal | D/C | 220 | 36 | 59 | 59 | 57 | 32 | JUN-21 | DEC-21 | Work in Progress and all efforts have been made to complete the work by Aug-21.
8 | Dehan - Hamirpur | D/C | 220 | 110 | 198 | 152 | 116 | 37.75 | JUN-21 | OCT-21 | Delay in FC.
9 | Hatkoti-Pragati Nagar | D/C | 220 | 56 | 80 | 80 | 80 | 56 | MAR-17 | MAR-20
10 | Kashang - Jangi Pooling Station | D/C | 220 |  | 0 | 0 | 0 |  |  |  | power of kashang and other generating projects in vicinity was planned to be pooled at Jangi pooling station, since other generating projects have withdrawn LTA therefore the construction of Jangi pooling station has been dropped for the time being.
11 | Koti-Karian | S/C | 220 | 35 | 0 | 0 | 0 |  |  | MAR-19 | Delay FCA approval.
12 | LILO of 2nd Ckts. of 220kV Kunihar- Panchkula line at Baddi s/s | D/C | 220 | 4 | 0 | 0 | 0 |  | SEP-21 | SEP-21
13 | LILO of Bajoli Holi- Lahal line at Heling ss (GEC-I) | D/C | 220 | 0 | 0 | 0 | 0 |  |  | SEP-21 | Forest Clearance Case is under Process
14 | LILO of both ckt of Kashang -Bhaba line at Wangtoo GIS | D/C | 220 |  | 0 | 0 | 0 |  |  | DEC-18 | Work in Progress
15 | LILO of Nalagarh-Baddi at Mandhala S/S | D/C | 220 | 8 | [5 empty] | MAR-17
16 | Mazra - Karian | D/C | 220 | 35 | 52 | 30 | 0 | 0 | JUN-21 | JUN-21 | Work is in Progress.
17 | Rauri-Kunihar | D/C | 220 | 28 | [5 empty] | MAR-17
18 | Stringing of 2nd Ckts. 220kV line Dehar Power House -Kangoo s/s | D/C | 220 | 4 | 0 | 0 | 0 |  | SEP-21 | SEP-21
19 | Sunda-Hatkoti | D/C | 220 | 50 | 69 | 65 | 65 | 40 | JUN-21 | DEC-21 | Re-routing of the Tranmsission Line was done from tower no. T-33 to T-52 and T-63 to T-69, for which revised Forest Clearance case was submitted. Final approval (Stage-II) of the Forest Clearance case has been received from MoEF on 29-06-2021 subject to Hon'ble Apex Court Decision.
20 | Chanju-I - Chanju-II | D/C | 132 | 12
21 | Chanju-II - Chanju-III | D/C | 132 | 8
22 | Chanju - Nakrot line | D/C | 132 | 12 | 30 | 29 | 27 | 10 |  | MAY-16 | commissioned.
23 | LILO of Both Ckt 132 kV D/C Kurthala - Bathri at 220/132 Mazra GIS | 2xD/C | 132 | 1 | 0 | 0 | 0 |  |  |  | Forest Clearance Case is under Progress
24 | Rupin HEP - Sunda (GEC-I) | D/C | 132 | 0
25 | Tangnu Romai-I HEP - 220/132 kV Sunda S/S | D/C | 132 | 24 | 37 | 25 | 17 | 5 |  | DEC-21 | work is progress and all efforts have been made to complete the work by Dec-21.
HIMACHAL PRADESH STATE ELECTRICITY BOARD LIMITED(HPSEBL)
1 | Ghanvi-II - Kotla with HTLS Line (GEC-I) | D/C | 66 | 8
2 | Hatkoti - Samoli Line (GEC-I) | N/A | 66 | 0
3 | Kotla- Nogli-Samoli Line (GEC-I) | N/A | 66 | 120
4 | Nathpa - Wangtoo Line (GEC-I) | N/A | 66 | 0
5 | Bajaura - Naggar Line at Kullu (GEC-I) | S/C + D/C | 33 | 0
6 | Baner Power House - Dehan (Dharmshala) line (GEC-I) | S/C | 33 | 0
7 | Darkata (Ranital) - Lunj Line (GEC-I) | S/C | 33 | 0
8 | Dunkhra (Jari) - Manikaran Line (GEC-I) | D/C | 33 | 0
9 | Gaj Powerhouse - Kangra Line (GEC-I ) | N/A | 33 | 37
10 | LILO from Gaj - Shahpur at Chambi Line (GEC-I) | S/C | 33 | 0
11 | LILO of Bharmour-Gharola line at Lahal (GEC-I) | N/A | 33 | 0
12 | LILO of one Ckt. Shahpur - Kangra at Chambi (GEC-I) | D/C | 33 | 0
13 | LILO of Pandoh - Bijni line at Pandph (GEC-I) | N/A | 33 | 0
14 | LILO point Gharola - Chamba at Karian (GEC-I) | N/A | 33 | 96
15 | Naggar - Bajaira Line at Kullu (GEC-I) | N/A | 33 | 0
16 | Padhar (Gwali) - Bijni Line at Mandi (GEC-I) | S/C | 33 | 0
17 | Pandoh - Bijni Line (GEC-I) | D/C | 33 | 0
18 | Pirini - AD Hydro HEP XLPE Cable Pirini (GEC-I) | N/A | 33 | 0
19 | Pirini - AD Hydro HEP XLPE Cable Pirini (GEC-I) | N/A | 33 | 0
20 | Reconductoring of Gaj-Shahpur line (New reconductoring ) (GEC-I) | S/C | 33 | 19
21 | Salooni - Koti Line (GEC-I) | D/C | 33 | 0
22 | Gumma - Andhra (GEC-I) | D/C | 22 | 12
23 | Jhakri - Rampur line (GEC-I) | D/C | 22 | 0
24 | Karcham - Bhoktoo line (GEC-I) | D/C | 22 | 0
25 | Rampur - Nagli line (GEC-I) | S/C | 22 | 0
26 | Rukti - Shaung line (GEC-I) | D/C | 22 | 8
27 | Gondpur (Paonta) - Sataun line (GEC-I) | D/C | 132 | 0
28 | Uhl-III - Hamir Pur (By BVPCL) | D/C | 132 | 71 | 0 | 0 | 0 |  |  |  | completed on Mar-14
JHARKHAND URJA SANCHAR NIGAM LTD.(JUSNL)
1 | Chandil - Chaibasa (PGCIL) | D/C | 400 | 65 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
2 | Chandil - Dhanbad GSS | D/C | 400 | 125 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
3 | Chandil New - Chaibasa (PG) line | D/C | 400 | 0 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. Tender will be floated by approval from JSERC.
4 | Dumka - Jasidih | D/C | 400 | 70 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
5 | Koderma - Jasidih | D/C | 400 | 130 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
6 | Latehar (JSUNL) - PTPS | D/C | 400 | 220 | 304 | 275 | 260 | 81.55 | SEP-21 | SEP-21 | Work in Progress.
7 | LILO of Bero- Patratu at GSS Mander | D/C | 400 | 15 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
8 | LILO of one ckt QM Kahalgaon - Maithon at GSS Dumka | D/C | 400 | 20 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
9 | OM Jasidih - Koderna GSS | D/C | 400 | 135 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
10 | Patratu - Chandil GSS | D/C | 400 | 135 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
11 | Patratu New - Chandil New line | D/C | 400 | 0 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. Tender will be floated by approval from JSERC.
12 | Patratu New - Kodarma (JUSNL) line | D/C | 400 | 0 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. Tender will be floated by approval from JSERC.
13 | Patratu New - Patratu line | D/C | 400 | 0 | 0 | 0 | 0 |  |  | MAR-22 | Project is being implemented by JUSNL. Tender is likely to be floated in Jul 20. Length of line is 8ckm.
14 | PTPS - Bero (New Ranchi) | D/C | 400 | 102 | 139 | 139 | 139 | 97.58 | AUG-21 | AUG-21 | Balance 0.195 Km stringing awaited for shutdown of DVC Power Line Crossing.
15 | QM Koderma - Daltonganj | D/C | 400 | 200 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
16 | QM Koderma DVC TPS - Koderma JUSNL | D/C | 400 | 15 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
17 | QM North Karanpura - Latehar | D/C | 400 | 100 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
18 | QM Patratu - Koderma GSS | D/C | 400 | 150 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
19 | Quad Essar (Latehar) - Latehar (JUSNL) TL | D/C | 400 | 81 | 122 | 121 | 115 | 42.58 | SEP-21 | DEC-20 | Work in Progress.
20 | TTPS - Dumka GSS | D/C | 400 | 236 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
21 | 3 Ph. Baliyapur - Topchanchi | D/C | 220 | 50 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
22 | 3 Ph. Giridih - Domchanch | D/C | 220 | 90 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
23 | 3 Ph. Giridih - Topchanchi | D/C | 220 | 60 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
24 | 3 Ph. Khunti - Mander (400kV GSS) | D/C | 220 | 60 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
25 | 3 Ph. Khunti - Simdega | D/C | 220 | 120 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
26 | 3 Ph. Koderma - Domchanch | D/C | 220 | 16 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
27 | Chaibasa - Gua TL | D/C | 220 | 168 | 278 | 127 | 110 | 0 | JAN-22 | JAN-22 | Wildlife clearance issue.
28 | Chandil (4ookV GSS) - Jadugoda | D/C | 220 | 80 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
29 | Chandil GSS - Chandil | D/C | 220 | 10 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018.
30 | Chandil GSS - Tamar | D/C | 220 | 25 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
31 | Chandrapura DVC - Chandrapura | D/C | 220 | 8 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
32 | Chatra - Latehar | D/C | 220 | 216 | 340 | 340 | 335 | 206.08 | SEP-21 | SEP-21 | Working Permission awaited.
33 | Chatra - PBCMP (Barkagaon) | D/C | 220 | 117 | 185 | 158 | 125 | 20 | DEC-21 | DEC-21 | Work in Progress.
34 | Giridih - Jamua | D/C | 220 | 160 | 0 | 0 | 0 |  | MAY-18 |  | This line actually constructing at 132kV volatge level instead of 220kV voltage level
35 | Govindpur - Govindpur | D/C | 220 | 7 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
36 | Hazaribagh - Barkatta | D/C | 220 | 18 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
37 | Koderma (JSEB) - Koderma(DVC) | D/C | 220 | 21 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 31.01.2018
38 | Koderma - Giridih | D/C | 220 | 140 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
39 | LILO of 220kV D/C Govindpur -TTPS at Jainmore | D/C | 220 | 70 | 92 | 82 | 67 | 24.3 | SEP-21 | SEP-21 | Work in Progress.
40 | LILO of both ckts Dumka - Govindpur at Palojori GSS | D/C | 220 | 10 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
41 | LILO of Chandil - Ranchi (PG) at Tamar | M/C | 220 | 10 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
42 | LILO of Hatia - Lohardaga at GSS Mander | D/C | 220 | 10 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
43 | LILO of Patratu - Hatia at PTPS by MC Tower | D/C | 220 |  | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
44 | Link Line Daltonganj - Garhwa TL (Bhagodih END) | D/C | 220 | 82 | 159 | 159 | 159 | 89 | MAR-22 | AUG-20 | Link Line Daltonganj-Garhwa (both end Bhagodih end and Daltonganj end) has been commissioned on 18.08.2020.
45 | Mander - Tamar | D/C | 220 | 56 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
46 | Noamundi - Chaibasa (PG) | D/C | 220 | 130 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
47 | Noamundi - Jadugoda | D/C | 220 | 80 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
48 | Patratu - Ratu (Burmu ) line | D/C | 220 | 63 | 124 | 122 | 121 | 49.25 | AUG-21 | AUG-21 | Tree Cutting Permission awaited from DFO, Ramgarh.
49 | P.T.P.S. - Ratu | D/C | 220 | 70 | 124 | 122 | 121 | 49.25 | MAY-18 | OCT-20 | Tree Cutting Permission awaited for Hapua-Katia Proposal from DFO, Ramgarh.
50 | Ratu - Mander | D/C | 220 | 15 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
51 | Simdega - Chaibasa | D/C | 220 | 165 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
52 | Tenughat - Chandrapura | D/C | 220 | 55 | 0 | 0 | 0 |  |  |  | Transmission line deleted as per last revised & approved list of project by CEA during MOM meeting & letter issued on 12.01.2018
53 | Tenughat - Gomia | D/C | 220 | 20 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
54 | Tenughat - Hazaribagh | D/C | 220 | 135 | 0 | 0 | 0 |  |  | MAR-22 | Under PPP mode (TBCB) - Transmission Licensee Regulation 2019 has been notified by Hon'ble JSERC. RFP has been issued to the selected bidders. Last date of Bid submission is 17.02.2020.
55 | TTPS - Govindpur TL | D/C | 220 | 181 | 300 | 298 | 296 | 152.17 | JUN-21 | JUN-21 | Work in Progress.
J&K POWER DEVELOPMENT DEPARTMENT(JKPDD)
1 | Kharu S/S - Himya S/S | S/C | 66 | 51 | 242 | 239 | 204 | 36 |  | DEC-16 | Slow progress.
2 | Leh III (Army base) - Leh | S/C | 66 | 10 | 53 | 29 | 8 | 2 |  | DEC-16 | Rerouting of line and ganglas s/s droped. Leh Army S/S shall be connected with Leh S/S.
3 | Kiru HEP - Kishtwar Pooling Station (Triple HLTS Conductor) | D/C | 400 | 0 | 0 | 0 | 0 |  |  | DEC-21 | work under planning stage.
4 | LILO of one Ckt. of Kiru HEP - Kishtwar PS at Kwar HEP and Pakal Dul HEP | D/C | 400 | 0 | 0 | 0 | 0 |  |  | DEC-21 | Work under planning stage.
5 | Delina - Wahipora-Kishanganga | D/C | 220 | 80 | [6 empty] | Fund yet to be tied up.
6 | LILO of 220 kV D/C Wagoora-Mirbazar line at Lassipora | D/C | 220 | 12 | 22 | 19 | 7 |  | JUN-21 | JUN-21 | Works under Progress.
7 | LILO of Hiranagar-Bishnah line at Samba | D/C | 220 | 11 | 0 | 0 | 0 | 11 |  | AUG-21 | Commissioned 07/21.
8 | LILO of Thein-Hiranagar at Kathua-II (Ghatti) | D/C | 220 | 5 |  |  |  | 5 | APR-21 | AUG-21 | Commissioned 07/21.
9 | (PMDP - Jammu) LILO of Hiranagar - Bishnah at Jatwal Grid station | D/C | 220 | 4 | 11 | 11 | 11 | 4 | MAR-19 | JUL-21 | Commissioned 05/21 (Late Reported).
10 | (PMDP - Kashmir) Extension of Mirbazar - Alusteng line upto New Wanpoh | D/C | 220 | 12 | 19 | 7 | 0 | 0 | SEP-19 | SEP-21 | Works in progress.
11 | (PMDP - Kashmir) LILO of one ckt. Alusteng - New Wanpoh at Tailbal | D/C | 220 | 7 | 0 | 0 | 0 |  | SEP-21 | SEP-21 | LOA for Tower erection and stringing issued.
12 | (PMDP - Kashmir) LILO of Wagoora - Mirbazar line at Lassipora | D/C | 220 | 11 | 22 | 19 | 7 | 0 | JUN-21 | JUN-21 | Works under progress.
13 | Thein (RSD)-Hiranagar (2nd ckt) | S/C | 220 | 40 | 117 | 117 | 117 | 40 | MAR-08 | DEC-19 | E-NIT floated by PGCIL for the three works on 09-10-2017.
14 | Wagoora-Budgam- Zainkote | D/C | 220 | 60 | 123 | 106 | 82 | 17 | DEC-19 | MAR-22 | ROW issues at various locations delaying the project.
15 | Wagoora-Mirbazar | D/C | 220 | 104 | 177 | 175 | 173 | 63 | AUG-21 | SEP-21 | ROW,, compensation issues delaying the project.
16 | Zainkote-Alusteng-Mirbazar | D/C | 220 | 254 | 444 | 436 | 371 | 114 | MAY-19 | SEP-21 | Section I-- Zainakote-Alusteng completed and commissioned in Feb 20. Erection works on Section-II Alusteng-Mirbazar section under progress.
17 | Lower Kalnai - Thathri S/s (existing) line | D/C | 132 | 6
18 | Parnai HEP - Parnai (JKPDD) | D/C | 132 | 30
19 | (PMDP - Jammu) Hiranagar - Kathua line (Reconductoring) | D/C | 132 | 152 | 0 | 0 | 0 |  | MAR-19 | DEC-19 | CC-I meeting held on 3rd and 4th of June 2019 and minutes of meeting yet to be issued.
20 | (PMDP - Jammu) LILO of Canal - Miran Sahib at Chatha | D/C | 132 | 16 | 3 | 0 | 0 |  | MAR-19 | MAR-20 | Out of 40 Kanals of land 20Kanals land has been acquired. Preliminary works (soil testing and demarcation) are under progress. Layout also approved.
21 | (PMDP - Kashmir) LILO of Budgam - Bemina at Tengpora (Power Cable) | D/C | 132 | 8 | 0 | 0 | 0 |  | MAR-20 | SEP-21 | Drawings and GTPs approved. Work under progress.
22 | (PMDP - Kashmir) Replacement of Conductor in Pampore - Cheshmashahi | D/C | 132 | 28 | 0 | 0 | 0 |  | MAR-19 | JAN-21 | LOI issued.
23 | Solar Park - Samba line (GEC-II) | D/C | 132 | 0
J&K STATE POWER DEVELOPMENT CORPORATION(JKSPDC)
1 | Udhampur- Gladni | S/C | 220 | 48 | 165 | 165 | 165 | 48 | APR-08 | SEP-14 | Severe RoW and Court case.
KARNATAKA POWER TRANSMISSION CORP. LIMITED(KPTCL)
1 | Bellary (PS) - C.N. Hally | D/C | 400 |  | 0 | 0 | 0 |  |  | MAR-18 | DPR approved. To be tendered
2 | Bellary (TPS) - Bellary (PS) | D/C | 400 | 5 | 0 | 0 | 0 |  |  | MAR-18 | This work is not in planned works.
3 | Hiriyur - Mysore (GEC-II) | D/C | 400 | 390
4 | Kalburgi - YTPS | D/C | 400 |  | 0 | 0 | 0 |  | SEP-18 | MAR-18
5 | LILO both Ckts. of Nelamangala - Hoody (Twin Moose) at Devanahalli (Hardware Park) | D/C | 400 | 3 | 4 | 4 | 4 | 1 | SEP-19 | OCT-19 | 2 spans stringing completed. (Balance stringing work will be taken up at the time of 400 kV station commissioning i.e. LILO arrangements to station)
6 | LILO of Bellary PS - Chikkanayakanahalli at Jagalur (Common Point at Rampura) | M/C | 400 | 130 | 187 | 184 | 184 | 117.6 | SEP-18 | AUG-18 | Work is under progress.
7 | LILO of both ckt. of Bellary Pool - Madhugiri at Tumkur (Pavagada ) PS (GEC-II) | M/C | 400 | 0
8 | LILO of Both ckt of Nelamangala - Talaguppa at CN Halli | D/C | 400 | [6 empty] | MAR-18 | Not in planned work for FY 16-17
9 | Tumkur (Pavagada) PS - Devanahally (KPTCL) (GEC-II) | D/C | 400 | 170
10 | Tumkur PS - Hiriyur (GEC-II) | D/C | 400 | 218
11 | Yermarus TPS - Gulbarga | D/C | 400 | [6 empty] | MAR-18 | Detailed survey completed. Estimate is being prepared.
12 | Beerenahalli - Thallak (Chitradurga) (Balance portion) | D/C | 220 | 41 | 73 | 53 | 42 | 0 | MAR-18 | DEC-19 | Contractor has stooped the work from March 2017 fue to ROW issues. Notice issued to the agency. In meeting held on 31.07.19 at Tumakuri Tz, agency requested for time extension and PV approval to Zonal office and instructed agency to recommence the work but agency is demanding for approval to recommence the work.
13 | Bidadi (PGCIL) - Magadi S/S | D/C | 220 | 64 | 127 | 80 | 70 | 11 | FEB-17 | MAR-20 | 220kV line passes through Balekatte minor forest area land covering of 1.724 Hectares. Forest clearance for stage-1 proposal resubmitted by attending, all the observations made by forest officers. The proposal acepted by APCCF through online on 26.03.19. Hard copies of the proposal submitted by EE, MWND to the DCF Ramangara on 05.04.19. The same has been forwarded to RFO Magadi for verification on 25.04.2019. After Verification by RFO Mogadi , reports submitted to DCF Ramanagar on 17.07.19. Verification is under progress.
14 | Bidadi GI S/s - 220/66/11 kV Vrushabhavathi Valley S/s (UG cable) | S/C | 220 | 23 | 0 | 0 | 0 |  | NOV-21 | NOV-21 | NHAI and NH (PWD) permission awaited for completion of balance work. Cable jointing work under progress.
15 | Bidadi - Kothipura (Channapatna) | D/C | 220 | 174 | 82 | 63 | 2 |  | FEB-08 | JUN-18 | Contract terminated on 25.01.2016. LOI issued on 06.09.2017 for balance portion of the work. Check survey approved on 20-Aug-2018. ROW problems pending in DC Court Ramanagar for Loc 15 since 2012, NHD: Not intimated
16 | Bijapur - Sindagi | D/C | 220 |  | 0 | 0 | 0 |  | SEP-19 | SEP-19
17 | Chikkabettahalli limits (8 Pole Structure) - Sahakarinagar GIS s/s | M/C | 220 | 19 | 0 | 0 | 0 |  | DEC-21 | DEC-21
18 | Chintamani - Srinivaspura | D/C | 220 |  | 0 | 0 | 0 |  | SEP-19 | SEP-19
19 | Chitradurga - Hiriyur S/S | D/C | 220 | 78 | 152 | 142 | 103 | 56 | MAR-19 | DEC-19 | ROW issues resloved and work is under progress. Emergincy Restoration system required for taking up the works in Multi Ckts Corridor (5062 kms) under the supervision of PGCIL. Hence, requested PGCIL on 10.06.219 to inspect the spot and give the concurrence. PGCIL inspected the spot on 21.08.2019.
20 | Devanhalli -(Hardware Park 2nd ckt) and Doddaballapura (2nd ckt) | M/C | 220 | 100 | 0 | 0 | 0 |  | DEC-21 | DEC-21 | Work in Progress.
21 | Gulbarga - Afzalpur (Ganagapura) | D/C | 220 |  | 0 | 0 | 0 |  | SEP-19 | SEP-19 | Work is in tendering stage.
22 | Hiriyur (PG) - Hiriyur S/S | S/C | 220 | 16 | 18 | 0 | 0 |  | APR-19 | DEC-19 | work to be taken up.(Only stringing work to be done in the existing corridor conductor supplied)
23 | Honnali - Channagiri (Benkikere/Nallur) | D/C | 220 | 95 | 191 | 43 | 37 | 0.4 | MAR-19 | DEC-19 | DC coourt, davangere issued orders on 27.05.2019 for land compensation for tower foot area and line corridor for both 220kV and 66kV new lines. On 16.7.19the land comensation proposal sent to DGM Teach from CEE, Tz. Land compensation approved on 02.08.19.
24 | Hoondy 200 kv - EPIP GIS 200 kv staion (UG Cable) | S/C | 220 |  | 0 | 0 | 0 |  |  | MAR-19
25 | Hosadurga - CN Halli line | D/C | 220 |  | 0 | 0 | 0 |  |  | DEC-18 | Letter of intent to be issued.
26 | Hosadurga (Madure) - Benkikere | D/C | 220 | 83 | 156 | 62 | 17 |  | SEP-18 | DEC-19 | Severe row issues in Nagenahalli, Ailpura, Gangasamudra. Approached and letter addressed to DC, Chitradurga for issuing land compensation. work under progress.
27 | Itagi - Kudligi (Badeladaku) line | D/C | 220 | 65 | 119 | 112 | 95 | 0 | AUG-19 | DEC-19 | RoW issues at Loc nos 88,109,113,114. Farmers are Demanding for higher compensation and also they are not allowing to enter their field as there are standing crops. Requested for police protection.
28 | Jagalur (Hiremallanahole) - Chitradurga | M/C | 220 | 71 | 154 | 82 | 52 | 1 | MAY-21 | MAY-21 | Work in Progress.
29 | Jagalur (Hiremallanahole) - Kudligi line | D/C | 220 | 83 | 159 | 159 | 159 | 83 | JUL-19 | MAY-20 | Commissioned 05/20.
30 | Kolar - Malur at Somanahalli | D/C | 220 | 180 | 280 | 271 | 267 | 146.23 | MAR-18 | DEC-19 | Malur-Kolar line charged (42 Ckm). Line from Malur end upto Loc 137 charged (68.98 Ckm).Line from Somanahalli end upto Loc 55 charged (23.64 Ckm). Total line charged 134.62 Ckm. Work short closed and LOI issued on 15.09.2017 for balance portion of work. Case pending in High Court: (i) Loc 84, 85, 86, 88 & 89: Case filed by KPTCL in DC Court on 27.01.2014 , LHD: 14.02.2017. Posted for orders. (ii) Loc 84, 85, 86 : Case filed by party in Court of Civil Judge (Jr Dv), Anekal .LHD: 14.06.2018 . NHD:10.08.2018. (iii) Loc 88 & 89: Case filed by KPTCL in DC Court Bangalore Urban District on 27.01.2014 LHD: 14.02.2017 posted for orders. (iv) Loc 88 & 89: Case filed by party in Court of Junior Civil Judge, Bangalore Rural District on 11.02.2014 . LHD: 10.01.2018. NHD: 11.07.2018
31 | LILO from Kothipura - Tubinakere at Channapatna | D/C | 220 | 6 | 28 | 0 | 0 |  |  | DEC-19 | approval obtained form DGM (T), KPTCL to pay necessary charges to PWD on 17.06.2019. Letter addressed to firm to pay charges on 29.06.2019/16.07.2019. Approval obtained to pay BG to PWD on 12.07.2019. BG and 297L paid to EE, PWD to issue NOC on 31.07.2019. NOC issued on 21.08.2019 but site was not handed over. PWD is seeking clarification regarding security and safety. Letter to be addressed to EE PWD regarding security and safety. Note: CKt. Kms has been changed (3.25km to 3.35 km) as per check survey approval on 29.03.2019.
32 | LILO from Shimoga - Mysore at Hassan (220 kV Re-orientation and shifting lines) | D/C | 220 | 35 | 68 | 65 | 64 | 22 |  | MAR-20 | Agency has stopped the work. Letter addressed to Agency to restart the work on 01.02.2019,26.03.19 & 29.03.19. Letter addressed to ADLR, Hassan to submit the sketch and RTC and all the associated documents pertaining to survey numbers coming under line corridor on 03.04.19. Awaited for sketch.
33 | LILO line from 220kV Varahi-Kemar S/C line at Heggunje (Mabdarthi Line) | M/C | 220 | 2 | 9 | 6 | 0 |  |  | NOV-19 | Forest issue: Location : AP 9 to AP 10 - BILLADI BLOCK - 1.0325 ha forest area. AP 17 to AP 18 - KORGI - HESKATTURU BLOCK - 0.728 Ha forest area. Application submitted on 24-05-2019. Proposal returned with obsevations dtd 15.06.2019. The observations received from PCCF, Aranya Bhavan bengalur are attended and proposal to be re submitted.
34 | LILO line on M/C Towers from 220kV RTPS - Sedam - Ramasamudra S/S | M/C | 220 | 7 | 12 | 0 | 0 |  |  | DEC-19 | The work is delayed due to land issue. M/s DP Jain & Co Infrastrcture Pvt. Ltd. has stopped the work of removal or murrum. Hence, the CCE TZ has directed to procure alternative land vide Ltr. No. 3436-37Dtd:17.07.2019. New land to be identified.
35 | LILO of Gadag - Lingapur at Koppal | D/C | 220 | 1 | 2 | 2 | 2 | 1 |  | OCT-19 | Electrical Inspectorate Approval obtained on 25.07.19.
36 | LILO of Hoody-Kolar at Hoskote | D/C | 220 | 27 | 55 | 35 | 31 | 0.35 | MAR-18 | MAR-20 | Land compensation issue: Meeting was conducted by SEE (Tr.) Works circle on 11.07.2019 to convince M/s L&T for arranging land compensation payment . However the agency disagreed. Proposal for making payment from KPTCL end submitted to corporate office for approval on 07.08.2019. Approval awaited.
37 | LILO of Hoody - Nelamangala to proposed 220/66 kv Manyatha S/s | M/C | 220
38 | LILO of HSR- NIMHANS to proposed at Koramangala | S/C | 220 | 5 | 0 | 0 | 0 |  | SEP-17 | OCT-19 | 6/6 section cable laying completed. Cable charged on 20.05.19.
39 | LILO of Mylasandra - Malur to proposed 220/66 kV EXORA S/s | S/C | 220 |  | 0 | 0 | 0 |  | SEP-19 | MAR-20
40 | LILO of Mylasandra to the 220kV Somanhalli-Malur | M/C | 220 |  | 0 | 0 | 0 |  | SEP-17 | SEP-19 | Detailed check survey under progress.
41 | LILO of Shimoga - Mysore at Dandiganahally | D/C | 220 | 35 | 68 | 65 | 64 | 21.95 | JAN-18 | JAN-19 | Work under progress. ROW issues: Cases filed in DC Court: a) At loc. No. 49 (Sy.No: 151/2): Case filed by Sri. K.Narayan & Sri.Srinivasa on 17.09.2016. Case cleared on 15.09.2017 . Order copy yet to be received. b) At Loc.No.47-48 (Sy.No.350/1): Case filed by Sri.G.R.Shivaram on 17.09.2016. Case cleared on 15.09.2017 . Order copy yet to be received.
42 | LILO of Thubinkere - Ramnagara to Maddur | D/C | 220 | [5 empty] | SEP-19 | MAR-20
43 | Manyatha-(GIS in premises of existing HBR Layout | D/C | 220 | 9 | 0 | 0 | 0 |  | JAN-22 | JAN-22
44 | Melasandra (New elctronic city) - Yerandanahalli | M/C | 220 | 27 | 35 | 35 | 35 | 27 | JUN-21 | SEP-21 | Commissioned 08/21.
45 | Mylasandra - Somanahalli line | S/C | 220 | 1 | 0 | 0 | 0 |  |  | DEC-19 | Check survey approved. The work to be taken p duly procuring excess materials by TK agency for 220kV DC UG cable which is not envisaged in DWA. One number of 220kV MC Cable terminating tower foundation work completed. Note: As per check survey approved route length is 1.775Kms and single ckt. has been revised to double ckts.
46 | Mylasandra - Somanahalli-Naganthapura-HSR Layout | M/C | 220 | 20 | 38 | 38 | 38 | 20 | SEP-17 | SEP-21 | Commissioned 08/21.
47 | Nagamangala- Anchepalya | D/C | 220 | [5 empty] | SEP-19 | MAR-20
48 | Nagamangala-Tubinkere | D/C | 220 | [5 empty] | SEP-19 | MAR-20
49 | Nelamangala - Peenya S/s | M/C | 220 | [5 empty] | SEP-18 | MAR-19
50 | Nelmangala - Brindavan Alloys | D/C | 220 | 1 | 7 | 7 | 7 | 1 | SEP-17 | OCT-19 | Work completed. CEIG approval to be obtained.
51 | Peenya - A Station UG Cable | S/C | 220 | 0 |  |  |  |  | SEP-18 | MAR-19
52 | Ramanagara (Kothipura) - Bidadi line | M/C | 220 | 73 | 89 | 63 | 2 |  |  | DEC-19 | There is no alternate power supply arrangement for Bidadi-Ramanagara down stream stations, hence the work will be taken up after commissioning of the Kothipura Station.
53 | Shanthigrama - B4 line ( near Hedanahalli limits) | D/C | 220 | 16 | 34 | 34 | 32 | 9 | MAR-18 | DEC-19 | LOI issued for balance portion of work on 10.06.2019. Revenue Survey work under progress, 4.5 kms survey completed out of 7.76 kms.
54 | Somanahalli - Malur I and II lines - Yarandanahally S/s Sommanahally-SingarpetSC line Corridor | M/C | 220 | 27 |  |  |  |  | SEP-18 | MAR-19
55 | Somanahalli- Subramanyapura (M/C M/V) | M/C | 220 | [5 empty] | SEP-18 | MAR-19
56 | Somanahalli - T.K. Halli SC line to DC | D/C | 220 |  | 0 | 0 | 0 |  | SEP-17 | NOV-20 | LOI issued on 03-Aug-19. Activity Chart submitted on 28.08.2019 and under verification.
57 | Somananahalli Malur I & II lines - Jigani | D/C | 220 | 23 | 34 | 6 | 4 | 0 | MAR-18 | MAR-18 | Termination issued to agency on 22.03.2017. Jigani station commissioned on 04.03.2018
58 | Tubinakere - Ramnagar (Kothipura) line | D/C | 220 | 142 | 290 | 290 | 290 | 142 | JUN-09 | MAY-20 | Commissioned 05/20.
59 | Vajamangala - Kadakola | D/C | 220 | 40 | 70 | 49 | 45 | 0 | MAR-18 | DEC-19 | Work terminated on 19-Sep-15. Balance works to be retendered at CEE, Trz, Mysore. Resurvey to be carried out. Letter sent to Corporate office for approval of Re-survey for the subject work on 03.06.2019. Ltr received from DGM (Tech.) on 17.06.2019 to place the subject before CPC. PC agenda sent to Corporate office on 24.7.19 for approval of detailed re-survey.
60 | Vajamangala -Kodakola and Vajamangala-Varun M/C lines | M/C | 220 | 9 | 23 | 23 | 23 | 10 |  | OCT-19 | Line work completed. The 220kV D/C line on MCMV towersform Loc-04(3) to 21 will be comissioned after copletion of 220kV double circuit link line on both Vajamangala (loc No.1 to 3) and Kadakola (loc No. 21 to 70) ends. 220kv 4.567 kms. only 66kV DC line commissioned on 31-0316. 66kV Line. 4.852kms Terminal Bay: Commissioned on 03-Feb-16.
61 | Yelanhanka(KPTCL)- Yelanhanka(PG) | D/C | 220 | 6 | 0 | 0 | 0 | 11.6 |  | AUG-18 | Commissioned on 14.09.2018.
KERALA STATE ELECTRICITY BOARD(KSEB)
1 | Malaparamba - Areakode line | D/C | 400 | 78 | 118 | 118 | 118 | 78.6 |  |  | commissioned on 11.02.2021
2 | Kanhirode - Mylatti line | D/C | 220 | 178 | 303 | 140 | 52 | 14.4 | JAN-22 | JAN-22 | Work in Progress.
3 | Karukadom - Kothamangalam line | M/C | 220 | 14 | 10 | 10 | 10 | 14 |  | AUG-19 | Charged on 11.12.19
4 | Kattakkada-Vizhinjam | D/C | 220 | 44 | 0 | 0 | 0 |  | APR-21 | APR-21 | Work in Progress.
5 | Kodungallur - Irinjalakuda | D/C | 220 | 24 | 60 | 47 | 42 | 7.7 | MAY-21 | SEP-21 | Work in Progress.
6 | Kottayam - Ettumanoor | D/C | 220 | 13 | 25 | 24 | 24 | 8.38 | JUN-21 | OCT-21 | Work in progress
7 | Kottayam - Thuravoor (Kottayam Dist Alapuzha Dist) | D/C | 220 | 45 | 69 | 60 | 59 | 26.3 | JUN-21 | OCT-21 | work in progress.
8 | LILO of 220kV Kaniampetta - Areakode at Kunnamangalam line | D/C | 220 | 15 | 0 | 0 | 0 |  | JAN-21 | JAN-21 | Work in Progress.
9 | LILO of 220kV Lower Periyar - Madakathara at Chalakundy line | D/C | 220 | 24 | 0 | 0 | 0 |  | APR-20
10 | LILO of Arekode-Kaniyambetta -Kunnamngalam | D/C | 220 | 15 | 0 | 0 | 0 |  | APR-21 | APR-21 | Work in Progress.
11 | LILO of PL -AM - Kottayam at Kottayam | M/C | 220 | 13 | 17 | 15 | 15 | 9.5 |  | OCT-21 | work in progress.
12 | Malapramba - Keezhissery at Areakode upgradation of existing line from Kizhissery - Nallalam | D/C | 220 | 206 | 276 | 276 | 274 | 189.11 |  | JAN-21 | Charged on 26.12.2020.Commissioned on 11.02.2021
13 | Malayammma - Kunnamangalam | M/C | 220 | 15 | 29 | 29 | 29 | 15 | JUL-21 | AUG-21 | Commissioned 07/21.
14 | Mundayad - Thalasseri line | D/C | 220 | 43 | 83 | 71 | 61 | 0 | JUL-21 | JUL-21 | Work in Progress.
15 | Mylatti-Vidyanagar | D/C | 220 | 23 | 0 | 0 | 0 |  | DEC-21 | DEC-21 | Work in Progress.
16 | Palikkara - Aluva | D/C | 220 | 23 | 45 | 45 | 45 | 22.86 |  | APR-21 | charged on 31/03/21.
17 | Pallivasal - Aluva line | D/C | 220 | 166 | 265 | 260 | 257 | 145.34 | JUL-21 | SEP-21 | Work in Progress.
18 | Wadakkanchery - Kunnamkulam | D/C | 220 | 44 | 84 | 700 | 65 | 16.7 | MAY-21 | SEP-21 | Work in Progress.
MAHARASHTRA STATE ELEC. TRANSMISSION COMPANY LTD.(MSETCL)
1 | Babhaleshwar - Kudus | D/C | 400 | 447 | 726 | 589 | 526 | 181.82 |  | MAR-22 | Forest Status: (148 Ha) Second & Final approval received on 06.04.2018. GMRT Issue: The issue is resolved. RoW: A)Nashik Zone: 23cases for erection and foundation filed to Collector, Pune, he delegated powers to SDO, Manchar- Junnar, orders awaited. Stringing span ROW at 3 locs, cases filed. B) Vashi Zone: Major ROW problems due to nonpayment of compensation as per SDO order. Matter apprised to Collector Thane by Honble Director sir on 23.10.2020. Collector Thane called meeting on 5-11-20. Major Constraint:  As per GR dated 31.05.2017 there is provision for payment of compensation in respect of Tower foundation & erection i.e. 2 times the ready reckoner rate.  However, revenue authority has issued orders for huge compensation.
2 | Jejuri - Hinjewadi - I and II | D/C | 400 | 207 | 277 | 204 | 187 | 69.54 |  |  | Pkg-I: ROW :dtd 03-06-16 : SDO Bhor- revised Lr. dt 15.06.16:SDO Haveli: 2 nos (loc 86,87). Agency went into Arbitration . Tender on Risk & cost is under process.
3 | Jejuri - Lonand | D/C | 400 | 20 |  |  |  |  | MAR-19
4 | JPGPL TPS Switchyard - Warora PS (JPGPL-TBCB) | D/C | 400 | 0 | 0 | 0 | 0 |  |  |  | Not in STU Plan.
5 | LILO of 400KV Bhusawal - Aurangabad ckt-II at Aurangabad (Thaptitanda) | D/C | 400 | 126 | 273 | 263 | 234 | 126 | MAR-22 | DEC-21 | Work in progress.
6 | LILO of Karad - Lonikand at Jejuri | D/C | 400 | 20 |  |  |  |  | MAR-19
7 | LILO of one ckt Dhule - Sardar Sarovar at Balsane (PS) | D/C | 400 | 36 |  |  |  |  | MAR-20
8 | LILO of two ckts Bhadravati - Chandrapur- I at Chandrapur -II | D/C | 400 | 5 |  |  |  |  | MAR-19
9 | LILO om Solapur ( PG) - Karad at Tembhurni | S/C | 400 | 20 |  |  |  |  | MAR-22
10 | LILO on 220kV Mhaisal - Jath at 400kV Alkud | D/C | 400 | 45 | 77 | 50 | 9 | 0 | SEP-21 | DEC-21 | Work in Progress.
11 | LILO on Chandrapur I - Parli 3rd Ckt at Warora | D/C | 400 | 50 |  |  |  |  | MAR-22
12 | LILO on Kolshet-Wada and Padghe-Wada line at Kudus S/s | M/C | 400 | 31 | 50 | 29 | 26 | 5.27 | DEC-21 | DEC-21 | Forest clearance issue. Stage -I clearance not received.
13 | Shevgaon / Pathardi - Tapti Thanda | D/C | 400 | 120 | 198 | 195 | 194 | 87 | MAR-22 | OCT-21 | ROW case hearing completed. Order awaited for stringing span.
14 | 220 kV M/C LILO of one Ckt. of 220 kV Tarapur -Borivali and Boisar-Ghodbandar line on M/C toweres at 400kV Kudus S/S | M/C | 220 | 117 | 124 | 85 | 50 | 0 | DEC-19 | DEC-21 | Work is in progress under police protection. Forest :The ( 11 Ha/2 tower) Revised online proposal submitted on 05.08.2020.
15 | 2nd ckt Dodaicha - Shahada | S/C + D/C | 220 | 27 | 0 | 0 | 0 |  | MAR-18 |  | Tenderization under process.
16 | 2nd ckt stringing of 220 kV Valve - Jamde SCDC line | S/C | 220 | 13 | 0 | 0 | 0 | 13 | APR-21 | MAY-21 | Commissioned 04/21.
17 | 2nd Ckt. Stringing of Gangapur - Valve at Jamde (GEC-I) | S/C on D/C | 220 | 13 | 0 | 0 | 0 |  | MAR-21
18 | 2nd Ckt. Stringing of Miraj - (Tilawani) Ichalkaranji | S/C + D/C | 220 | 35 | 0 | 0 | 0 | 21.92 | MAR-23 | FEB-21 | Balance line charged on 09.02.2021.
19 | Ambazari - Mankapur (UG) | M/C | 220 | 36 |  |  |  |  | MAR-23
20 | Amrapur - Thaptitanda line | D/C | 220 | 114 | 198 | 195 | 194 | 86.98 | AUG-21 | OCT-21 | Work in progress.
21 | Aurangabad (PG) - Bidkin | D/C | 220 | 40 |  |  |  |  | MAR-22
22 | Babhaleshwar - Kopargaon LILO Point | M/C | 220 | 36 | 118 | 90 | 2 | 0 | MAR-18 |  | ROW at 13 nos loc. Railway crossings involved.
23 | Balsane (Shivajinagar) (T Conductor) - Shivanjinagar | D/C | 220 | 36 |  |  |  |  | MAR-20
24 | Boisar (PG)-Wada | S/C on D/C | 220 | 50 | 211 | 173 | 165 | 28.05 | MAR-22 | MAR-19 | The work stopped due to 1) Severe RoW2) Forest issue.The existing contract closure proposal is approved by C.O.The balance work shall be executed by placing new contract.
25 | Butibori - III - Addl. Butibori | D/C | 220 | 20 |  |  |  |  | MAR-23
26 | Chinchwad - II for reorientation of existing line at Chinchwad - II | D/C | 220 | 12 | 4 | 4 | 2 | 0 | DEC-19 | MAR-20 | Work in progress.
27 | Colourchem - Kolshet | D/C | 220 | 8 |  |  |  |  | MAR-21
28 | Deoli (PGCIL) - Yavatmal | D/C | 220 | 84 | 140 | 137 | 137 | 67 | JUN-19 | OCT-21 | 5.72 Ha Involved. Work in progress.
29 | Dondaicha - Nandurbar | D/C | 220 | 80 |  |  |  |  | MAR-23
30 | Eklahare - Pimpalgaon | D/C | 220 | 87 | 158 | 158 | 157 | 66.16 |  | OCT-21 | alance stringing work is in progress.
31 | Indapur MIDC (Loni Deokar) - Tembhurni | D/C | 220 | 30 | 0 | 0 | 0 |  | MAR-18 |  | Scheme under revision.
32 | Kalmeshwar - Warud | D/C | 220 | 170 | 306 | 304 | 268 | 107.93 |  | OCT-21 | Work is in progress.
33 | Kandalgaon - Dasturi SCDC line | S/C on D/C | 220 | 75 | 236 | 92 | 0 | 0 |  | MAR-19 | Severe ROW problem. Work stopped since June-2016. Short closure is approved. Balance work is to be carried out on Risk & cost basis.
34 | Khapakheda - Uppalwadi | D/C | 220 | 7 |  |  |  |  | MAR-19
35 | Kopargaon tap - Babhaleshwar | M/C | 220 | 144 | 118 | 90 | 2 | 0 |  | DEC-20 | ROW cases filed, order awaited [13].Railway crossing loc no 12-13 and 55-56. Proposal submitted to railway authority. New LOA issued to M/s Precious Infra services on Risk & Cost.
36 | Koradi II - Butibori | D/C on M/C | 220 | 106 | 189 | 133 | 117 | 21.69 | MAR-11 | MAR-20 | Work is stopped.
37 | Koradi-II - Uppalwadi UG and O/Hline | D/C | 220 | 15 | 13 | 8 | 3 | 0 | DEC-21 | DEC-21 | Cable laying 5.75/8 Ckm completed.
38 | Kumbhargaon (Nanded) - Kurunda | D/C | 220 | 110 | 224 | 194 | 187 | 83.14 | SEP-21 | DEC-21 | ROW Issue at Loc. No. 124,125,126.
39 | Lamboti - Karkamb | D/C | 220 | 60 |  |  |  |  | MAR-20
40 | LILO of 220 kV Uran- JNPT MUSS line at 220 kV JNPT SEZ S/S | S/C | 220 | 5 | 0 | 0 | 0 | 5 |  | SEP-21 | Commissioned 08/21.
41 | LILO of Aaret (RINFRAT) - Borivalli (MSETCL) (Proposed cable ) at Goregaon Filmcity - 5 (UG Cable) | D/C | 220 | 5 |  |  |  |  | MAR-23
42 | LILO of Aarey (RINFRAT) - Borivalli (RINFRAT) at Goregaon Filmcity - 5 (UG Cable) | D/C | 220 | 5 |  |  |  |  | MAR-23
43 | LILO of Dhule - Dondaicha at 400 kV Balsane PS (GEC-II) | D/C | 220 | 0 | 0 | 0 | 0 |  |  |  | Not yet tenderised.
44 | LILO of one Ckt. Ahmednagar Bhose at Supa | D/C | 220 | 40 |  |  |  |  | MAR-22
45 | LILO of one Ckt. Aurangabad (PG) - Shendra at Shendra (AURIC) (DMIC Project) | D/C | 220 | 16 |  |  |  |  | MAR-19
46 | LILO of one Ckt. borivali - Boisar at Boisar (PG) | D/C | 220 | 5 |  |  |  |  | MAR-20
47 | LILO of one Ckt. of 220kV Kolshet-Wada line and Padghe-Wada line on M/C towers at 400 kV Kudus S/S | D/C | 220 | 31 | 50 | 29 | 26 | 5.27 | DEC-21 | DEC-21 | Forest clearance issue. Stage -I clearance not received.
48 | LILO of one Ckt. Padegaon - Paithan line at Chitegaon | D/C | 220 | 5 |  |  |  |  | MAR-19
49 | LILO of Tarapur-Borivli at Boisar II | D/C | 220 | 16 | 15 | 15 | 12 | 11 | MAR-07 |  | The work is stopped due to1) Severe ROW. Forest of 0.49 Ha involved forest Clearance proposal is pending at DCF, Dahanu.
50 | LILO on Babhaleshwar - Nashik at Sinnar | D/C | 220 | 20 |  |  |  |  | MAR-20
51 | LILO on Boisar (M) - Versova at Boisar | S/C + D/C | 220 | 1 |  |  |  |  | MAR-20
52 | LILO on Boisar - Kopri at Chikhal Dongri | D/C | 220 | 4 |  |  |  |  | MAR-19
53 | LILO on Boisar - Nalasopara at Palghar | D/C | 220 | 20 | 4 | 2 | 2 | 0.5 | MAR-19 | OCT-21 | Forest involved. RFO submitted his report to ACF on 10.03.21. ACF visited on 17.3.21. DCF Dahanu visited site on 03.06.2021.
54 | LILO on Boisar - Varsova at Virar | D/C | 220 | 4 | 0 | 0 | 0 |  | MAR-20 |  | Not in STU Plan.
55 | LILO on Boisar - Vasai Loc No. A | D/C | 220 | 7 |  |  |  |  | MAR-20
56 | LILO on both ckts. of Uran-Kharghar Ulwe Node | D/C | 220 | 18 | 0 | 0 | 0 |  | DEC-21 | DEC-21 | 8105/9055 cable laying completed. 17/20 joints completed. nd termination at CTT completed for both circuits.Work in progress
57 | LILO on Kandalgaon -Lanand at Kesurdi | S/C | 220 | 10 |  |  |  |  | MAR-22
58 | LILO on Loc No. A (MC Towers ) - Kopri (Virar E) | M/C | 220 | 5 |  |  |  |  | MAR-20
59 | LILO on Nalasopara- Boisar line at Palghar | D/C | 220 | 1 | 4 | 2 | 2 | 0.5 | JUN-21 | OCT-21 | Forest involved. RFO submitted his report to ACF on 10.03.21. ACF visited on 17.3.21. DCF Dahanu visited site on 03.06.2021.
60 | LILO on narrow base towers Boisar - Varsova Loc No. A | 2xD/C | 220 | 2 |  |  |  |  | MAR-20
61 | LILO on one Ckt. of Bhusawal (Khadka) - Chalisgaon at Jamner | D/C | 220 | 1 | 2 | 2 | 2 | 0.36 | MAR-19 | APR-19 | Line commissioned on 25-03-2019.
62 | LILO on one Ckt. of Eklahare - Navsari at Girnare | D/C | 220 | 10 |  |  |  |  | MAR-22
63 | LILO on Padghe - Wada at Kudus | D/C | 220 | 10 | 50 | 29 | 26 | 5.27 | MAR-18 | DEC-21 | Forest Area involved 14.5 Hec., 25 locations, 8.946 km length, Revised online proposal submitted on 05.08.2020 All required hard copies submitted to respective DCF Thane office.
64 | LILO on two ckts Boisar (M) - Borivalli at Kudus | D/C on M/C | 220 | 100 | 124 | 85 | 50 | 0 | MAR-19 | DEC-21 | Line name: 220kV M/C LILO on 220kV Tarapur-Borivali & Boisar-Ghodbandar line for 400kV Kudus S/s - 27 kms. Total Ckm - 117.42. Forest involvement after re-routing: Area involved 11 Ha (Appr). Revised proposal submitted on 05.08.2020
65 | LILO on two ckts Boisar - borivalli at Boisar | M/C | 220 | 1 | 7 | 7 | 7 | 3.6 | MAR-20 | JUL-20 | Line commissioned on 16/07/2020.
66 | LILO on Vita - Miraj at Kupwad s/s | S/C | 220 | 1 |  |  |  |  | MAR-22
67 | Mangaon CCPP(Vile)- Bhagad | D/C | 220 | 4 | 0 | 0 | 0 |  |  |  | commissioned 03/16
68 | Nagothane - Wadkhal | D/C | 220 | 30 | 104 | 56 | 44 | 52 |  |  | Work was stopped by agency due to severe ROW problem on 18/05/2008. Later the line is charged on 11/03/2016 by JSW under ORC using the corridor of existing 220kV DC IPCL-Wadkhal line from loc no 9.
69 | Raymonds - Girnare | D/C | 220 | 30 |  |  |  |  | MAR-22
70 | Second Ckt. stringing Padegaon - Sawangi line | S/C on D/C | 220 | 15 | 4 | 4 | 4 | 15 | DEC-17 | SEP-21 | Commissioned 08/21.
71 | Solapur (PG) - Narangwadi | D/C | 220 | 148 | 247 | 247 | 247 | 148 | SEP-21 | SEP-21 | Commissioned 08/21.
72 | Uppalwadi - Mankapur | M/C | 220 | 32 |  |  |  | 0 |  |  | Scope revised O/H - 7.5 Km U/ G - 2.5 Km To be considered in Ph. III, if necessary as per BR 112/12 .
73 | Uppalwadi - New Pardi | M/C | 220 | 54 | 0 | 0 | 0 |  |  | DEC-21 | 12.51/26 ckm cable laying completed. The HDD work for NH road crossing is under progress at JB5 to JB6.
74 | Vairag - Paranda | S/C + D/C | 220 | 40 | 0 | 0 | 0 |  | MAR-20 |  | Not in STU Plan.
75 | Vashi - Pawane | D/C | 220 | 3 |  |  |  |  | MAR-22
76 | Vishwind- Bhenda | D/C | 220 | 84 | 0 | 0 | 0 |  | JUN-21 | JUL-21 | Work in Progress.
77 | Wani - Pandharkawda line | D/C | 220 | 29 | 199 | 96 | 88 | 28.64 | JAN-20 | JUN-22 | Work order issued for phase II. - Check survey submitted by agency on 10.08.21, joint inspection could not be carried out due to non availability of agency's representative.
78 | Wardha (PGCIL) - Ghatodi | D/C | 220 | 322 | 551 | 451 | 333 | 76.33 |  | DEC-21 | Work in progress.
79 | Yavatmal Tap - Ghatodi Line | D/C | 220 | 25 |  |  |  |  | MAR-21
80 | 2nd Ckt. Stringing of Aundh - Dahiwadi line (GEC-I) | S/C + D/C | 132 | 0 | 2 | 2 | 1 | 28.3 |  | OCT-20 | Line commissioned on 30/09/2020.
81 | 2nd Ckt. Stringing of Georai - Beed (GEC-I) | S/C on D/C | 132 | 0 | 0 | 0 | 0 | 31.8 |  | NOV-19 | Line commissioned on 28/11/2019.
82 | 2nd Ckt. Stringing of Kale (T) - Warna line (GEC-I) | S/C on D/C | 132 | 0 | 0 | 0 | 0 |  |  |  | Line under GEC-I cancelled. MBR sanctioned for MSETCL scheme.
83 | 2nd Ckt stringing of Kharda - Bhairavnath (GEC-II) | S/C | 132 | 0 | 0 | 0 | 0 |  |  |  | Space is not available at 132kV Kharda S/s,and alternate sources are available at Kharda S/s, Hence 2nd ckt stringing is not required.
84 | 2nd Ckt. Stringing of Manmad - Yeola line (GEC-I) | S/C + D/C | 132 | 0 | 1 | 1 | 1 | 28.78 |  | JUL-19 | Line commissioned on 03/06/2019.
85 | 2nd Ckt. Stringing of Nandurbar - Visarwadi line (GEC-I) | D/C | 132 | 0 | 3 | 3 | 3 | 43.75 |  | MAR-20 | Line commissioned on 08/03/2020.
86 | 2nd Ckt. Stringing of Shevgaon - Ghodegaon line (GEC-I) | S/C + D/C | 132 | 0 | 2 | 2 | 2 | 39.95 |  | MAR-20 | Line commissioned on 07/03/2020.
87 | 2nd Ckt. Stringing of Shevgaon - Pathardi line (GEC-I) | D/C | 132 | 0 | 0 | 0 | 0 | 22.6 |  | DEC-19 | Line commissioned on 16/11/2019.
88 | 2nd Ckt. Stringing Shevgaon - Benda line (GEC-I) | D/C | 132 | 0 | 0 | 0 | 0 | 25.68 |  | MAR-19 | Line commissioned on 18.03.2019.
89 | Ahmednagar - Ahmednagar MIDC line (GEC-I) | D/C | 132 | 0 | 0 | 0 | 0 |  |  |  | This line's MBR sanctioned as MSETCL scheme, scope under GEC-I stands cancelled.
90 | Ahmednagar - Supa line (GEC-I) | D/C | 132 | 0 | 65 | 64 | 59 | 31.45 |  | OCT-21 | Work in progress.
91 | Babhaleshwar - Rahuri at Ahmendnagar MIDC line (GEC-I) | D/C | 132 | 0 | 185 | 171 | 80 | 25.34 |  | DEC-21 | Stringing work in Rahuri Krishi Vidyapeeth is stopped by Registar.Matter is taken up with SDM Shrirampur, Order received. Still Regstar of Krishi Vidyapeeth is resisting the work. Applied for police protection.
92 | Kadegon - Kirloskawadi line (GEC-I) | S/C + D/C | 132 | 0 | 56 | 56 | 56 | 28.64 |  | DEC-20 | Line commissioned on 19.10.20
93 | Kavthemahankal - Jath line (GEC-I) | D/C | 132 | 0 | 108 | 108 | 108 | 63.84 |  | JUN-21 | Line charged on 28.05.2021.
94 | Kavthemahankal - Savlaj line (GEC-I) | S/C + D/C | 132 | 0 | 96 | 96 | 96 | 25 |  | JUN-19 | Commissioned on 31.03.2019.
95 | Kharda - Ashta (D/C partly on M/C Tower (GEC-I) | D/C | 132 | 0 | 168 | 161 | 153 | 57.37 |  | SEP-21 | ROW cases under section 16 filed for Loc.no. 129, 130 and 136 at SDO Patoda.
96 | LILO of Ashti - Kharda at Patoda (GEC-II) | D/C | 132 | 0 | 0 | 0 | 0
97 | LILO of Lonand - Phaltan line at Phaltan MIDC GEC-I) | S/C | 132 | 0 | 0 | 0 | 0 |  |  |  | Line cancelled.
98 | LILO of Mul Ashti at - Chamorashi | D/C on M/C | 132 | 30 | 56 | 56 | 56 | 13.99 | MAR-20 | DEC-19 | Line commissioned on dtd. 30.12.2019
99 | LILO of Myani - Dighnchi line at Mhaswad (GEC-I) | S/C | 132 | 0 | 0 | 0 | 0 |  |  |  | Line cancelled.
100 | LILO of Padegaon -s Sillod at Phulambri line (GEC-I) | S/C | 132 | 0 | 0 | 0 | 0 |  |  |  | The lines are not required as revised necessity is verified by STU.
101 | LILO of Sawangi - Pishor at Phulambri line (GEC-I) | N/A | 132 | 0 | 0 | 0 | 0 |  |  |  | The line is not required as revised necessity is verified by STU.
102 | LILO on Kalwan - Dindori at Lakhampur | D/C | 132 | 20 |  |  |  |  | MAR-23
103 | LILO on Markal - Kharadi at Eon Kharadi (Using U/G Cable) | D/C | 132 | 4 |  |  |  |  | MAR-19
104 | LILO on Ozar - Kalwan line at Pimpalgaon (GEC-I) | S/C | 132 | 0 | 24 | 24 | 24 | 10.4 |  | JUN-20 | Line LILO on Ozar - Chandwad line at Pimpalgaon (GEC-I) commissioned on 05/05/2020.
105 | Patoda - Raimoha (GEC-II) | S/C on D/C | 132 | 0 | 0 | 0 | 0 |  |  |  | Yet to be tenderized.
106 | Sawantwadi - Kudal line (GEC-I) | D/C | 132 | 0 | 0 | 0 | 0 |  |  |  | The line is not required as revised necessity is verified by STU.
107 | Vish Wind - Bhenda (GEC-I) | D/C | 132 | 0 | 140 | 130 | 113 | 29.16 | MAR-21 | OCT-21 | Total 29 no's Obstruction cases filed at SDM Pathardi Out of which order received for 12 no's of farmers ROW being resolved, work in progress.
108 | LILO on Kalwa - Vashi at Pawane | D/C | 110 | 1 | 1 | 0 | 0 | 0 | MAR-20 | DEC-21 | 340/460 meter cable trench completed. CTT foundation work in progress.
109 | LILO on Padghe - Vasai | UG Cable | 110 | 42 |  |  |  |  | MAR-19
MEGHALAYA ENERGY CORP. LTD.(MeECL)
1 | Killing (Byrnihat)-EPIP-I | M/C | 132 | 17 | 19 | 19 | 19 | 21.75 |  | MAY-17 | 1. Date of award of contract is 18.03.2011. 2. Schedule date of completion was 18.03.2012. 3. The line was completed on 11.02.2016 and commissioned on 12.05.2017. 4. Delay was due to RoW issue, all of which have been resolved and also due to delay in commissioning of SAS at 400/220/132 kV Killing sub-station.
2 | LILO of Agia - Nangal at Mendipathar | D/C | 132 | 5 | 9 | 9 | 9 | 4.57 |  | DEC-15 | 1. Date of award of contract is 11.02.2011. 2. Schedule date of completion was 11.08.2011. 3. Actual date of completion was 28.01.2014. The line was kept charged w.e.f 28.01.2014, but was commissioned with its connected 132/33 kV sub-station at Mendipathar on 22.12.2015. 4. Delay in completion of the line was due to RoW problem. 5. No issue of forest clearance.
3 | LILO of Mawlai - Cherra at Mawngap. | D/C | 132 | 10 | 16 | 15 | 15 | 5 |  | DEC-19 | 1. Date of award of contract is 19.01.2011. 2. Schedule date of completion was 19.07.2011. 3. Anticipated date of completion is March 2020. 4. Delay is due to RoW issues. Work held up due to ROW problem. The PHED, GOMe has complained and filed an FIR against Loc No. 3 to 8. 5. The matter has been taken up with the District Administration for solving the RoW issues. 6. Overall status is 90% completed.
4 | LILO of NEHU - Khliehriat line at Mustem | D/C | 132 | 1 | 4 | 4 | 4 | 1.1 |  | NOV-15 | 1. Date of award of contract is 12.02.2015. 2. Schedule date of completion was 12.05.2015. 3. The LILO was completed and test charged in 7th August, 2015 but was commissioned along with the 132/33 kV Mustem sub-station on 20.11.2015. 4. Delay in completion of the line was due to sub-station was not ready. 5. No issue of forest clearance or RoW issues.
5 | LILO of NEIGRIHMS - Khliehriat at Lad Nongkrem | D/C | 132 | 6 | 7 | 7 | 7 | 3.2 |  | DEC-19 | 1. Date of award of contract is 26.02.2016. 2. Schedule date of completion was 26.02.2017. 3. Anticipated date of completion is December 2019. 4. Delay is due to delay in supply of materials for line by the vendor. 5. No issues on forest clearance and RoW issues. Commissioned on 9th December, 2019
6 | LILO of Rongkhon - Ampati at Praharinagar | D/C | 132 | 20 | 30 | 0 | 0 | 0 |  | MAR-20 | Survey works for 132 kV LILO is completed. Materials procurement is under process. Tendering for the LILO is under process.
7 | Mawngap - Sumer | D/C | 132 | 66 | 102 | 102 | 102 | 66.15 |  | DEC-11 | 1. Date of award of contract is 20.07.2009. 2. Schedule date of completion was 20.07.2010. 3. Actual date of completion was 21.12.2011. 4. No issue of forest clearance, and the RoW issues that were there were resolved. 5. The line was commissioned on 21.12.2011.
8 | Nangalbibra - Agia | S/C | 132 | 92 | 316 | 316 | 316 | 92.15 |  | AUG-13 | 1. Date of award of contract is 14.12.2007. 2. Schedule date of completion was 14.12.2009. 3. Actual date of completion was 24.05.2013 but the line was commissioned on 06.08.2013. 4. Delay in completion was due to RoW issues and due to fund flow constraints. 5. The line was commissioned on 06.08.2013.
9 | New Umtru HEP - Norbong (EPIP-II) | D/C | 132 | 1.21 | 7 | 7 | 7 | 1.21 |  | MAR-17 | 1. Date of award of contract is 05.02.2016. 2. Schedule date of completion was 05.05.2016. 3. The 132 kV line was completed on 11.11.2016 and commissioned on 25.03.2017. 4. Delay was due to delay in supply of conductor for line by the vendor and also that the New Umtru HEP was not ready as this line is an ATS of the New Umtru HEP. 5. No issues of forest clearance. 6. Line parameter: one circuit only of the 132 kV D/C line - 0.14 ckm, 132 kV S/C line - 1.07 ckm 7. The total expenditure incurred is Rs.471.87 Lakhs and is inclusive of 132 kV New Umtru - Umtru HEP line.
10 | New Umtru - Umtru HEP | S/C | 132 | 0.5 | 1 | 1 | 1 | 0.5 |  | MAR-17 | 1. Date of award of contract is 05.02.2016. 2. Schedule date of completion work 05.05.2016. 3. The 132 kV line was completed on 11.11.2016 and commissioned on 25.03.2017. 4. Delay was due to delay in supply of conductor for line by the vendor and also that the New Umtru HEP was not ready as this line is an ATS of the New Umtru HEP. 5. No issues of forest clearance. 6. Line parameter: one circuit only of the 132 kV D/C line - 0.14 ckm and 132 kV S/C line - 0.36 ckm 7. The total expenditure incurred is Rs. 448.76 Lakhs and is inclusive of the cost of 132 kV New Umtru HEP - Norbong -EPIP-II line.
11 | Rongkhon S/S - Ampati | D/C | 132 | 33 | 102 | 102 | 102 | 32.14 |  | DEC-18 | 1. Date of award of contract is 29.07.2011. 2. Schedule date of completion was 29.07.2012. 3. Anticipated date of completion is December, 2018. 4. Delay is due to heavy flood damage in Garo Hills in September 2014, and also due to fund flow constraint and RoW issues. 5. No issues on forest clearance and no court cases. 6. The line has been charged on 20th November'2018.
M. P. POWER GENERATING CORPORATION LIMITED(MPPGCL)
1 | Sailana - Ratlam | D/C | 220
M.P. POWER TRANSMISSION CORPORATION LIMITED(MPPTCL)
1 | Ashta - Ujjian (GEC-I) | DCDS | 400 | 179 | 258 | 226 | 181 | 38.27 | JUN-21 | DEC-21 | Construction activities got hampered due to COVID-19 and monsoon rains.
2 | Dada Dhuniwale TPP - Moondi Pooling Point | D/C | 400 | 80
3 | DBTPS - Vindhyachal PS (Quad) line | D/C | 400 | 0
4 | Handia - Ashta(2nd stage) | D/C | 400 | 180
5 | Indore (PGCIL) - Ujjian (GEC-I) | DCDS | 400 | 91 | 130 | 129 | 122 | 80.14 | MAR-22 | MAR-22 | Work in Progress.
6 | LILO of Damoh - Bhopal at Sagar | D/C | 400 | 40
7 | LILO of Indira Sagar - Satpura at Handia | D/C | 400 | 40
8 | LILO of Indore - Itarsi at Handia | D/C | 400 | 40
9 | LILO of one ckt of Khandwa (PGCIL) - Rajgarh (PGCIL) at Chhegaon | DCDS | 400 | 3 | 8 | 8 | 8 | 2.52 | MAY-21 | OCT-21
10 | LILO of one ckt of Vindhychal - Satna at Nigrie | D/C | 400
11 | Moondi Pooling Point - Handia | D/C | 400 | 240
12 | Pithampur - Moondi Pooling Point | D/C | 400 | 280
13 | REVA TPP - Moondi Pooling Point | D/C | 400 | 70
14 | Shri Singaji TPP - Moondi Pooling Point | D/C | 400 | 40
15 | Ashta - Shajapur | D/C | 220 | 95
16 | Badod - Nipaniya line PS | D/C | 220 | 8.813 | 0 | 0 | 0 |  |  | MAR-19
17 | Badod - Susner (GEC-I) | D/C | 220 | 0 | 0 | 0 | 0 |  |  |  | Double Entry
18 | Badwar PS - PGCIL S/s | D/C | 220 | 4 | 4 | 4 | 4 | 2.26 |  | MAR-19 | CKT -I Charged on 28.03.2019 Ckt-II charged on 4.07.2019
19 | Chhatarpur - Tikamgarh 220 KV Line | DCDS | 220 | 90 | 298 | 297 | 297 | 91.54 | DEC-21 | DEC-21 | Work in Progress.
20 | DCDS Barsitadesh PS - PGCIL S/s | D/C | 220 | 2 | 7 | 7 | 7 | 2 |  | DEC-18 | Ckt. - I charged on 17.06.2018 & 2nd ckt charged on 23.07.2018
21 | DCDS Ramnagar pahad PS - PGCIL S/s | D/C | 220 | 5 | 13 | 13 | 13 | 5.14 |  | DEC-18 | Line work completed. Ckt-I charged on 22.07.2018 & 2nd ckt charged on 10.10.2018
22 | Julwaniya - Kukshi line | DCDS | 220 | 126 | 218 | 218 | 216 | 107.49 | JUN-21 | OCT-21
23 | Katni - Damoh | D/C | 220 | 220
24 | LILO of both ckt Indore - Pithampur at Indore | D/C | 220 | 8
25 | LILO of both ckt of Ratlam - Badnagar at Badnawar | D/C | 220 | 40 | 0 | 0 | 0 |  |  |  | double entry
26 | LILO of Handia - Barwaha at Handia | D/C | 220 | 40
27 | LILO of Indore-II - Ashta at Shankargarh | D/C | 220 | 20
28 | LILO of one ckt of Bansagar (Tons) - Satna at Sirmour | D/C | 220 | 2
29 | LILO of one ckt of Bina - Gwalior at Datia | D/C | 220 | 10
30 | LILO of one ckt of Bina - Sagar at Bina | D/C | 220 | 10
31 | LILO of one ckt of Indore - Barwaha at Simrol | D/C | 220 | 13
32 | LILO of one ckt of Pithampur - Rajgarh (PGCIL) at Dhar | D/C | 220 | 4
33 | LILO of second ckt of Auraiya - Malanpur at Mehgaon | D/C | 220 | 6
34 | LILO of second ckt of Damoh - Tikamgarh at Damoh | D/C | 220 | 10
35 | Maheshwar (HEP) - Rajgarh (Dhar) | D/C | 220 | 230
36 | Morena - Malapur | D/C | 220 | 80
37 | Morena SP - Morena s/s (ISTS) line (GEC-II) | D/C | 220 | 0
38 | Pithampur - Gandhinagar | D/C | 220 | 60
39 | Rajgarh (B) - Susner (Nalkheda) | DCDS | 220 | 124 | 205 | 205 | 205 | 124 | AUG-21 | JUL-21 | Commissioned 06/21.
40 | Rajgarh - Susner (GEC-I) | D/C | 220 | 0 | 0 | 0 | 0 |  |  |  | Double Entry
41 | Rewa UMSP- Sidhi line | DCDS | 220 | 100 | 198 | 154 | 129 | 10.22 | MAR-22 | DEC-21 | Heavy forest involved.
42 | Ujjain - Dewas | D/C | 220 | 90
43 | Ujjain - Susner (GEC-I) | D/C | 220 | 0 | 0 | 0 | 0 |  |  |  | Double Entry
44 | Ujjain - Susner (Nalkheda) (GEC) | DCDS | 220 | 160 | 253 | 253 | 253 | 160 | JUN-21 | JUL-21 | Commissioned 06/21.
45 | 2nd Circuiting of Mahidpur - Zarda (GEC-I) | S/C | 132 | 0 | 0 | 0 | 0 | 23.1 |  |  | Line Charged on 31.03.2019
46 | Kanwan (220) - Kanwan (132) (GEC-I) | D/C | 132 | 26 | 42 | 42 | 42 | 29.63 |  | MAR-19 | 2x13.115 + 3.4 Kms (second circuit) line charged on 30.03.2019
47 | Kanwan (220) - Teesgaon (GEC-I) | D/C | 132 | 24 | 44 | 44 | 44 | 24.65 |  | MAR-19 | Line Charged on 26.03.2019
48 | Sendhwa (220) - Sendhwa (132) (GEC-I) | D/C | 132 | 12 | 15 | 15 | 15 | 9.61 |  | MAR-19 | 1x2.538 + 7.071 Km (second Circuit) Line charged on 29.03.2019
ORISSA POWER TRANSMISSION CORPORATION LTD.(OPTCL)
1 | Bolangir - Kesinga line | D/C | 220 | 170 | 329 | 326 | 324 | 69.4 | MAY-21 | FEB-22
2 | Cuttack (OPTCL) - Pratapsasan | D/C | 220 | 96 | 173 | 121 | 62 | 13.9 |  | MAR-22 | Total no. of location may be changed to 174 nos.
3 | Katapalli-Kiakata | D/C | 220 | 250 | 445 | 267 | 245 | 59.6 | JAN-20 | MAR-22 | The no. of Towers may be revised to 440 nos.
4 | Kesinga - Baliguda | D/C | 220 | 200 | 376 | 322 | 299 |  | JUN-17 | MAR-22 | Delayed due to forest clearance issue. The total locations may be revised to 382 due to site requirement.
5 | LILO of Balimela-Malkangiri at Gobindpalli | S/C + D/C | 220 | 80 | 146 | 136 | 126 | 21.37 | MAR-20 | FEB-22 | The S/s charged through "T"connection. The line is delayed due Forest clearance issue.
6 | LILO of Budhipadar - Tarkera at Bamra | S/C | 220 | 13 | 37 | 31 | 13 |  | DEC-21 | DEC-21 | the ckm should be 11.6 ckm. Schedule Completion may be made Dec 21
7 | LILO of Budhipadar - Tarkera at Kuanramunda | S/C | 220 | 61 | 65 | 52 | 45 | 3.8 | OCT-21 | MAR-22 | The ckm should be 30.036 ckm. Schedule Completion may be made May 20
8 | LILO of Duburi - Balasore at Dhamra | S/C | 220 | 70 | 133 | 52 | 40 |  |  | MAR-22 | Schedule of Completion may be made as June 20
9 | LILO of Joda-TTPS line at Telkoi | D/C | 220 | 29 | 56 | 56 | 56 | 29 | MAY-21 | JUN-21 | Commissioned 05/21.
10 | LILO of Narendrapur - Therubali at Aska S/S | D/C | 220 | 86 | 161 | 99 | 90 |  | FEB-22 | JAN-22
11 | LILO of Narendrapur - Therubali line at Gunupur S/S | D/C | 220 | 27 | 53 | 51 | 48 |  | AUG-21 | NOV-21
12 | LILO of one Ckt. of Bhanjanagar -Meramundali at Daspalla | D/C | 220 | 60 | 113 | 106 | 91 | 33 | FEB-22 | MAR-22
13 | LILO of one Ckt. of Budhipadar-Basundhara at Lephripara s/s | D/C | 220 | 9 | 20 | 20 | 20 | 9 | MAY-21 | SEP-21 | Commissioned 08/21.
14 | LILO of one ckt of Rengali-Barkote line at Deogarh | S/C | 220 | 25 | 50 | 50 | 50 | 25 | JUN-21 | SEP-21 | Commissioned 08/21.
15 | LILO of one ckt of Rengali - Tarkera at Deogarh | S/C | 220 | 24 |  |  |  |  | MAR-21
16 | Malkangiri - Kalimela | S/C | 220 | 67 | 128 | 128 | 128 | 0 | JAN-22 | MAR-22 | Delayed due to forest clearance issue
17 | Pandiabili PGCIL - Pratapsasan line | D/C | 220 | 58 | 114 | 110 | 104 | 47.4 | AUG-21 | OCT-21 | Work in Progress.
18 | LILO of Aska - Bhanjanagar at Aska line | S/C | 132 | 12 | 0 | 0 | 0 |  | MAR-18 |  | May be deleted as it is 132kV voltge level
POWER AND ELECTRICITY DEPARTMENT, MIZORAM(PEDMIZO)
1 | 2nd evacuation line : Tuirial HEP to Sihhmui via Bawktlang | S/C | 132 | 105 | [6 empty] | Concept Note is being submitted
2 | Bairabi to W.Phaileng via Mamit | D/C | 132 | 74 | 0 | 0 | 0 |  |  |  | Sanction received from NEC. Preliminary survey started
3 | Bawktlang (Kolasib) S/S - Sihhmui S/S | D/C | 132 | 47 | 135 | 135 | 135 | 46.67 |  | DEC-16 | The 132KV Sihhmui substation was constructed by P&E, Govt. of Manipur and completed on 31.03.2016. Line has completed.
4 | LILO of 2nd ckt of Tuirial-Aizwal at Kolasib | D/C | 132 | 105 | 0 | 0 | 0 |  |  |  | Funding of project is yet to be identified
5 | LILO of Zemabawk - W.Phaileng at Sihhmui | S/C | 132 | 5 | 0 | 0 | 0 | 0 |  | DEC-13 | Approval from State Govt. obtained
6 | Luangmual to Sihhmui | D/C | 132 | 16 | [6 empty] | Work progress is 28 percent due to ROW problem since the line is to be constructed through city area
7 | Melriat to Khumtung | D/C | 132 | 25 | [6 empty] | Proposal stage
8 | Sihhmui s/s to Airport road Sihhmui(to re-align existing W.Phaileng line | S/C | 132 | 11 | [6 empty] | Proposal stage. Fund will be sought from NEC/DoNER
9 | Tuirial HEP - Bawktlang (Kolasib) S/S | S/C | 132 | 42 | 85 | 85 | 85 | 42 |  | FEB-17 | Line completed on Mar-17.
POWER TRANSMISSION CORP. OF UTTARAKHAND LTD.(PTCUL)
1 | Kuwari Pass (Pipalkoti)-Karanprayag -Srinagar(Khandukhal) | D/C | 400 | 184 | 220 | 45 | 0 | 0 |  | DEC-21 | Contract awarded in 03 no. packages in Sep 2017. Forest proposal had been submitted on dated 24.11.2018 for Package-I, on dated 23/10/2018 for Package-II and on dated 23/02/2019 for Package-III. Stage-I clearance of forest case for Package I, II and III is expected by Oct'19, Oct'19 and Nov'19 resp. Construction work of line will be started after approval of stage-I clearance of forest.
2 | LILO of Loharinagpala - Koteshwar at Pala - Maneri | D/C | 400 | 10 | 0 | 0 | 0 | 0 |  |  | The work at Pala Maneri HEP stopped as per GOI order.
3 | LILO of Vishnu Prayag - Muzaffarnagar at Tapovan Vishnugarh HEP | D/C | 400 | 2 | 0 | 0 | 0 |  |  |  | Approval is pending in Standing Committee, CEA. Construction of Transmission line will be planned after due approval from competent authority.
4 | Loharinagpala-Koteshwar line | D/C | 400 | 180 | 0 | 0 | 0 | 0 |  |  | The work at Loharinagpala HEP stopped as per GOI order.
5 | Pipalkoti HEP (THDC) - Pipalkoti (Kuwari Pass) Switching Substation T/line | D/C | 400 | 2 | 0 | 0 | 0 |  | SEP-19 | DEC-21 | Construction of line shall be planned as per schedule of Pipalkoti HEP (THDC) after signing of Implementation Agreement with PTCUL.
6 | Srinagar(Khandukhal)-Kashipur(Rampura) | D/C | 400 | 362 | 0 | 0 | 0 | 0 |  | DEC-21 | Implementation of line to be taken up under central sector as an ISTS scheme with the matching timeframe of commissioning of Vishnugad -Pipalkoti(HEP) of THDC i.e June 2023 or Tapovan-Vishnugad HEP of NTPC whichever is earlier as per minutes of 3rd NRPC meeting (Transmission planning) held on dt 19.02.21.
7 | Tapovan Vishnugadh - Kunwari Pass (Pipalkoti) | D/C | 400 | 36 | 48 | 13 | 4 |  | DEC-21 | DEC-21 | Final approval on forest proposal was accorded on dt 21.07.2020. Natural calamity happened on dt.07.02.2021in Joshimath,Dist Chamoli at Rishi Ganga, which also affected the NTPC HEP. Revised commissioning schedule of Tapovan-Vishnugad HEP is awaited from NTPC.
8 | Vishnugad - Kuwari Pass (Pipalkoti) | D/C | 400 | 40 | 62 | 0 | 0 | 0 |  | DEC-18 | Construction of 400 KV DC Vishnugad-Pipalkoti line & LILO of 400 KV DC Vishnuprayag-Muzaffarnagar at Piapalkoti is under progress. Rroute alignment, profile has been finalized and forest case preparation is under process. Completion period of line as amended is 02 years from 26.09.2016.
9 | Almora-Pithoragarh | D/C | 220 | 146 | 0 | 0 | 0 | 0 |  | DEC-20 | Revised DPR under preperation.
10 | Arakot -Mori and LILO of Arakot -Mori at Hanol Tuni | D/C | 220 | 94 | 0 | 0 | 0 | 0 |  | MAR-20 | Land for construction of S/s is being searched. Construction of line will be planned as per Connectivity Schedule of Generators in Yamuna Valley.
11 | Devsari-Karanprayag | D/C | 220 | 52 | 0 | 0 | 0 | 0 |  |  | Construction of Transmission line will be planned as per Connectivity Schedule of Devsari HEP (SJVNL) in Alaknanda Valley.
12 | Jakhol -Sankri -Mori and LILO of Jakhol -Sankri -Mori at Natwar Mori | D/C | 220 | 76 | 0 | 0 | 0 | 0 |  | MAR-18 | Construction of line as per Conectivity Schedule of Generators in Yamuna Valley.
13 | Joshimath - Kunwari Pass (Pipalkoti) | D/C | 220 | 40 | 0 | 0 | 0 |  |  | DEC-21 | Contract of transmission line has been terminated on 23.01.2017 due to the stay order of Hon'ble Supreme Court for Construction of Lata Tapovan HEP(171MW).
14 | Lakhwar- Dehradun | D/C | 220 | 60 | 110 | 57 | 52 | 0 |  | JUN-20 | Foundation Completed : 57Nos. Tower erection : 52 Nos. Stringing :0.000 Kms
15 | Lata Tapovan- Joshimath | D/C | 220 | 24 | 36 | 0 | 0 | 0 |  | DEC-21 | Contract of transmission line has been terminated on 23.01.2017 due to the stay order of Hon'ble Supreme Court for Construction of Lata Tapovan HEP(171MW).
16 | LILO of Baramwari - Srinagar at Singoli Bhatwari | D/C | 220 | 5 | 0 | 0 | 0 | 0 | DEC-19 | MAY-21 | Work held up due to COVID-19.
17 | LILO of Dhauliganga - Pithoragarh (PGCIL) line at proposed 220/33 kV S/s Baram (Jauljivi) | D/C | 220 | 22 | 0 | 0 | 0 |  | JUN-21 | MAY-20 | Work is under progress. Physical Progress is 36%. Excavation done for 6 nos. tower locations out of 39 tower locations.
18 | LILO of Kashipur - Pantnagar line at Jaffarpur | D/C | 220 | 8 | 17 | 17 | 17 | 8 | MAY-20 | APR-21 | Commissioned 03/21.
19 | LILO of Lakhwar- Dehradun at Vyasi | D/C | 220 | 71 | 113 | 100 | 88 | 24 | JUN-21 | DEC-21 | Work in progress.
20 | LILO of Mori - Dehradun line at Nogaon | D/C | 220 | 10 | 39 | 1 | 0 | 0 |  | MAY-20 | Target date of Completion 31.05.2020.
21 | LILO of Nandprayag -Karanprayag at Langrasu | D/C | 220 | 16 | 0 | 0 | 0 | 0 |  |  | Construction of Transmission line will be planned as per Connectivity Schedule of Langrasu HEP (UJVNL) in Alaknanda Valley.
22 | LILO of Vyasi HEP - Dehradun at Dehradun (PG) S/S | D/C | 220 | 70 | 0 | 0 | 0 | 0 |  | DEC-18 | Route Survey has been completed. Tower schedule and profile of line has been approved. Principal approval obtained from MOEF on dated 11/09/2017. Proposal for transfer of land (73.36 Hect.) for compensatory afforestation was submitted to DM, Dehradun on dated 14/09/2017. SDM directed to Tehsildar on 03/10/2017 for further necessary action. Total Progress 12%
23 | Mori -Dehradun | D/C | 220 | 200 | 0 | 0 | 0 | 0 |  | DEC-21 | Implementation of line may be considered in future under central sector with materialization of projects other that Natwar-Mori in Yamuna Basin as per minutes of 3rd NRPC meeting (Transmission planning) held on dt 19.02.21. For evacuation of Natwari Mori HEP, alternative arrangement was approved in the meeting.
24 | Naitwar Mori HEP - Mori SS | D/C | 220 | 0 | 0 | 0 | 0 | 0 |  | DEC-21 | Implementation of line may be considered in future under central sector with materialization of projects other that Natwar-Mori in Yamuna Basin as per minutes of 3rd NRPC meeting (Transmission planning) held on dt 19.02.21. For evacuation of Natwari Mori HEP, alternative arrangement was approved in the meeting.
25 | Phata HEP-Baramwari (Rudrpur) | D/C | 220 | 8 | 8 | 0 | 0 |  |  | DEC-22 | Pertains with L&T HEP.
26 | Puhana - Imlikhera (Pirankaliyar) line | D/C | 220 | 14 |  |  |  |  | NOV-19
PUNJAB STATE TRANSMISSION CORPORATION LIMITED(PSTCL)
1 | Jassa Singh - HMEL 400kV Switching Station at Village Behman | D/C | 400 | 34 | 53 | 53 | 53 | 34 | APR-21 | OCT-21 | Work Completed. & will be commissioned by Oct.2021
2 | LILO of 400kV Talwandi Sabo-Moga Ckts. at Switching Station at Behman Jassa Singh | D/C | 400 | 32 | 50 | 50 | 50 | 22.42 | APR-21 | OCT-21 | Work in Progress.
3 | LILO of both ckts. Rajpura Thermal s/s to Nakodar s/s at Doraha | 2xD/C | 400 | 22 |  |  |  |  | MAR-18
4 | LILO of both lines Rajpura s/s- Lalru s/s at Mohali | D/C | 400 | 14 |  |  |  |  | MAR-18
5 | Gaunsgarh - Ladhowal | D/C | 220 | 34 | 61 | 55 | 55 | 26.33 | MAY-21 | DEC-21 | Court Case-ROW issue
6 | LILO of 220kV Sarna Wadala -Granthian at Gurdaspur | D/C | 220 | 16 | 31 | 0 | 0 | 0 | DEC-21 | DEC-21 | Work not started yet due to ROW problem
7 | LILO of both ckts. Jamalpur s/s Dhandari Kalan-I s/s at Sherpur (Focal Point) | D/C | 220 | 26 |  |  |  |  | MAR-18
8 | LILO of Ckt. one RSP - Sarna at Shahpur Kandi PH-I and PH-II | S/C on D/C | 220 | 0.5 | 0 | 0 | 0 | 0 |  | AUG-24
9 | Makhu - Taran ¦Tarn | D/C | 220 | 60
10 | Malout - Abohar | S/C on D/C | 220 | 30 | 102 | 101 | 95 | 19.89 | DEC-21 | DEC-21 | Work in Progress.
11 | RSD - Shahpur Kandi PH-I | S/C on D/C | 220 | 20 | 0 | 0 | 0 |  |  | AUG-24
12 | Sarana- Kotli Surat Malli line | S/C on D/C | 220 | 62 | 185 | 70 | 0 | 0 |  |  | Work deferred for the timebeing.
13 | Shahpur Kandi PG-II - Sarna with HTLS conductor of 1200 A Capacity | S/C on D/C | 220 | 18 | 0 | 0 | 0 |  |  | AUG-24
14 | Shahpur Kandi PH-I - Shahpur Kandi PH-II | S/C on D/C | 220 | 3.5 | 0 | 0 | 0 | 0 |  | AUG-24 | PSTCL to fund the upfront payment for this work .
RAJASTHAN VIDYUT PRASARAN NIGAM LIMITED(RVPNL)
1 | Suratgarh TPS - Babai ( Jhunjhunu) | D/C | 400 | 480 | 676 | 676 | 676 | 469 | MAR-22 | SEP-21 | Work order awarded to M/s Aster Chennai. 02 nos. tower at Loc. 34/12 & 35/0 were collapsed on dated 16.04.2019, Work has been stalled wef 02.11.19. Stay against termination of contract issued by court. Matter is under the jurisdiction of court.
2 | GSS Basni (Jodhpur) - GSS NPH (U/C) Jodhpur | D/C | 220 | 3 | 18 | 18 | 18 | 3 | JUN-21 | NOV-21 | 1. W.O. issued to M/S Transrail on 14.12.17. 2. Drawing submitted by firm and Installation of cable end termination approved on 08.03.21. 3. Cable laid. Work stopped by the Contractor.
3 | Jodhpur (400 kV GSS) - Banar | D/C | 220 | 21 | 39 | 37 | 36 | 18.39 | OCT-12 | SEP-21 | W.O. awarded to M/s Hitech. Tower erection work had been stopped due to ROW. Advocate advised to exectue the work in existing ROW as RVPN is not a party in court case.
4 | Jodhpur CHB - Soorsagar | D/C | 220 | 16 | 32 | 32 | 32 | 15.46 |  | NOV-19 | Work order issued on dated 10.05.2018 to M/S Astvinayak. Work completed on 31.03.2019
SIKKIM POWER DEVELOPMENT CORPORATION LTD.(SIKKIM)
1 | LILO of Teesta III - Rangpo 400 kv line at Dikchu (Interim connectivity) | D/C | 400 | 1 | 2 | 2 | 12 | 1 |  | FEB-17 | Completed.
2 | Dikchu HEP - Dikchu Pool | D/C | 132 |  | 0 | 0 | 0 |  |  |  | Yet to award
TAMILNADU TRANSMISSION CORPORATION LTD.(TANTRANSCO)
1 | Ariyalur - Thiruvalam PGCIL | D/C | 765 | 347 | 500 | 500 | 500 | 347 | MAY-21 | DEC-21 | All works completed. Will be energised on commissioning of Ariyalur 765 KV SS.
2 | NCTPS Stage-III - North Chennai (PS) line | D/C | 765 | 13 | 20 | 17 | 16 | 8.84 | JUN-21 | DEC-21 | Work under progress. RoW issues in 2 Locations.
3 | North Chennai PS - Ariyalur | D/C | 765 | 542 | 799 | 799 | 799 | 546.91 | JUN-21 | DEC-21 | Work under progress.
4 | Uppur SCTPP - Virudhunagar | D/C | 765 | 204 | 0 | 0 | 0 |  | MAR-21 |  | Tender to be floated.
5 | Virudhnagar - Coimbatore | D/C | 765 | 498 | 717 | 329 | 193 | 20.28 | MAR-21 | MAR-22 | Work in progress in all the 3 reaches awarded.
6 | Ennore SEZ - North Chennai Pooling Station | D/C | 400 | 33 | 51 | 39 | 36 | 7.59 | SEP-21 | DEC-21 | Work is under progress.PWD/Railway approval awaited. ROW issue involved.
7 | ETPS exp.- Ennore SEZ | D/C | 400 | 24 | 22 | 21 | 19 | 4.86 | APR-19 | SEP-22 | Work is under progress.PWD/Railway approval awaited. ROW issue involved.
8 | ETPS exp. - North Chennai Pooling Station | D/C | 400 | 24 | 9 | 8 | 8 | 1.89 | SEP-18 | SEP-23 | Work is under progress.PWD/Railway approval awaited. ROW issue involved.
9 | ETPS to Tondiarpet point ATS | D/C | 400 | 18 | 5 | 5 | 5 | 0.87 | SEP-17 | SEP-23 | Work is under progress.PWD/Railway approval awaited. ROW issue involved.
10 | LILO of Karaikudi - Pugalur feeder-I at Vellalaviduthi | D/C | 400 | 167 | 246 | 241 | 231 | 96.49 | SEP-21 | DEC-21 | Work under progress. Row issues involved.
11 | LILO of one ckt of Thappagundu - Anaikadavu 400 line at Udumalpet (PGCIL) S/S | D/C | 400 | 40 | 60 | 60 | 60 | 29.09 | JUN-21 | DEC-21 | Stringing work pending as land owners are demanding compensation in advance. Being followed with district collector and Revenue officials.
12 | LILO of Pugalur - Kalivanthapattu line at Ariyalur | 2xD/C | 400 | 15 | 15 | 15 | 15 | 14.57 | MAY-21 | DEC-21 | Work completed. Will be energised on commissioning of Ariyalur 765 KV SS
13 | LILO of Sunguvarchatram - Alamathy at Vellavedu (Guindy) | D/C | 400 | 16 | 43 | 43 | 42 | 25.9 |  | DEC-21 | Works are under progress. Court case - 1 no.
14 | Manali - Pulianthoppe | D/C | 400 | 19 | 64 | 64 | 63 | 9.15 | JUN-21 | DEC-21 | Work in Progress. Court case at 1 Location.
15 | Manali - Pulianthoppe | D/C | 400 | 9 | 64 | 64 | 63 | 18.3 |  | DEC-21 | Work in Progress. Court case at 1 Location.
16 | Manjakuppam - Korattur | D/C | 400 | 22 | 0 | 0 | 0 |  | APR-17 | NOV-22 | Work awarded on 27.5.20. Route survey Completed. Route drawing approved.
17 | NCTPS Stage-II to Pulianthope Rearranging of North Chennai Pooling station to Pulianthope | D/C | 400 | 44 | 0 | 0 | 0 |  | SEP-17 | DEC-21 | Tender is under process.
18 | Parali - Karamadai line | D/C | 400 | 0 | 0 | 0 | 0 |  |  |  | Parali - Karamadai 400 kV D/C line is to run on D/C tower up to location no. 57 (Hilly terrain area) and subsequently on 400 kV M/C tower (with four circuits) upto Karamadai 400/230 kV S/S (S/S (in Plains area ), which will also accommodate existing Parali-Karamadai 400 kV D/C line utilizing the corridor of existing Kundah PH-II-ARasur 230 kV S/C line. the lines will have HTLS conductor.
19 | Rasipalayam - Dharmapuri (Palavadi) | D/C | 400 | 379 | 564 | 564 | 564 | 377.57 | AUG-21 | SEP-21 | Work under progress.
20 | Sholinganallur 400 kV S/S (Perumbakkam) - Guindy 400 kV S/S | D/C | 400 | 40 | 48 | 18 | 16 |  |  | MAR-22 | Marsh land, Court case involved. Proposed for UG cable instead of OH sent for approval.
21 | Sholinganallur - Guindy | D/C | 400 | 12 | 0 | 0 | 0 |  |  | MAY-22 | UG cable work from Perumbakkam Jn to Guindy Work awarded on 27.05.20. As per field route length is 9 Kms.
22 | Thervaikandigai - Korattur | D/C | 400 | 5 | 9 | 9 | 9 |  | APR-15 | OCT-17 | line Energised on 23.07.17.
23 | Thervaikandikai - Korattur | D/C | 400 | 74 | 113 | 103 | 81 | 19.96 | DEC-19 | MAR-22 | SEW Aster Contract terminated due to slow progress of Work and balnace work awarded to M/s.L&T on 20.04.21. Work in progress..
24 | Tondiarpet point Puleanthope (Manali & NCTPS stage-II) (UG Cable) | D/C | 400 | 21 | 0 | 0 | 0 |  | SEP-17 | MAR-18 | BLTC Note for award of work is under approval.
25 | Udangudi - Ottapidaram (QM ACSR Conductor) line | D/C | 400 | 0 | 200 | 68 | 34 |  |  |  | Check survey submitted and approved - 38.809Km. Soil investigation Approved-77 Loc.
26 | Udangudi - Samugarengapuram (QM ACSR Conductor) line | D/C | 400 | 0 | 154 | 0 | 0 |  |  |  | Estimate approval under process.
27 | Udangundi - Virudhunagar (QM ACSR Condutor) line | D/C | 400 | 0 | 0 | 0 | 0
28 | Vellavedu - Guindy 400 kV S/S (U/G Cable) | D/C | 400 | 40 | 0 | 0 | 0 |  |  | MAY-23 | Work awarded on 27.05.20. Route map approved . Obtaining statutory approvals in process. DI issued for 8.6 kms of cables.survey completed. Route drawing to be submitted by M/s LS cables.
29 | Virudhnagar - Kamuthi | D/C | 400 | 114 | 0 | 0 | 0 |  | MAR-21 |  | Tender to be floated. Revised estimate under preparation.
30 | Virudhnagar - Kayathar | D/C | 400 | 158 | 201 | 145 | 94 |  | MAR-21 | DEC-21 | Work under progress. Row issues involved.
31 | Virudhnagar - Thappagundu | D/C | 400 | 160 | 0 | 0 | 0 |  | MAR-21 |  | Tender to be floated.
32 | Basin Bridge - TNEB HQ (UG Cable) | S/C | 230 | 7 | 0 | 0 | 0 | 0 | JUN-21 | DEC-21 | Total section 15. Laying work for section 13/15 Laying work for section 11/15 completed. Joints 15/42 completed. Work under progress.
33 | Checkanurani - Sembatty feeder | S/C on D/C | 230 | 26 | 103 | 103 | 103 | 29.5 | SEP-18 | JUN-21 | Work Completed.
34 | CMRL Central 230 kV SS to Pulianthope 400 kV SS (UG Cable) | S/C | 230 | 3.4 | 0 | 0 | 0 |  | SEP-17 | JUN-21 | Tender to be floated.
35 | CMRL Central Jail to proposed Mambalam 230kV GIS SS (UG Cable) | S/C | 230 | 9 | 0 | 0 | 0 |  | SEP-17 | JUL-21 | Guindy - R.A.Puram at Mambalam (UG Cable) energised on 10.06.19. CMRL Cental Jail to Mambalam 230 KV GIS SS: Total sections: 19. Laying 16/19 completed. Joints 9/54 completed. Work under progress.
36 | Dharmapuri (Palavadi) - Udanapally 230 kV S | D/C | 230 | 115 | 247 | 247 | 247 | 115 | JUN-21 | AUG-21 | Commissioned 07/21.
37 | KPSHEP - Parali lines on M/C towers | S/C | 230 | 0 | 238 | 0 | 0 |  |  | JUN-21 | Tender in process for reach 1 & 2. Tender to be floated for reach 3
38 | LILO in 230 kV Othakalmandapam - Ponnapuram at the proposed Edayarapalayam 400 kV SS | D/C | 230 | 50 | 43 | 39 | 35 | 8.56 | SEP-18 | MAR-22 | Work under progress. ROW issue in respect of land compensation.
39 | LILO in the existing 230 kV Shoolagiri - Karimangalam at the propsosed Uddanapally 230kV SS | D/C | 230 | 30 | 3 | 3 | 3 | 1.02 | SEP-18 | JUN-21 | Energised 0n 26.07.18
40 | LILO in the existing Dharmapuri (Palavadi) 400 kV SS to the proposed Uddanapally 230 kV SS | D/C | 230 | 136 | 247 | 247 | 247 | 114.36 | SEP-18 | DEC-21 | Energised line charged.
41 | LILO of Dharmapuri (Palavadi) 400 kV SS to the proposed Tirupattur 230 kV SS | S/C on D/C | 230 | 75 | 299 | 290 | 248 | 33.5 | SEP-18 | DEC-21 | Work under progress.
42 | LILO of KPSHEP - Kundah PH-III at Parali (400/230 kV S/S) | D/C | 230 | 0 | 0 | 0 | 0 |  |  |  | The existing LILO of KPSHEP - Kundah PH-III, 230 kv D/C line to Parali 400/230 kV S/S . And utilizing the existing 230kV corridor upto Parli.
43 | LILOof Sriperumbudur-Kadapperi at Porur 230KV SS (UG) Kadapperi to Porur (OH+UG) | D/C | 230 | 28 | 0 | 0 | 0 |  | MAR-18 | DEC-20 | UG cable work awarded to M/s Universal cable on 16.02.17.Total section 12 nos. Cable laying in the section completed. Joints 27/33 completed.
44 | LILO of Tonidapet - Mylapore at TNEB HQ (UG Cable) | D/C | 230 | 1 | 0 | 0 | 0 | 0 |  | SEP-20 | Dropped. Scheme will be completed while making LILO of CMRL Central to Mylapore feeder at TNEB HQ
45 | LILO the existing 230 kV Alundur - Thanjavur at the proposed Thuvankudy | M/C | 230 | 30 | 61 | 61 | 61 | 29.72 | JUN-21 | SEP-21 | All works completed.
46 | LILO the existing 230 kV P.P Nallur - Thanjavur at proposed Narimanam 230 kV SS | D/C | 230 | 30.4 | 0 | 0 | 0 |  | SEP-18 | MAR-22 | Revised administrative approval is under process.
47 | LILO the existing 230 kV P.P.Nallur - Thiruvarur at the proposed Narimanam 230 kV SS | D/C | 230 | 30.8 | 0 | 0 | 0 |  | SEP-18 | MAR-22 | Revised administrative approved is under process.
48 | Neyveli - TS-II to the proposed Neyveli 230/110 kV SS | D/C | 230 | 2 | 20 | 20 | 20 | 9.5 | SEP-18 | JUN-21 | Work completed. Energised on 26.12.19
49 | N.T. Kudy - Karaikudi line | S/C on D/C | 230 | 104 | 370 | 365 | 354 | 88.68 | SEP-21 | SEP-21 | Work under progress. RoW issues in 2 Locations.
50 | Palavady - Thirupathur line | D/C | 230 | 75 | 299 | 290 | 248 | 33.5 | AUG-21 | DEC-21 | Work under progress.
51 | Palladam - Ingur | S/C on D/C | 230 | 62 | 249 | 239 | 209 | 40.7 | APR-13 | MAR-22 | Line energised from Palladam to Kurukkathi tapping points ie up to loc 160. Severe Row issue between Loc no 160 - 190 .Court case pending in High Court.Case to be listed.
52 | Sholinganallur - KITS | D/C | 230 | 24 | 50 | 47 | 44 | 20.8 |  | DEC-21 | 6 Locations under RF issue. Pending at Regional Office. Also, Court case in 4 locations. (Marsh land)
53 | Sriperumbudur -Korattur (Changing of conductor) | S/C | 230 | 20 | 70 | 0 | 0 | 12 | SEP-06 | DEC-20 | Line work is under modification. Revised administrative approval is under process.
54 | Thiruvalam - Singarapet Feeder (Loc1 to 4) | D/C | 230 | 2 | 0 | 0 | 0 | 2 |  | AUG-21 | Commissioned 07/21.
55 | Vellalavidhuthi 400 kV SS - Nemmeli Thippayakudy 230 kV SS | S/C | 230 | 23 | 93 | 93 | 93 | 22.93 | SEP-21 | DEC-21 | Work completed.
56 | Vellalaviduthi 400 kV SS - Thuvakudy 230 kV SS | S/C on D/C | 230 | 33 | 125 | 125 | 125 | 32.93 | SEP-21 | DEC-22 | Work completed.
57 | Vellalaviduthi 400 kV SS to Mondipatti 230 kV SS | S/C on D/C | 230 | 90 | 354 | 352 | 352 | 87.47 | SEP-18 | DEC-22 | Work under progress. RoW issues - 2 locations - 1 No Court case.
58 | Vellalaviduthi - existing Pudukottaai 230 kV SS | S/C on D/C | 230 | 21 | 84 | 84 | 84 | 20.62 | SEP-21 | DEC-22 | Work under progress. Railway crossing approval awaited.
59 | Villupuram - Ulundurpet | S/C | 230 | 55 | 183 | 181 | 124 | 20 | SEP-21 | DEC-21 | Work under progress.
60 | Basin Bride - Pulianthope (UG Cable) | S/C | 220 | 2 | 0 | 0 | 0 |  |  | JUN-21 | Work awarded. Can be taken up only on completion of pulianthope 400 .KV GIS SSWork to be taken up on completion of Pulianthope 400 KV GIS SS.
61 | Common Point (from Karamadai) - Thudialur (2nd Circuit) | S/C | 220 | 20 | 68 | 68 | 68 | 38.67 | AUG-15 | JUN-21 | Both the Ckts energised on 19.12.16 and 06.02.17
62 | Ingur - Arasur (PGCIL) | S/C | 220 | 54 | 228 | 226 | 220 | 33 | SEP-21 | DEC-21 | Police protection awaited for Stub setting at Loc.8& 18. Land owners are demanding land compensation amount before commencement of work. Being followed with the District Collector's office.
63 | Kilpauk - CMRL Central Jail | S/C | 220 | 10 | 0 | 0 | 0 |  |  | DEC-21 | Tender finalised. Work to be awarded.
64 | LILO of Existing Paramathi - Alundur at Valayapatty | D/C | 220 | 60 | 116 | 111 | 110 | 55.94 | SEP-21 | SEP-21 | Work under progress. PWD approval obtained for river crossing at 6 locations. Work commenced and stub completed for 1 location. But due to water discharge from 22.05.2021, work couldnot be proceeded for balance locations.
65 | LILO of the exisiting 230 kV Ingur - Kurukathi - Palladam feeder at sanctioned Rasipalayam 400 kV S/S | D/C | 220 | 50 | 59 | 57 | 51 | 1 |  | MAR-22 | Court case involved. Land owners are demanding yield compensation. Being followed up with Revenue officials.
66 | LILO of the exisiting 230 kV Myvady - Kurukathi - Pugalur feeder at sanctioned Rasipalayam 400 kV SS | D/C | 220 | 46 | 93 | 90 | 89 | 22.14 | SEP-21 | MAR-22 | Work under progress. Row issue involved.
67 | Ottiyambakkam - Kits S/s | D/C | 220 | 24 | 50 | 47 | 44 | 20.8 |  | JUN-21 | 6 Locations under RF issue. Pending at Regional Office. Also, Court case in 4 locations. (Marsh land)
68 | Ottiyambakkam - Omega | D/C | 220 | 70 | 150 | 147 | 147 | 66 | APR-14 | DEC-21 | Works are under progress. Reserve Forest clearance under process for 3 locations.
TRANSMISSION CORPORATION OF ANDHRA PRADESH LIMITED(APTRANSCO)
1 | Chilakaluripeta (PG) to Chilakaluripeta (AP) | D/C | 400 | 64 | 0 | 0 | 0 |  | AUG-19 | SEP-20 | Tenders floated on 13.12.2018 Tenders finalized and LOI issued on 21.02.2019.Detailed purchase order issued on 30.05.2019.
2 | Elluru-Gudivada (Q) | D/C | 400 | 160 | 0 | 0 | 0 |  | AUG-19 |  | This line is cancelled as the contract for construction of 400kV SS at Eluru is rescinded.
3 | Gudivada-Chilakaluripeata (Q) | D/C | 400 | 206 | 0 | 0 | 0 |  | AUG-19 |  | The line is cancelled as the contract for construction of 400kV SS at Chilakaluripeta is rescinded.
4 | Jammalamdugu-Gani (QM) | D/C | 400 | 240 | 0 | 0 | 0 |  | AUG-19 |  | The Scheme is under revision.
5 | LILO of 400kV Kalpaka-Vemagiri at Kallpaka | D/C | 400 | 40 | 0 | 0 | 0 |  | AUG-20 |  | The scheme not yet formulated
6 | LILO of 400kV VTS-Sattenapalli at CRDA Amaravathi SS-I | D/C | 400 | 40 | 0 | 0 | 0 |  | AUG-20 |  | The scheme not yet formulated
7 | LILO of 400kV VTS-Sattenapalli at CRDA Amaravathi SS-II | D/C | 400 | 40 | 0 | 0 | 0 |  | AUG-21 |  | The scheme not yet formulated
8 | LILO of existing VTS-Sattenapalli at oroposed Inavolu/Thullurs SS | D/C | 400 | 20 | 0 | 0 | 0 |  | AUG-18 | MAR-20 | Administrative Approval issued for the LILO of existing VTS-Sattenapalli at proposed Thallayaplem SS.
9 | LILO of Hindupur - Kadapa (Cuddapah) at NP Kunta PS (GEC-II) | D/C | 400 | 18 | 0 | 0 | 0 |  |  |  | Not pertains to APTRANSCO
10 | LILO of Kadapa (Cuddapah) - Kolar S/C line at NP Kunta PS (GEC-II) | D/C | 400 | 14 | 0 | 0 | 0 |  |  |  | Not pertains to APTRANSCO
11 | LILO of Vemagiri-I Sattenpali at Eluru | D/C | 400 | 40 | 0 | 0 | 0 |  | AUG-18 | NOV-20 | The scope of the work is modified as the contract for construction of 400kV SS at Eluru is rescinded.
12 | MAilavaram - Kondapura (Jammalamadugu) (GEC-II) | D/C | 400 | 21 | 0 | 0 | 0 |  | JUL-20 |  | The line is cancelled as the scheme is modified by laying 220kV lines from pooling stations at Mylavaram Ultra Mega Solar Park (1000MW ) at kadapa dist. of AP to the existing 400kV Jammamalamadugu in a Cost effective manner instead of constructing separate 400kV Substation at Mylavaram.
13 | Mylavaram-Jammalamdugu QMDC Line | D/C | 400 | 21 | 0 | 0 | 0 |  | JUL-20 | JUL-20 | The line is cancelled as the scheme is modified by laying 220kV lines from pooling stations at Mylavaram Ultra Mega Solar Park (1000MW ) at kadapa dist. of AP to the existing 400kV Jammamalamadugu in a Cost effective manner instead of constructing separate 400kV Substation at Mylavaram.
14 | Narnoor-Aspiri (QM) | D/C | 400 | 180 | 0 | 0 | 0 |  | AUG-19 |  | The scheme is cancelled as the uncommissioned RE connectivities which are proposed to connect Aspiri scheme are envisaged in 10,000MW Solar Power establishment Scheme at other Substations.
15 | NTTPS, Vijayawada TPS-existing Sattenapalli SS | D/C | 400 | 120 | 0 | 0 | 0 |  | AUG-18 | MAR-20 | Instead of taking up seperate Evacuation line from VTPS -stage-V, it is proposed to take up Replacement of ACSR Moose conductor with INVAR conductor from 400kV VTS - Sattenapalli DC line and Renovation of existing VTPS -I&II Feeder Bays at Sattenapalli SS . Tenders will be called soon.
16 | Polavaram-Kamavarapukota (QM) | D/C | 400 | 140 | 0 | 0 | 0 |  | AUG-19 | AUG-20 | The scope of the work revised due to site constraints. 400kV QMDC Line from 400kV Polavaram SS to 400/22/11 kV Guddigudem SS is proposed in place of earlier approved 400kV Polavaram-K.Kota QMDC Line.Tenders floated with revised scope of work on 28.01.2019.Tenders finalized and LOI placed on 29,04.2019 .Line survey works completed. Works will be taken up after finalization of award of contract of Polavaram Hydro Electric Project by APGENCO.
17 | Urvakonda-Uravkonda-II | D/C | 400 | 100 | 0 | 0 | 0 |  | AUG-18 |  | May be deleted that CEA , during 42nd standing committe meeting recommended to take up 400/220kV Uravakonda  2 Substation with 3 x 500MVA PTRs + 1 x 125 MVAR Bus Reactor in the existing 400/220KV Uravakonda - 1 Sub-station of APTRANSCO duly extending the 400 KV Bus without constructing a new 400/220kV Sub-station.
18 | Vemagiri - Kamavarapukota | D/C | 400 | 185 | 268 | 235 | 202 | 91.92 | SEP-21 | JUN-21 | Works are being executed in slow pace due to ROW issues and due to limited working season (45 days only) at 137 Locations
19 | Chittoor 400 kV SS-Mananapalli | D/C | 220 | 130 | [5 empty] | MAR-17
20 | Garividi-Bobbili | D/C | 220 | 75 | 130 | 126 | 115 | 51 |  | DEC-16 | Works are under progress
21 | Garividi - Garividi | D/C | 220 | 70
22 | Garividi - Pydibhimavaram | D/C | 220 | 100 | 169 | 169 | 169 | 46 |  | FEB-21 | Works under progress
23 | Hindupur (400) - Hindupur (220)(GEC-I) | D/C | 220 | 31 | 54 | 14 | 2 | 0 | SEP-21 | SEP-21 | Tower foundations & Tower erection works are under progress.
24 | Hindupur (400) - Pampanur Tanda (220)(GEC-I) | D/C | 220 | 70 | 257 | 0 | 0 | 0 | SEP-21 | SEP-21 | Work in Progress.
25 | Hindupur - Penukonda | D/C | 220 | 54 | 100 | 18 | 10 | 0 | SEP-21 | SEP-21 | work is under progress
26 | Jammalamadugu (400) - Tadipatri (220) (GEC-I) | D/C | 220 | 80
27 | Jammalamadugu - Betamacherla | D/C | 220 | 152 | 259 | 241 | 214 | 37.48 | MAY-21 | MAY-21 | Works are under progress.
28 | Jammalamadugu - Porumamilla | D/C | 220 | 198 | 338 | 328 | 327 | 192.88 | JAN-15 | OCT-18 | Works are under progress. 10 Nos tower foundations and 2.8 km stringing in Forest reach are pending for want of forest clearance.
29 | Kalyandurg-Anantapur | S/C | 220 | 61 | [5 empty] | DEC-16
30 | Kamavarapukota - Kamavarapukota | D/C | 220 | 30 | 16 | 7 | 0 | 0 |  | DEC-20 | Works are under progress
31 | LILO of onc Ckt. of 220kV Undi-Eluru (Gudivada) line to proposed S/S at Akiveedu in West Godavari District | S/C | 220 | 3 | 0 | 0 | 0 | 3 |  | JUN-21 | Commissioned 05/21.
32 | LILO of Uravakonda - Kalyandurga at Borampalli | D/C | 220 | 22 | 0 | 0 | 0 |  |  |  | Charged on 19.09.2020
33 | Maradam (from 400kV Maradam) - Pydibhimavaram line | D/C | 220 | 46 | 169 | 169 | 169 | 46 | JUN-21 | JUN-21 | Commissioned 05/21.
34 | Muddanur-Anantapur (3rd line) | S/C on D/C | 220 | 100 | [5 empty] | DEC-16
35 | Muddanur (RTPP) - Dharmavaram | D/C | 220 | 200
36 | Narketpally_Suryapet | S/C on D/C | 220 | 60 | [5 empty] | DEC-16
37 | Narsapur-Doultabad | S/C | 220 | 15 | [5 empty] | DEC-16
38 | Narsapur-Manoharabad | S/C | 220 | 15 | [5 empty] | DEC-16
39 | Nirmal-Nandipeta | S/C | 220 | 20 | [5 empty] | DEC-16
40 | Nizamabad-Janakampeta | S/C | 220 | 10 | [5 empty] | DEC-16
41 | Oddugudem-Koyagudem | D/C | 220 | 20 | [5 empty] | DEC-16
42 | Oglapur(Warangal 400 kV SS)-Warangal 220 kV SS | D/C | 220 | 36 | [5 empty] | DEC-16
43 | Peddapuram-Koruprolu | D/C | 220 | 130 | [5 empty] | MAR-17
44 | ppannadorapalem - Bobbili (Ckt-II) | D/C | 220 | 84 | 0 | 0 | 0 |  |  |  | Charged on 29.03.2017
45 | Somayajulapalli - Gani/Panyam S/S | D/C | 220 | 20
46 | Uravakonda - Kalyanduring | D/C | 220 | 100 | 160 | 147 | 137 | 42 | NOV-14 | OCT-19 | Works are under progress.
47 | Badvel-Porumamilla (2nd Ckt) (GEC-I) | S/C on D/C | 132 | 0 | 0 | 0 | 0 |  |  |  | Charged on 21.08.2018
48 | LILO of Both Circuits of Badvel-Porumamilla at Porumamilla(GEC-I) | M/C | 132 | 4 | 0 | 0 | 0 |  |  | AUG-19 | line charged on 28.8.19
49 | LILO of both circuits of Suzlon Wind-Jammalamadugu(132) at Jammalamadugu(400) (GEC-I) | M/C | 132 | 24 | 35 | 35 | 33 | 0 | MAR-18 | APR-21 | Work in Progress.
50 | Penukonda(220) - Penukonda (132) | D/C | 132 | 20 | 0 | 0 | 0
Transmission Corporation of Telangana Limited(TSTRANSCO)
1 | Vadarevu - Amangal | S/C | 765 | 240 | 0 | 0 | 0 | 0 |  | AUG-16
2 | Chandlapur SS to Tukkapur SS (TMDC) | D/C | 400 | 60 |  |  |  |  | SEP-17
3 | Damacherla TPP - Choutuppal | D/C | 400 | 300 |  |  |  |  | SEP-18
4 | Damacherla TPP - Dindi | D/C | 400 | 280 |  |  |  |  | SEP-18
5 | Damaracherla TPP - Jangaon | D/C | 400 | 310 |  |  |  |  | SEP-18
6 | Damaracherla TPP - Maheswaram (TS) | D/C | 400 | 310 |  |  |  |  | SEP-18
7 | Julurupadu - Kamalapuram LI TMDC line | D/C | 400 | 80 | 123 | 115 | 100 | 26.6 | FEB-20 |  | 9 Nos ROW.
8 | Kethiredypally - AP-41 line (Twin HTLS Quad Conventional Towers) | D/C | 400 | 53 | 79 | 79 | 79 | 51.12 | JUN-21 | JUN-21 | Stringing works are under progress
9 | LILO of both Ckt. KTPP - Gajwel line to Chandlapur SS (TMDC) | M/C | 400 | 164 |  |  |  |  | SEP-17
10 | LILO of both Ckt. of Nedunuru - Telangana STPP line to Yellampalli | M/C | 400 | 40 |  |  |  |  | SEP-17
11 | LILO of both Ckt. of SCCL - Gajwel line to Ramadugu SS (QMDC) | D/C | 400 | 72 |  |  |  |  | SEP-17
12 | LILO of both ckt. of SCCL - Ramadugu QMDC line to Yellampalli SS | M/C | 400 | 32 |  |  |  |  | SEP-17
13 | LILO of existing 400kV Khammam - Mamidipally TMDC line - Choutuppal S/S | D/C | 400 | 0 | 48 | 38 | 0 |  |  |  | Tower Foundation works are under progress.
14 | LILO of suryapet - Kethireddypalli (Manikonda) line to Uddandapur SS | D/C | 400 | 120 |  |  |  |  | SEP-18
15 | Narlapur SS - Yedula SS | D/C | 400 | 60 |  |  |  |  | AUG-21
16 | Narsapur SS to Tukkapur SS (TMDC) | D/C | 400 | 140 |  |  |  |  | SEP-17
17 | NTPC - Ramadugu (QMDC) line | D/C | 400 | 104 | 161 | 161 | 161 | 98.23 | AUG-19 | JAN-20
18 | Ramadugu SS to Tippapur SS (QMDC) | D/C | 400 | 40 |  |  |  |  | SEP-17
19 | Ramdugu SS - Medaram SS (QMDC) | D/C | 400 | 42 |  |  |  |  | SEP-17
20 | Sirichilla (NTPC) Common Point ) - Narsapur | D/C | 400 | 171 | 492 | 492 | 492 | 346.9 | FEB-19 | JAN-20
21 | Telangana STPP - Narsapur | D/C | 400 | 354 | 492 | 492 | 492 | 354 | DEC-19 | SEP-21 | Commissioned 08/21.
22 | Telangana STPP - Ramadugu | D/C | 400 | 104 | 161 | 161 | 161 | 104 | DEC-19 | SEP-21 | Commissioned 08/21.
23 | Tippapur SS to Chandlapur SS (QMDC) | D/C | 400 | 42 |  |  |  |  | SEP-17
24 | Vattem SS - Uddandapur SS | D/C | 400 | 100 |  |  |  |  | SEP-18
25 | Veltoor SS - Yedula SS | D/C | 400 | 100 |  |  |  |  | AUG-21
26 | Yadadri TPP Switchyard - Choutuppal S/S | D/C | 400 | 0 | 259 | 216 | 98 |  |  |  | Tower Foundation and Erection works are under progress.
27 | Yadadri TPP switchyard - Damaracherla S/S | D/C | 400 | 0
28 | Yadadri TPP Switchyard - Dindi s/s | D/C | 400 | 0 | 290 | 209 | 136 |  |  |  | Tower foundation and Erection works are under progress.
29 | Yadadri TPP switchyard - Jangaon S/S | D/C | 400 | 0
30 | Yedula SS - Maheswaram SS | D/C | 400 | 260 |  |  |  |  | SEP-18
31 | Yedula SS - Vattem SS | D/C | 400 | 68 |  |  |  |  | AUG-21
32 | 2nd ckt. Stringing on existing line from Malyalpally - Jagityal line | S/C | 220 | 58 | 0 | 0 | 0 | 58 |  | AUG-21 | Commissioned 11/18 (Late Reported),
33 | 400/220 kV Janagaon s/s -220/132/33 Janagaon s/s | D/C | 220 | 7 | 0 | 0 | 0 | 7 |  | AUG-21 | Commissioned 05/19 (Late Reported).
34 | Akkaram-Markook | D/C | 220 | 18 | 0 | 0 | 0 | 18 |  | JUL-21 | Commissioned 04/20 (Late Reported).
35 | Asupaka - Aswaroapet line | D/C | 220 | 40 | 73 | 73 | 73 | 40 | NOV-17 | AUG-21 | Commissioned 04/18 (Late Reported).
36 | Chilakallu - Narketpally | D/C | 220 | 25 | 42 | 42 | 42 | 25 |  | JUL-19 | It is 220kV LILO of Chilakallu - Narketpally to the 220kV Huzurnagar SS. This Line charged on 05.12.2018.
37 | Dindi -Existing Kondamallepally line | D/C | 220 | 66 | 118 | 115 | 106 | 42 | JUN-21 | DEC-21 | Work under Progress.
38 | Dindi - Nagarkurnool | S/C | 220 | 79 | 138 | 138 | 138 | 79 | JUN-17 | AUG-21 | Commissioned 04/19 (Late Reported).
39 | Existing 220kV from Proposed Damaracharla -Huzurnagar | D/C | 220 | 77 | 136 | 93 | 49 |  | JAN-22 |  | Works under progress.
40 | Existing TMDC line form Proposed S/S Damaracharla-Miryalaguda | D/C | 220 | 34 | 63 | 54 | 45 |  | JUL-21 | NOV-21 | Works under progress.
41 | Gajwel - Akkaram (TMDC) | D/C | 220 | 14 | 0 | 0 | 0 | 14 |  | AUG-21 | Commissioned 02/20 (Late Reported).
42 | Gajwel - Siddipet line (on Galvanized Towers with Mosse ACSR) | D/C | 220 | 66 | 131 | 126 | 120 | 53 | SEP-19 | AUG-21 | work under progress
43 | Ghanapur s/s -CPRI (220kV Monopole DC/SC line) | D/C+S/C | 220 | 9 | 0 | 0 | 0 |  | NOV-21 | MAY-22 | Permission from National highways, HGCL,Forest Authority under process
44 | Janagon -Husnabad Proposed line | D/C | 220 | 84 | 139 | 137 | 123 | 20 | DEC-21 |  | Works under progress.
45 | Julurupadu - Pedagopathi line | D/C | 220 | 90 | 74 | 74 | 74 | 90 | SEP-18 |  | Commissioned 12/18 (Late Reported).
46 | Kalwakurthy-Dindi 3rd line | S/C | 220 | 24 | [5 empty] | DEC-16
47 | Kamareddy-Bhumpally | S/C | 220 | 15 | [5 empty] | DEC-16
48 | Kethireddypalli (Manikonda) - Kanakamamidi DC line | D/C | 220 | 10 | 22 | 22 | 22 | 10 | JUN-17 |  | Line charged on 13.12.2018
49 | Kethireddypalli (Manikonda) SS to Kanakamamidi SS | M/C | 220 | 5 | 16 | 16 | 16 | 5 | SEP-17 |  | Line charged on 14.11.2018.
50 | Kethireddypally (Manikonda) - Kankamamidi line | D/C | 220 | 9 | 0 | 0 | 0 | 9 |  | AUG-21 | Commissioned 12/18 (Late Reported).
51 | LILO of 220kV XLPE UG cable Chandrayangutta - Imlibun to the proposed Chanchalguda | S/C | 220 | 1 | 0 | 0 | 0 | 1 | SEP-18 |  | Line charged on 26.02.2020
52 | LILO of Bhoothpur - Kalwakurthy at Thimmajipet | D/C | 220 | 2 | 4 | 4 | 4 | 1 |  | OCT-18 | Line charged on 07.06.2017
53 | LILO of Bhoothpur - Kalwakurthy at Thimmajipet (Ckt-II) | D/C | 220 | 2 | 4 | 4 | 4 | 1 |  | OCT-18 | Line charged on 07.06.2017
54 | LILO of both Ckts. Durshed-Sirchilla line at Ramadugu | D/C | 220 | 48 | 32 | 32 | 32 | 48 | SEP-19 | AUG-21 | Commissioned 03/20 (Late Reported).
55 | LILO of both Ckts. of Dindi - Bonguluru to Madugula and Maheshwaram | D/C | 220 | 18 |  |  |  |  | SEP-17
56 | LILO of both Proposed Ckts. of existing 220kV Malkaram-Narketpally at Choutuppal s/s | M/C | 220 | 62 | 61 | 35 | 0 |  | DEC-21 |  | Works under progress.
57 | LILO of Budidampadu - Bhongiri at Waddekothapally | D/C | 220 | 14 |  |  |  |  | DEC-13
58 | LILO of Dindi - Maheshwaram at Madugula | D/C | 220 | 6 | 0 | 0 | 0 | 6 |  | AUG-21 | Commissioned 08/18 (Late Reported).
59 | LILO of Durshed - Seddipet at Nadunuru line | D/C | 220 | 20 |  |  |  |  | SEP-17
60 | LILO of existing 220kV Salivagu-Bheemghanpur (Twin Mosse) line at Ramappa proposed point at KTPP s/s | D/C | 220 | 44 | 83 | 60 | 30 |  | FEB-21 | DEC-21 | Works under progress.
61 | LILO of existing 220kV (Twin Moose) Pulukurthy-Bheemghanpur (Twin Mosse) line at Ramappa Point KTPP s/s | D/C | 220 | 48 | 88 | 85 | 68 | 6 | FEB-21 | NOV-21 | Works under progress.
62 | LILO of existing RSS (Malayalapalli) - Bheemgal proposed line at Ramadugu (Karimnagar District) | S/C | 220 | 24 | 0 | 0 | 0 |  | SEP-19 |  | Work cancelled as new 220/11kV Rampur is taken up
63 | LILO of Ghanapur - Chandrayan Gutta to Kachavani Singaram | D/C | 220 | 4 | 0 | 0 | 0 |  | SEP-18 |  | Works yet to be taken up
64 | LILO of Ghanapur - Hayathnagar to Kachavani Singaram DC line | D/C | 220 | 4 |  |  |  |  | SEP-18
65 | LILO of Nirmal - Renzal at Mupkal | S/C | 220 | 1 | 0 | 0 | 0 | 1 |  | JUL-21 | Commissioned 05/20 (Late Reported).
66 | LILO of Oglapur - Durshad at Huzurabad | D/C | 220 | 20 | 0 | 0 | 0 | 20 |  | AUG-21 | Commissioned 07/17 (Late Reported).
67 | LILO of one Ckt. of 220kV Mahabubabad-Warangal propossed line at Ammavaripet | D/C | 220 | 64 | 111 | 82 | 53 |  | MAY-21 | DEC-21 | Works under progress.
68 | LILO of one Ckt. of Mamidipally - Shadnagar at Kothur S/S | D/C | 220 | 1 | 4 | 4 | 4 | 1 | JUN-19 | JUL-21 | Commissioned 10/20 (Late Reported).
69 | LILO of one Ckt. of Shamshabad - Kethireddypalli (Manikonda) at Kothur S/S | D/C | 220 | 19 | 36 | 36 | 36 | 19 | JUN-19 | JUL-21 | Commissioned 10/20 (Late Reported).
70 | LILO of Regumangadda - Gudipalligattu at Yelluru Water Grid s/s | D/C | 220 | 7 | 0 | 0 | 0 | 7 |  | AUG-21 | Commissioned 11/17 (Late Reported).
71 | LILO of RSS -Bheemgal Feeder at Rampur s/s | D/C | 220 | 2 | 0 | 0 | 0 | 2 |  | AUG-21 | Commissioned 05/19 (Late Reported).
72 | LILO of RSS -Nagaram at Ramagundam Fertillizers and Chemicals Limited (RFCL) | D/C | 220 | 22 | 0 | 0 | 0 | 22 |  | AUG-21 | Commissioned 03/19 (Late Reported).
73 | LILO of RSS -Nrimal at Jagityal line | D/C | 220 | 3 | 0 | 0 | 0 | 3 |  | AUG-21 | Commissioned 11/19 (Late Reported).
74 | LILO of Shamshabad-Yeddumailaram line and Shadnagar-Shankerpally line to proposed at Kethireddypally | D/C | 220 | 14 | 0 | 0 | 0 | 14 |  | AUG-21 | Commissioned 11/18 (Late Reported).
75 | LILO of Vemnur-Nirmal to 220kv Jagityal s/s | D/C | 220 | 3 | 0 | 0 | 0 | 3 |  | AUG-21 | Commissioned 11/19 (Late Reported).
76 | LILO of V-Lower Sileru-II - proposed Pump House-1 at B.G. Kottur | D/C | 220 | 40 | 74 | 74 | 74 | 33.38 | FEB-20 | JAN-20
77 | LILO of Yelluru - Gudipalligattu at Gouridevipally | S/C | 220 | 4 | 0 | 0 | 0 | 4 |  | AUG-21 | Commissioned 12/17 (Late Reported).
78 | LILO to Mahabubabad from Existing 220kV at Budidampadu - Warangal DC line | M/C | 220 | 24 | 20 | 20 | 20 | 24 | JUN-17 |  | Line charged on 29.01.2018
79 | Maheshwaram 400/220 kV SS to Fabcity 220kV SS | D/C | 220 | 47 |  |  |  | 47 | SEP-17 | AUG-21 | Commissioned 08/17 (Late Reported).
80 | Manuguru - BTPS | D/C | 220 | 46 | 0 | 0 | 0 | 46 |  |  | Commissioned 09/20 (Late Reported).
81 | Marripally common point- Hayatnagar S/S XLPE cable | DC UG cable | 220 | 14 | 0 | 0 | 0 | 7.5 |  | MAY-19 | Works are under progress.13/14 Nos Cable joints completed and remaining works are under progress
82 | Narketpally - Udaya Samudram (LIS) | D/C | 220 | 18 | 0 | 0 | 0 | 18 |  | AUG-21 | Commissioned 03/18 (Late Reported).
83 | Narsapur -Bowrampet on Monopole towers (Part of 220kV Narsapur-Bowrampet D/C line) | D/C | 220 | 7 | 21 | 0 | 0 |  | NOV-21 | MAY-22 | Survey work under progress. Monopole structure revised design approval under process.
84 | Narsapur -Bowrampet with 220 kV 1200 Swmm XLPE UG Cable (Part of 220kV Narsapur-Bowrampet D/C line) | D/C | 220 | 7 | 1 | 0 | 0 |  | NOV-21 | MAY-22 | "Detailed Survey approved.cable manufacture clearance under progress . 220 KV DC line from 400 KV Narsapur to 220kV Bowrampet is taken up in three parts i.e M/C - over head line (136ckm) +7 ckm UG Cable + 7 ckm Line on Monopoles"
85 | Narsapur -Meenajipet line | D/C | 220 | 48 | 0 | 0 | 0 | 48 |  | AUG-21 | Commissioned 02/20 (Late Reported).
86 | Narsapur- Proposed Bowrampet line | D/C | 220 | 136 | 136 | 132 | 119 | 109.37 | NOV-21 | DEC-21 | work under progress
87 | Narsapur to Toopran & LILO of Gajwel - Minpur to Toopran line | D/C | 220 | 79 | 0 | 0 | 0 |  | DEC-17 |  | Works yet to be taken up
88 | Nirmal - Indravelly (Utnoor) proposed line at Adilabad District | D/C | 220 | 199 | 345 | 345 | 345 | 199 | JUN-21 | SEP-21 | Commissioned 08/21.
89 | Nirmal -Renzal line | D/C | 220 | 136 | 0 | 0 | 0 | 136 |  | AUG-21 | Commissioned 02/20 (Late Reported).
90 | Nirmal s/s - Existing 220/132kV Nirmal s/s | D/C | 220 | 9 | 0 | 0 | 0 | 9 |  | AUG-21 | Commissioned 12/17 (Late Reported).
91 | Nirmal Upgraded 220/132kV Ranjal SS | D/C | 220 | 136 | 228 | 228 | 228 | 136 | NOV-17 |  | Line charged on 15.02.2020
92 | Parigi SS to Lakshmidevipalli | D/C | 220 | 20 |  |  |  |  | SEP-17
93 | Ramadugu - Rampur | D/C | 220 | 70 | 0 | 0 | 0 | 70 |  | JUL-21 | Commissioned 06/20 (Late Reported).
94 | Rampur -Rajeshwar Rao Peta s/s | D/C | 220 | 72 | 0 | 0 | 0 | 72 |  | AUG-21 | Commissioned 06/19 (Late Reported).
95 | RC Puram 400kV to Raidurg 220kV | D/C | 220 | 10 |  |  |  |  | SEP-17
96 | Sitapuram -Huzurnagar line | D/C | 220 | 59 | 0 | 0 | 0 | 59 |  | AUG-21 | Commissioned 12/18 (Late Reported).
97 | Sundilla - Annaram line | D/C | 220 | 58 | 0 | 0 | 0 | 58 |  | AUG-21 | Commissioned 09/18 (Late Reported).
98 | Sundilla - Medigadda line | D/C | 220 | 148 | 0 | 0 | 0 | 148 |  | AUG-21 | Commissioned 09/18 (Late Reported).
99 | Thimmajipet to Jadcherla DC line | D/C | 220 | 40 | 0 | 0 | 0 |  | SEP-17 |  | As per the field condition, not yet taken up.
100 | Timmajipet - Balanagar | D/C | 220 | 60 |  |  |  |  | SEP-17
101 | Yeddumailram - Pargi | D/C | 220 | 135 | 137 | 137 | 137 | 90 |  | MAR-19 | Works are in progress
102 | Yellampalli - Goliwada | D/C | 220 | 1 |  |  |  |  | SEP-17
103 | Yellampalli - Sundla | D/C | 220 | 30 |  |  |  |  | SEP-17
104 | Yellampalli to Kaleshwaram | D/C | 220 | 60 |  |  |  |  | SEP-17
TRIPURA STATE ELECTRICITY CORPORATION LIMITED(TSECL)
1 | Surajmani nagar-P.K.Bari | D/C | 400 | 260 | 0 | 0 | 0 | 0 |  | MAR-17 | Fund not yet tied up. Proposed under World Bank Financing /SPA/NEC.
2 | AGTP - Agartala line | D/C | 132
3 | AGTP - Kumarghat line | S/C | 132
4 | Gamai Tilla - Dhalabil | S/C | 132 | 31 | 107 | 101 | 78 | 17 |  | SEP-13 | ROW problems affected the work
5 | LILO of Rokia - Udaipur at Melaghat for connection to Monoarchak | D/C | 132 | 20 | 40 | 0 | 0 | 0 |  | JUN-15
6 | Monarchak - Surajmani Nagar | D/C | 132 | 43 | 154 | 145 | 128 | 15 |  | AUG-20 | RoW issues. TSECL has connected a portion of the said D/C line splitting the existing Rokhia - Udaipur 132 KV S/C line near Melaghar (12.178 Km distance from Monarchak) thereby connecting Monarchak with Rokhia and Udaipur sub-stations. The said arrangement has already been commissioned and is in operation w.e.f January 2015 for evacuation of Monarchak Power.
7 | P.K. Bari - Kanchanpur | S/C | 132 | 47 | 113 | 109 | 99 | 17 |  | MAR-15 | All works completed in non forest land. Stage- I clearance received and compliance for conditions completed.
8 | Surajmani Nagar - Badarghat | D/C | 132 | 6 | 0 | 0 | 0 | 0 |  | AUG-16 | Fund proposed in World Bank.
9 | Surajmani Nagar - Rokhia | D/C | 132 | 20 | 80 | 68 | 56 | 7 |  | DEC-18 | RoW issue
10 | Surajmani Nagar - Udaipur | D/C | 132 | 50 | 50 | 0 | 0 | 0 |  | JUN-15 | Proposed under NEC.
U.P. POWER TRANSMISSION CORPORATION LTD.(UPPTCL)
1 | Agra - Gr. Noida line | S/C | 765 | 200 | 411 | 411 | 411 | 159 |  | MAR-21 | charged on 18.03.2021
2 | Agra (UP) - Greater Noida (UP) | S/C | 765 | 0 | 0 | 0 | 0 |  |  |  | To be deleted
3 | Anpara D - Unnao | S/C | 765 | 426 | 1225 | 1225 | 1225 | 426.14 | AUG-19 | SEP-21 | 1) Earthing work in progress. OPGW Testing in progress. 2) Contract terminated vide letter no. 243 dt. 15.02.20220, termination put on hold on the request of the firm.
4 | Ghatampur TPS-Agra line | S/C | 765 | 240 | 579 | 579 | 579 | 229 |  | APR-21 | Energized (Antithept) from Agra end on 30.04.2021. Being constructed in TBCB mode by M/s Adani Transmission Ltd . Anti theft charged
5 | Ghatampur TPS - Agra (UP) | S/C | 765 | 0 | 0 | 0 | 0 |  |  |  | To be deleted
6 | Ghatampur TPS - Hapur | S/C | 765 | 0 | 0 | 0 | 0 |  |  |  | To be deleted
7 | Ghatampur TPS-Hapur Line | S/C | 765 | 400 | 1052 | 1047 | 1045 | 407 |  | OCT-21 | Work in progress. Being constructed in TBCB mode by M/s Adani Transmission Ltd. Work in progress..
8 | LILO of Anpara D-Unnao line at Obra | S/C | 765 | 40 | 28 | 28 | 28 | 8 |  | SEP-21 | Work completed , Being constructed in TBCB mode by M/s Adani Transmission Ltd. Work in progress..
9 | LILO of Mainpuri - G Noida at Jawaharpur TPS | S/C | 765 | 30 | 66 | 66 | 66 | 21.97 |  | SEP-21 | Work completed. Being constructed in TBCB mode by PGCIL. Work in progress.
10 | aligarh - Shamli Line | D/C | 400 | 180 | 739 | 681 | 589 | 199.98 |  | DEC-21 | 1) Gamg work in progress, Foundation-08 gangs, Erection-08 gang & Stringing-06 ROW at 25 loc. 2) Contract termination vide letter no. 233 dt. 14.02.2020, termination being put on hold.
11 | Badaun-Sambhal Line | D/C | 400 | 90 | 224 | 224 | 224 | 76.76 |  | SEP-21 | All work completed, Line expected to be charged within one week.
12 | Ballia (PG)-Rasra Line | S/C | 400 | 35 | 115 | 114 | 114 | 35.65 |  | JUN-21 | To be deleted
13 | Ghatampur TPS - Kanpur (PG) line | D/C | 400 | 0 | 0 | 0 | 0 |  |  |  | To be deleted
14 | Ghatampur TPS-Kanpur PG Line | D/C | 400 | 120 | 138 | 138 | 138 | 98 |  | MAY-21 | 765 KV PG at Rania Sub-station 01 nos. Bay has been energized by PGCIL on 13.05.2021 and completed both the circuits of the line and connected to Gantry at Rania end.Being constructed in TBCB mode by M/s Adani Transmission Ltd. Work in progress.
15 | Gonda - Shahjehanpur (PG) | D/C | 400 | 460 | 543 | 296 | 140 | 0 |  |  | The project was being developed under TBCB mode.
16 | Jawahapur TPS-Firozabad Line | D/C | 400 | 80 | 204 | 204 | 203 | 68.67 |  | JUL-21 | Energized (Antitheft) on 07 and 08.07.2021. Being constructed in TBCB mode by PGCIL. Work in progress.
17 | LILO of 400 kV Aligarh-Sikandrabad at Harduaganj TPS Line | D/C | 400 | 61 | 84 | 84 | 84 | 61 |  | JUN-21 | Commissioned 05/21.
18 | LILO of ckt-II of Kursi Rd PG- Unnao line at Hardoi Rd (Jehata) | D/C | 400 | 25 | 45 | 45 | 45 | 25 | APR-21 | SEP-21 | Commissioned 08/21.
19 | LILO of ckt-I of 400 kV DC Kursi Rd PG- Unnao line at Hardoi Rd(Jehata) | D/C | 400 | 34 | 57 | 57 | 57 | 34 | APR-21 | SEP-21 | Commissioned 08/21.
20 | LILO of Ckt.-I of Unchahar (NTPC) - Fatehpur PGCIL line at Raebareli | D/C | 400 | 65 | 106 | 106 | 106 | 65.02 | OCT-21 |  | Work completed.
21 | LILO of Gorakhpur (PG) - Lucknow (PG) line Ckt.-III at Basti | D/C | 400 | 47 | 79 | 79 | 79 | 47 | MAR-20 | AUG-21 | Commissioned 07/21.
22 | LILO of Ibrahim Patti (PGCIL) - Kasaramau (Mau) at Rasra | D/C | 400 | 74 | 115 | 115 | 115 | 74 | JUN-21 | AUG-21 | Commissioned 07/21.
23 | LILO of jaunpur -Gajokhar at Junpur LIne | S/C | 400 | 60 | 0 | 0 | 0 |  |  | MAR-21 | There is no such line. Please remove this from the list.
24 | LILO of one ckt. Fatehpur-Unchahar at Malwan | D/C | 400 | 58 | 124 | 124 | 124 | 42 | JAN-20 | AUG-21 | Work held up due to water logging. Voltage Level 220 kV Line.
25 | LILO of one Ckt Obra C -Jaunpur at Obra | D/C | 400 | 30 | 0 | 0 | 0 |  |  | MAR-20 | To be deleted
26 | Mathura - Jawaharpuram | D/C | 400 | 220 | 0 | 0 | 0 |  |  |  | To be deleted.
27 | Obra-C-Jaunpur Line | D/C | 400 | 400 | 459 | 403 | 385 | 198 |  | AUG-21 | Work in progress.
28 | Panki TPS-Panki Line | D/C | 400 | 6 | 0 | 0 | 0 |  |  | SEP-21 | Work in progress.
29 | Panki TPS - Panki s/s | D/C | 400 | 0 | 0 | 0 | 0 |  |  |  | to be deleted
30 | Roza TPS-Badaun Line | D/C | 400 | 90 | 221 | 221 | 221 | 85 |  | APR-21 | energized on 02.04.2021. Being constructed in TBCB mode by M/s Adani Transmission Ltd. Line charged on 02.04.2021
31 | Sambhal-Moradabad Line | D/C | 400 | 100 | 0 | 0 | 0 |  |  |  | There is no such line. Please remove this from the list.
32 | Simbholi-Meerut Line | D/C | 400 | 40 | 79 | 78 | 76 | 26.72 |  | SEP-21 | Work in progress.
33 | Simbholi-Muradnagar-II Line | D/C | 400 | 50 | 209 | 146 | 112 | 5.06 |  | SEP-21 | Work in progress.
34 | Simbholi-Simbholi Line | D/C | 400 | 15 | 0 | 0 | 0 |  |  |  | To be deleted.
35 | Tanda TPS Extn- Basti (Q) | S/C | 400 | 43 | 137 | 137 | 137 | 87.72 | OCT-19 |  | Line energised on 14/03/2021. DC line.
36 | Varanasi (PG)-Jaunpur Line | D/C | 400 | 145 | 212 | 205 | 204 | 128.5 | OCT-21 | OCT-21 | Work is in progress.
37 | Anandnagar-Maharajganj Line | D/C | 220 | 50 | 0 | 0 | 0 |  |  |  | To be deleted
38 | Aurai - Mizapur | S/C | 220 | 43 | 152 | 129 | 77 | 0 |  | MAY-22 | Objection in DPR, New DPR has to be submitted.
39 | Aurai - Phoolpur | S/C | 220 | 71 | 223 | 212 | 178 | 41 |  | MAY-22 | Objection in DPR, New DPR has to be submitted.
40 | Badhaikalan (Muzaffarnagar) - Shamli line | D/C | 220 | 66 | 113 | 113 | 102 | 0 | JUN-21 | DEC-21 | Work in progress. Foundation & Erection work under progress.
41 | Bah (Agra) - Sirsaganj (Firozabad) line (GEC-II) | S/C | 220 | 0 | 140 | 68 | 15 | 0 |  |  | To be constructed in deposit scheme as par fund availability.
42 | Barabanki - Satrikh Road line | D/C | 220 | 49 | 79 | 79 | 79 | 15.6 | AUG-21 |  | Work in progress.
43 | Bhadrekhi (Orai) - Bah (Agra) line (GEC-II) | S/C | 220 | 0 | 0 | 0 | 0 |  |  |  | To be constructed in deposit scheme as par fund availability.
44 | Bhadrekhi (Orai) - Sikandera (Kanpur dehat) line (GEC-II) | S/C | 220 | 0 | 182 | 93 | 83 | 0 |  |  | To be constructed in deposit scheme as par fund availability.
45 | Bhopal Road-Khatauli Line | D/C | 220 | 60 | 0 | 0 | 0 |  |  |  | To be deleted.
46 | Firozabad (400)-Tundla | D/C | 220 | 50 | 0 | 0 | 0 |  |  | OCT-21 | 220 kV s/s Tundla is sanctioned on 21/01/2019 with connectivity thru' LILO of 220 kV Agra PG(765) - Firozabad(400) at Tundla(220).
47 | Gorakhpur-Anandnagar Line | D/C | 220 | 100 | 0 | 0 | 0 |  |  |  | Line Cancelled by TWC on dt. 09.09.2020.
48 | Greater Noida (765) - Integrated township Gr. Noida line | D/C | 220 | 80 | 159 | 159 | 159 | 80 | APR-21 | JUL-21 | Commissioned 06/21.
49 | Hamirppur-Banda Line | D/C | 220 | 140 | 0 | 0 | 0 |  |  | DEC-21 | 220kV S/s Hamirpur and 400 kV S/s Maheba in Jalaun distt sanctioned under MNRE scheme with DC ckt inter connectivity.
50 | Hamirpur-Sarh Line | D/C | 220 | 140 | 0 | 0 | 0 |  |  |  | To be deleted.
51 | Hardoi Road-Lucknow Line | D/C | 220 | 20 | 39 | 35 | 25 | 0 |  | SEP-21 | Work in progress.
52 | Hardoi Road-Sandila Line | D/C | 220 | 60 | 0 | 0 | 0 |  |  | MAR-21 | To be deleted
53 | Indirapuram - Pratap Vihar | D/C | 220 | 16 | 38 | 33 | 28 | 9 |  | OCT-21 | RoW-1) Status quo order from DRT-III Delhi court on location no- (34 to 38) in buildup area. Decision of court reserved on 26.02.2020, but decision couldn't till date. UPPTCL filed an urgent writ petition on 23.02.2021 in hon'ble High Court Delhi to vacate stay order of DRT court in public intrest. Matter is under scrutiny of the court. PTCC clearance received.Next hearing date os 13.08.2021 High court case won and work started Again stay order due to vendor applied case. Supreme court stay order.
54 | Jeheta (400)- Hardoi Rd (220) Interconnector | D/C | 220 | 19 | 34 | 34 | 25 | 0 | MAY-21 | AUG-21 | Work in progress, Severe ROW at loc no 15 & 17. Administration support required.
55 | LILO of 220 kV C.B. Ganj (220)- Budaun (220) line | D/C | 220 | 2 | 4 | 4 | 4 | 2 | MAR-21 | JUN-21 | Line energised on 31/03/2021.
56 | LILO of 220kV Gonda- Basti line at Bhaukhari | D/C | 220 | 26 | 0 | 0 | 0 | 26 |  | JUN-21 | Commissioned 05/21.
57 | LILO of 220 kV Pura Chandausi (220) - Budaun (220) line at Budaun | D/C | 220 | 36 | 58 | 58 | 58 | 36 | MAR-21 | APR-21 | Line energised on 31/03/2021.
58 | LILO of 220kV Rasra (220) - Gaipur S/C line at Rasra | D/C | 220 | 26 | 49 | 49 | 49 | 26.49 | APR-21 | MAR-21 | Line energised on 25/03/2021.
59 | LILO of Agra-Bharatpur Line | D/C | 220 | 20 | 0 | 0 | 0 |  |  |  | PGCIL scope. Line is energised.
60 | LILO of Banda-Karvi at Chittrakoot Line | S/C | 220 | 8 | 0 | 0 | 0 |  |  |  | To be deleted.
61 | LILO of Ckt.-I Mainpuri (PG) - Neebkarori line at Farrukhabad | D/C | 220 | 16 | 0 | 0 | 0 | 16 |  | AUG-21 | Commissioned 07/21.
62 | LILO of Nibkarori-Mainpuri PG Fatehgarh Line | D/C | 220 | 60 | 0 | 0 | 0 |  |  |  | To be deleted
63 | LILO of One ckt 220 kV Sohawal (PG) -New Tanda line at Ayodhya (220) | D/C | 220 | 27 | 56 | 56 | 56 | 23 | APR-21 | AUG-21 | Work in progress. PTCC case applied. Due to covid work is delayed. PTCC clearance received on 20.07.2021. Work delayed due to water logging
64 | LILO of One ckt Laitpur TPS -Dunara line at Babina | D/C | 220 | 15 | 25 | 25 | 25 | 14.54 | MAR-21 | AUG-19 | Line energised on 23.08.2019
65 | LILO of one Ckt. of Chhata (Mathura) - Manth (400) at Vrindawan | D/C | 220 | 46 | 74 | 74 | 74 | 44 | MAR-21 | MAR-21 | Line energised on 21/08/2020.
66 | LILO of Saharanpur-Nakur Line | S/C | 220 | 10 | 13 | 13 | 13 | 6.7 |  |  | Line charged on 05.05.2018
67 | Mallawan (220) - Hardoi(220) | D/C | 220 | 81 | 143 | 143 | 135 | 73.9 | SEP-21 |  | Work in progress. Railway crossing approved.
68 | Meerut by pass-Modipuram Line | D/C | 220 | 70 | 0 | 0 | 0 |  |  |  | To be deleted.
69 | Meerut-Gr. Noida-II Line | D/C | 220 | 200 | 0 | 0 | 0 |  |  | MAR-22 | 220 kV Substation Gr. Noida-II is planned for year 2022-23.
70 | Modipura-II-Bagpat PG Line | D/C | 220 | 70 | 133 | 131 | 118 | 8.36 |  | MAR-22 | Work in progress. PGCIL approved & PGCIL case submitted, Railway xing case submitted.
71 | Modipuram-II-Modipuram Line | D/C | 220 | 60 | 0 | 0 | 0 |  |  | MAR-22 | To be deleted
72 | Modipuram-II-Shamli Line | D/C | 220 | 120 | 262 | 235 | 138 | 0 |  | AUG-21 | Work in progress., PGCIL crossing approved & PTCC case submitted.
73 | Muradabad-Tajpur Line | D/C | 220 | 60 | 0 | 0 | 0 |  |  |  | to be deleted
74 | Nehtaur-Tajpur Line | D/C | 220 | 100 | 0 | 0 | 0 |  |  |  | To be deleted
75 | Nighasan-Lakhimpur Line | D/C | 220 | 120 | 0 | 0 | 0 |  |  |  | LILO of 220 kV Shahjahanpur PG(4000)- Gola DC line is sanctioned for 220 kV S/s Gola in Lakhimpur distt.
76 | Rae Bareli (400)-(Amethi (220) | D/C | 220 | 89 | 147 | 147 | 146 | 86.19 | OCT-21 |  | Work is in progress, Severe ROW at loc. No. 9/0 and 175mtr due to Railway crossing.
77 | Raebareli-Amethi Line | D/C | 220 | 89 |  |  |  |  | OCT-21
78 | Rasra (400) - Bhadaura (Gazipur) line | D/C | 220 | 108 | 184 | 172 | 109 | 0 | APR-21 | AUG-21 | Foundation work stop due to water logging Erection work under progress.
79 | Shahjahanpur PG (400)- Azizpur line | D/C | 220 | 49 | 95 | 95 | 95 | 49 | APR-21 | AUG-21 | Commissioned 07/21.
80 | Shamli-Khatauli Line | D/C | 220 | 50 | 0 | 0 | 0 |  |  |  | To be deleted.
81 | 132 kV D/C Agra cantt. - 400 kV Agra(South) | D/C | 132 | 24.08 | 44 | 44 | 44 | 24.32 |  |  | Line energised on 25/07/2017.
82 | Barkhera (Bajaj) - Dohna | D/C | 132 |  | 203 | 203 | 203 | 128.96 |  |  | Line energised on 13.09.2017.
83 | Bhadrekhi (Orai) - Jalaun line (GEC-II) | S/C | 132 | 0 | 108 | 108 | 108 | 36.65 |  | JUN-21 | Line energised on 30/06/2021.
84 | Dakore (Solar plant) - Bhadrekhi (Orai) line (GEC-II) | D/C | 132 | 0 | 105 | 105 | 105 | 69.6 |  |  | Line charged on 11.04.2018. (69.600 ckm)
85 | Dumariaganj- - Utraula | S/C | 132 |  | 114 | 114 | 114 | 40 |  |  | Line energised on 18.01.2019
86 | Gujrai (Solar Plant) - Pukhraya line (GEC-II) | D/C | 132 | 0 | 71 | 0 | 0 |  |  |  | To be constructed in deposit scheme as par fund availability.
87 | Gurrah (Solar plant) - Bhadrekhi (Orai) line (GEC-II) | D/C | 132 | 0 | 0 | 0 | 0 |  |  |  | To be constructed in deposit scheme as par fund availability.
88 | Jigna - Dadar Vijaypur (Solar plant) Mirzapur line (GEC-II) | D/C | 132 | 0 | 38 | 38 | 38 | 14.9 |  |  | Line charged on 07.03.2018
89 | LILO of 132 kV Bodla - Kheragarh at 400 kV Agra (South) | D/C | 132 | 11.9 | 19 | 19 | 19 | 11.9 |  |  | Line energised on 28/07/2017.
90 | LILO of 132 kV Kirawaki-Mathura at 400 kV Agra (South) | D/C | 132 | 11.5 | 25 | 25 | 25 | 5.6 |  | AUG-17 | Energised on 06/11/2017
91 | LILO of 132 kV Shamshabad-Kheragarh at 400 kV Agra(South) | D/C | 132 | 11.95 | 22 | 22 | 22 | 11.95 |  |  | Line energised on 25/07/2017
92 | LILO of Makreccha (Solar plant) - Bhadrekhi (Orai) line at Baghauli (Solar Plant) (GEC-II) | D/C | 132 | 0 | 0 | 0 | 0 |  |  |  | To be constructed in deposit scheme as par fund availability.
93 | Makreccha (Solar plant) - Bhadrekhi (Orai) line (GEC-II) | D/C | 132 | 0 | 0 | 0 | 0 |  |  |  | To be constructed in deposit scheme as par fund availability.
94 | Meja - Kosda Kala (Solar plant) Meja line (GEC-II) | D/C | 132 | 0 | 132 | 132 | 132 | 30 |  |  | Line Length 30 ckm. Energised in Feb, 2018.
95 | Parasan (Solar plant) - Bhadrekhi (Orai) line (GEC-II) | D/C | 132 | 0 | 54 | 0 | 0 |  |  |  | To be constructed in deposit scheme as par fund availability.
UTTARAKHAND POWER CORPORATION LIMITED(UKPCL)
1 | Baramwari (GIS)-Srinagar S/S | D/C | 220 | 180 | 228 | 210 | 182 | 72 | DEC-19 | DEC-19 | Baramwari  Srinagar 220 kV D/C line and LILO of this line at Singoli Bhatwari HEP are required for transfer of power from Singoli Bhatwari HEP up to Srinagar pooling station.But after the works of Phata Byung (2x38 MW) being severely affected due to flash floods in June, 2013 and all works being stalled since July, 2017 due to Funds constraints with the developer , this Baramwari switching station is not being constructed, therefore currently above line is being constructed from 400kV S/s Srinagar to interconnection point of 99MW Singoli Bhatwari HEP.This line is of 150 Ckm out of which 72 Ckm stringing have been completed. Also out of 220 tower locations, 210 fdns have been completed and 182 towers have been erected
WEST BENGAL STATE ELECTRICITY TRANSMISSION CO. LIMITED(WBSETCL)
1 | Gokarna - New Chanditala | D/C | 400 | 360 | 532 | 521 | 510 | 327.15 | SEP-21 | JAN-22 | work in progress
2 | Bankura - New Bishnupur line (GEC-II) | D/C | 220 | 0
3 | East Mednipur - Kharagpur line (GEC-II) | D/C | 220 | 0
4 | Establishment of Barasat - Rajarhat (PG) utilising Barasat - Kasba | D/C | 220 | 62 | [5 empty] | MAR-18
5 | Establishment of Rajarhat (PG) - New Town-IIIutilishing Barasat - Kasba | D/C | 220 | 2 | [5 empty] | MAR-18
6 | LILO of Arambag - Domjur at Mayapur | D/C | 220 | 36 | [5 empty] | MAR-20
7 | LILO of BKTPP - Satgachia at Mahachhanda | D/C | 220 | 14 | [5 empty] | MAR-19
8 | LILO ofc arambag - Midnapur at C.K.Road | D/C | 220 | 232 | [5 empty] | MAR-21
9 | LILO of Sadaipur - Gokarna at Kotasur | D/C | 220 | 8 | [5 empty] | MAR-20
10 | LILO of STPS - Durgapur at Asansole | S/C | 220 | 60 | 122 | 53 | 38 | 0 |  | APR-22 | Work under Progress.
11 | Rajarhat (PG) - New Town-II | D/C on M/C | 220 | 56 | 58 | 2 | 2 | 1.09 |  | MAR-19 | Work of main line yet to be commenced due to mass resistance by the villagers
12 | Satgachia - Rishra | D/C | 220 | 15 | 36 | 36 | 35 | 10.01 | JUL-21 | SEP-21 | Work under Progress.
13 | STPS - Raghunathpur | D/C | 220 | 100 | [5 empty] | MAR-21
14 | West Mednipur - Kharagpur line (GEC-II) | D/C | 220 | 0
15 | LILO of 132 kV One Ckt of Rammam-II - NBU at Rammam -III HEP | D/C | 132 | 20 | 0 | 0 | 0 |  | APR-19 | DEC-21 | "Survey work of the transmission lines completed. WBSETCL contemplated the ATS of Rammam III HPS of NTPC considering that WBSEDCL would purchase the entire power from NTPC. But the PPA of NTPC with WBSEDCL for sale power from Rammam III HPShas not been executed till date. After execution of the said PPA, WBSETCL would take up the construction work of the ATS obtaining Investment Approval fromWBERC."
16 | Rammam III - Chalsa | D/C | 132 | 130 | 0 | 0 | 0 |  | APR-19 | DEC-21 | "Survey work of the transmission lines completed. WBSETCL contemplated the ATS of Rammam III HPS of NTPC considering that WBSEDCL would purchase the entire power from NTPC. But the PPA of NTPC with WBSEDCL for sale power from Rammam III HPShas not been executed till date. After execution of the said PPA, WBSETCL would take up the construction work of the ATS obtaining Investment Approval fromWBERC."
ADANI POWER LTD.(APL)
1 | Bhuj PS - Lakadia PS | D/C | 765 | 215 | 280 | 245 | 162 | 4 | NOV-21 | DEC-21 | a) Facing severe Row: TSP is facing severe Right of Way in the Kutch District of Gujarat State due to exorbitant demand of compensation. Further, situation is more aggravated after recent order issued by SDM Nakhatrana allowing corridor compensation @ 15% of Rs. 900 per Sq. Mtr vide dated: 17.01.2021. Since, this project falls under same vicinity and now farmers of various villagers are not allowing to work and demanding the written assurance that the compensation for corridor shall be given @ 15% in place of @7.5% due to recent SDM order Dated: 17.01.2021. Because of this issue work is stand still. Also in the section where we have completed Foundation and Erection activities and sections are ready for the stringing, We are not able to do the stringing work due to Corridor compensation issue. Hence stringing work is presently on hold.
2 | Bikaner (PG) - Khetri S/S | D/C | 765 | 481 | 621 | 621 | 621 | 481 | MAY-21 | SEP-21 | Commissioned 08/21.
3 | Ghatampur TPS-Hapur (WUPPTCL) | S/C | 765 | 411 | 1052 | 1047 | 1045 | 408 | JUN-21 | OCT-21 | a) Severe ROW is being faced at Hapur end of the said line at 5 loc. and administrative support is being sought from the local administration. Also Land Measurement is being done jointly with administration as per SDO instruction. But farmer are demanding exorbitant compensation. Discussion is in progress. b)Pandemic COVID 19: Work affected due to COVID-19 since Feb'20, Also, due to lockdown most working season in transmission line projects i.e. Mar'20 to Jun' 20 had been lost and subsequent to that, monsoon delayed work at site. Further, due to recent 2nd wave of Covid-19, various restrictions imposed by Central/State Goverments to curb the situation and because of which execution work as supply is badly affected as labours are not willing to stay at site and returning back to their native in fear of lockdown.
4 | Lakadia PS - Banaskantha PS | D/C | 765 | 352 | 472 | 455 | 353 | 178 | NOV-21 | NOV-21 | a) Facing severe Row: Severe ROW at 1 location of the Banaskantha District and 5 location of Kutch district as land owners are demanding undue land & corridor compensation that is multifold of Jantri rates. Further, situation is more aggravated after recent order issued by SDM Nakhatrana allowing corridor compensation @ 15% of Rs. 900 per Sq. Mtr vide dated: 17.01.2021. Since, this project falls under same vicinity and now farmers of various villagers are not allowing to work and demanding the written assurance that the compensation for corridor shall be given @ 15% in place of @7.5% due to recent SDM order Dated: 17.01.2021. In Kutch district, the section where we have completed Foundation and Erection activities and sections are ready for the stringing, We are not able to do the stringing work due to Corridor compensation issue. Hence stringing work is presently on hold.
5 | Jaunpur -Obra (Twin) | D/C | 400 | 334 | 464 | 418 | 394 | 216 | JUL-21 | DEC-21 | a) NBWLclearance is critical for the completion of the balance work. During the NBWL meeting dated 18-02-21, the NBWL formed committee for the checking the feasibility of the bunching of the transmission line in wild life areas and during NBWL meeting dated 11-06-21, the proposal recommended. Demand Not charges paid and Final permission awaited. b)Pandemic COVID 19: Work affected due to COVID-19 since last week of Feb'20, Also, due to lockdown most working season in transmission line projects i.e. Mar'20 to Jun' 20 had been lost and subsequent to that, monsoon season delayed work at site. Further, due to recent 2nd wave of Covid-19, various restrictions imposed by Central/State Goverments to curb the situation in last three month and because of which execution work and supply badly affected as labours returned back to their native in fear of lockdown.
6 | LILO of Bhachau - EPGL (Tiple) line at Lakadia PS | D/C | 400 | 77 | 121 | 90 | 59 | 0 | NOV-21 | DEC-21 | a) Facing severe Row: TSP is facing severe Right of Way in the Kutch District of Gujarat State due to exorbitant demand of compensation. Further, situation is more aggravated after recent order issued by SDM Nakhatrana allowing corridor compensation @ 15% of Rs. 900 per Sq. Mtr vide dated: 17.01.2021. Since, this project falls under same vicinity and now farmers of various villagers are not allowing to work and demanding the written assurance that the compensation for corridor shall be given @ 15% in place of @7.5% due to recent SDM order Dated: 17.01.2021. Because of this issue work is stand still. Also in the section where we have completed Foundation and Erection activities and sections are ready for the stringing, We are not able to do the stringing work due to Corridor compensation issue. Hence stringing work is presently on hold.
7 | LILO of both ckt. of Ranchi - Maithon-RB line at Dhanbad (NKTL-TBCB) | D/C | 400 | 5 | 10 | 10 | 10 | 5 | MAY-21 | AUG-21 | Commissioned 07/21.
8 | North Karanpura - Chandwa (Jharkhand) NKSTPP line (NKTL -TBCB) | M/C | 400 | 52 | 42 | 22 | 22 | 8.7 | JAN-22 | JUL-22 | a) Covid-19: Project progress including Statutory proposals affected due to COVID-19. Further, due to recent 2nd wave of Covid-19, various restrictions imposed by Central/State Goverments. b) Forest Clearance: Delay in receipt of Forest clearance, around 806 days (Since 01-07-19) passed against 200 days agreed.Nodal office Forwarded the proposal to state Government on 11-08-2021 for onward forwarding to RO and Part-V. In meeting dated 16-03-20, 16-10-20, 29-01-21 NKTL conveyed that, NKTL will be able to complete the NK-C line in 9 months from the date of FC. Subsequently, the review meeting conducted by Joint Secretary (Trans.), MoP on 11-11-20, 10-02-21 & on 31-03-21 & 15-06-21, review meeting conducted by Secretary (Power), MOP wherein NKTL has requested support for FC.
9 | North Karanpura - Chandwa (Jharkhand) PS line (NKTL -TBCB) | D/C | 400 | 50 | 73 | 52 | 52 | 12.8 | JAN-22 | JUL-22 | a) Covid-19: Project progress including Statutory proposals affected due to COVID-19. Further, due to recent 2nd wave of Covid-19, various restrictions imposed by Central/State Goverments. b) Forest Clearance: Delay in receipt of Forest clearance, around 806 days (Since 01-07-19) passed against 200 days agreed.Nodal office Forwarded the proposal to state Government on 11-08-2021 for onward forwarding to RO and Part-V. In meeting dated 16-03-20, 16-10-20, 29-01-21 NKTL conveyed that, NKTL will be able to complete the NK-C line in 9 months from the date of FC. Subsequently, the review meeting conducted by Joint Secretary (Trans.), MoP on 11-11-20, 10-02-21 & on 31-03-21 & 15-06-21, review meeting conducted by Secretary (Power), MOP wherein NKTL has requested support for FC.
10 | North Karanpura - Gaya line (NKTL - TBCB) | D/C | 400 | 185 | 286 | 138 | 114 | 35.5 | SEP-19 | MAR-23 | a) Covid-19: Project progress including Statutory proposals affected due to COVID-19. Further, due to recent 2nd wave of Covid-19, various restrictions imposed by Central/State Goverments. b) Forest Clearance: Delay in receipt of Forest clearance, around 773 days (Since 20-07-19) passed against 300 days. The proposal has been accepted by Nodal officer after 408 days i.e. on 06.08.20 & presently proposal is pending with DFO for further processing. in meeting of 16-03-20, 16-10-20, 29-01-21 NKTL conveyed that, NKTL will be able to complete the NK-G line in 12 months from the date of forest clearance. Subsequently, the review meeting conducted by Joint Secretary (Trans.), MoP on 11-11-20, 10-02-21 & on 31-03-21 & 15-06-21, review meeting conducted by Secretary (Power), MOP wherein NKTL has requested support c) GM-JJ Land NOC and FRA NOC awaited from respective authorities. d) Also Proposal of the Bihar portion deliberated and approved by REC and stage-I issued.
ATHENA CHHATTISGARH POWER LIMITED(ACPL)
1 | LILO of one ckt of MSCTL - Chandrapur at Singhitrai | D/C | 400
BAJAJ ENERGY PVT. LTD.(BEPL)
1 | Balrampur-Utraula line | D/C | 132 | [7 empty] | Existing line.
CORPORATE POWER LTD.(CPL)
1 | Corporate TPP - Jharkhand Pooling Station | D/C | 400 | 6 | 11 |  |  |  |  | AUG-16
2 | Latehar - Namkum | D/C | 400 | 216 | 320 | 293 | 274 | 132 |  | AUG-16
D.B. POWER CORP. LTD.(DBPCL)
1 | LILO of Raigarh - Raipur (3rd Ckt) at Baradhara TPP ( Interim arrangement) | D/C | 400 | 30 | 44 | 44 | 44 | 30 |  | MAY-13 | Line completed. (Interim)
DIRANG ENERGY PVT. LTD.(DEPL)
1 | Gongri - Dinchang Pooling Station | D/C | 220
ESSAR POWER TRANSMISSION CO. LTD.(EPTCL)
1 | Navbharat TPP - Angul P.S. (PG) | D/C | 400
2 | Tori - Jhharkhand Pooling Station | D/C | 400
Essel Infraprojects Ltd.(ESSEL)
1 | Hyderabad - Kurnool (WKTL- TBCB) | D/C | 765 | 332 | 422 | 337 | 183 |  | FEB-20 | FEB-20 | Work hampered due to severe RoW issue in the stretch of AP 27  AP 29, AP 60 A AP 60 B and AP 66  AP 67.
2 | Warangal (New) - Chilakaluripeta (WKTL - TBCB) | D/C | 765 | 395 | 565 | 446 | 341 |  | FEB-20 | FEB-20 | Severe RoW issue existing in the stretch of AP 10  AP 11, AP 14- AP 15, AP 25  AP 28, AP 52- AP 53, AP 55  AP 56, AP 63  63/12, AP 76  AP 77, AP 84- AP 85 and AP 89  AP 90. Court Case: 04 no. of tower locations has been traversing though the proposed land area of M/s Emami Cement Ltd., out of which the 04 no. of foundations and 03 nos of erections are already completed. At this point of time, M/s Emami Cement Ltd. moved to High Court of Hyderabad for seeking Order to remove WKTL transmission towers along with direction to re-route the transmission line. At present this matter is under consideration of Honble High Court, Hyderabad and next date is yet to schedule. Forest Details of Tr. Line Falling under Forest: Forest area affected (ha):18.442 ha (2.75 Kms) in Andhra pradesh .Forest proposals sub on :23.08.2017. Stage I forest approval granted on 28.11.18.
3 | Warangal (New) - Hyderabad (WKTL - TBCB) | D/C | 765 | 265 | 344 | 312 | 247 |  | DEC-19 | DEC-19 |  RoW issue: In the stretch of AP 34 - AP 35, AP 37- AP 38, AP 41- AP 42, AP 46/0, AP 54/2, AP 17/3 and AP 21/6. At loc. nos. 47/2 and 47/3, locals have removed the stubs by using JCB. A FIR in this regard has been lodged with local Police Station. Court Case:  Land Owner of location no. 2/6 has approached High Court of Telangana. The Court has granted the stay on work. Further on hearing held on 07th June 2018, the Court adjourned and as on date the matter is still pending for scrutiny.  Land owner for the stretch between the location no. 30 to 31 has approached the District Court (Nalgonda) to accord permanent injunction. On the hearing held on 14.03.2019, , the Court scheduled next date of hearing on 01.05.2019 in this matter. In such situation, the work is at stand still at this location effectively from 20th Mar 2018.
4 | Warora (Pool) - Warangal (New) (WKTL - TBCB) | D/C | 765 | 645 | 827 | 773 | 423 | 58.6 | DEC-19 | NOV-19 |  Severe RoW issues.; Forest area affected (ha): 19.793 ha (2.954 Kms) in Maharastra and 47.592 ha (7.103 Kms) in Telangana. Forest proposals submitted on 4th Aug 17 for Maharashtra and on 23 Aug 17 for Telangana. Current status: Maharashtra Stage I received on 05.02.18. The Telangana stage I approval received on 13.12.2018 ; WIld life approval : Proposal forwarded by State Government to Member Secretary (NBWL) on 20.11.2018. Proposal forwarded to NTCA for their recommendation and MoEF&CC asked State Govt. to submit SBWL MoM, which is still awaited for further processing & consideration in next NBWL meeting.The work execution in under Maharashtra is severely affected due to farmer agitation demanding higher compensation for the construction of transmission line at their fields. Court Case- at loc. no. 89/8 in terms of stay order granted by Bombay High Court. The matter is listed on 15.01.2020.
5 | Babai (RRVPNL)- Bhiwani (PG) (NRSS-XXXVITL-TBCB) | D/C | 400 | 221 | 299 | 265 | 215 | 1.12 | MAR-22 | MAR-22 | Details of Tr. Line Falling under Forest: 3.37 Km ,Forest area: 12.90 Ha (2.80 Kms) of Rajsthan + 3.46 Ha (0.57 Kms) of Haryana. Forest proposals submitted on : 15.05.2017 for Haryana and on 11.08.2017 for Rajasthan. Stage I approval from Haryana Forest Deptt. received on 27.03.2018 and Stage I approval from Rajasthan Forest Deptt. received on 06.07.2018. Wildlife Clearance : Wildlife area(ha) : 7.452 Ha (2.80 Kms) Khetri Bansyal Conversion Reserve Wildlife proposals submitted on : 16.02.2018 and at present, Proposal recommended by NBWL and currently recommendations forwarded to State Govt. (Rajasthan). Severe RoW issues: 52/1, 52/3, 53/0, 54/0, 54/1, 54/2 & 54A/0 of Tehsil Dadri and loc. No. 17/0 & 18/0 of Tehsil Khetri.
6 | Koteshwar (PS) - Rishikesh (HTLS) (NRSS-XXXVITL-TBCB) | D/C | 400 | 81 | 106 | 16 | 0 |  | DEC-19 | DEC-19 | 1. Consent from Indian Drug and Pharmaceuticals Ltd. (IDPL) , Rishikesh for traversing 400 kV D/C Koteshwar-Rishikesh line through IDPL premises is awaited.Pending NOC from IDP (Rishikesh), the Forest Deptt. is not ready to accept the forest diversion proposal because all 16 no. of tower locations are falling inside the IDPL lease hold area, which belongs to the forest deptt.2. DFO-Tehri directed us to divert from our existing transmission line route, which was earlier approved and confirmed by Forest Range officer through verification of land schedule and DGPS survey in Jan-2018. 3) Severe RoW issues are existing at loc. No. 1/0, 2/0, 3/0, 4/0, 13/0, 14/0, 14/1, 15/0, 16/0, 42/0, 43/0, 44/0, 48/0, 48/1 and 49/0 .
7 | Sohwal - Lucknow (TTL -TBCB) | D/C | 400 | 240 | 0 | 0 | 0 |  |  |  | MoP has already dropped the project.
8 | Tanda - Sohwal (TTL - TBCB) | D/C | 400 | 186 | 0 | 0 | 0 |  |  |  | MoP has already dropped the project.
9 | Warangal (New) - Warangal (Existing) (Q) (WKTL - TBCB) | D/C | 400 | 95 | 130 | 9 | 0 |  | FEB-20 | FEB-20 | Forest : Nil
GATI INFRASTRUCTURE PRIVATE LIMITED(GIPL)
1 | LILO of one circuit of Chujachen - Rangpo line at Bhasmay | 2xS/C | 220 | 10 | [5 empty] | MAY-18 | Work yet to be awarded.
GMR ENERGY LIMITED(GMR ENERG)
1 | LILO of Talchar -Meramundli at Kamalanga TPP | D/C | 400 | 1 | 3 | 3 | 3 | 1 |  | MAY-12 | For start up power,work completed 5/12.
2 | Alaknanda HEP - Joshimath | D/C | 220
GUPTA ENERGY PVT. LTD.(GEPL)
1 | LILO of one ckt of Bhadrawati -Parli at GEPL TPS | D/C | 400
IDEAL ENERGY PROJECTS LTD.(IEPL)
1 | LILO of Mouda - Wardha at Bela | D/C | 400 | 0.3 | 2 | 2 | 2 | 0.3 |  | NOV-12 | Completed (Interim)
IND BHARATH POWER INFRA LIMITED(IBPIL)
1 | Ind Barath TPP - Tuticorin (PS) | D/C | 400 | 200
2 | LILO of Rouekila - Raigarh at Ind Barath | D/C | 400 | 47 | 72 | 72 | 72 | 47 |  | JUN-15
ISPAT ENERGY LTD(ISPAT)
1 | Haldia TPP - Egra | D/C | 220 | 180 | [6 empty] | Under planning stage by WBSETCL.
JAIN ENERGY TRADING LTD(JAIN ETL)
1 | Jain Energy TPS - Dharamjaygarh Korba Pooling station | D/C | 400 | [6 empty] | MAR-17
JAL POWER CORP. LTD.(JPCL)
1 | Rangit IV - New Melli line | D/C | 220 | 6.6 | 15 |  |  |  |  | MAR-19 | Work of 220kV line has been awarded to M/s. Ashish Infratech and completion period is 8 months from start of work. Generation project will take about 2? years for completion as against 8 months for completion of associated transmission line, there will be no mismatch for evacuation of power. It may also be mentioned that route survey of transmission line has been completed and design work of transmission system including towers (15 nos.) has also been completed. 220kV GIS bays at PGCIL substation at New Melli have also been awarded to M/s. PGCIL as deposit work. Line length is 3.3 KM. Associated transmission system comprises of 220kV GIS in PH building, 3.3 km long 220kV D/C line from PH to PGCIL pooling station at New Melli. Work for 220kV GIS substation at PH has been awarded to M/s. Siemens and GIS equipment has already been delivered at site.
KORBA WEST POWER COMPANY LIMITED(KWPCL)
1 | LILO of on Ckt of Raigarh - Raipur at Avantha Bhandar (Korba west ) TPS | D/C | 400 | 10 | 22 | 22 | 22 | 10 |  | DEC-13 | Interim arrangement.
KVK ENERGY PVT. LTD.(KVK)
1 | LILO of Mendasal - Baripada at Nilanchal TPP | D/C | 400 | 16 | 0 | 0 | 0 | 0 |  | JUN-16 | Work yet to Start.
LANCO ENERGY (P) LTD,.(LEPP)
1 | LILO of Seoni - Wardha at Lanco Vidarbha TPS | D/C | 765 | 15 | 16 |  |  |  |  | MAR-17
2 | Babandh TPP - Angul Pooling Station | D/C | 400 | 48 | 72 | 0 | 0 | 0 |  | DEC-16 | Work yet to start.
3 | Lanco Amarkantak - Champa Pooling Station | D/C | 400 | 95 | 158 | 96 | 12 | 0 |  | JUN-16
4 | Phata HEP-Baramwari (Rudrpur) | D/C | 220 | 8 | 20 | 0 | 0 | 0 |  | DEC-16
5 | Routing of one circuit of Jorthong - New Melli via Rangit - IV | D/C | 220 | [6 empty] | MAR-19 | Work in generation project is stopped for since 2013.
6 | Teesta VI HEP - Rangpo Pooling Station | D/C | 220 | 25 | [6 empty] | Detail survey completed section 164 approval received. Work yet to started.
MALANA POWER COMPANY LIMITED(MPCL)
1 | Ka Dogri - Jangi Pooling Station | D/C | 400
2 | Chango Yangthang - Ka Dogri Pooling Station | D/C | 220
MONNET POWER COMPANY LIMITED(MPCL)
1 | Malibrahmani - Angul | D/C | 400 | 62 | 108 | 100 | 80 | 20 |  | JUL-16
M/s Adani Renewable Energy Park Rajasthan Limited (AREPRL)(AREPRL)
1 | Bhadla IV SP - Bhadla Pooling station line (GEC-II) | D/C | 220 | 0
2 | Fatehgarh Solar Park - Fatehgarh Pooling Station line (GEC-II) | D/C | 220 | 0
3 | SPP - Bhadla (PS) (GEC-II) | D/C | 220 | 0
NORTH KARANPURA TRANSMISSION CO. LTD.(NKTCL)
1 | Bareilly - Meerut (NKTL - TBCB) | S/C | 765 | 240 | 0 | 0 | 0 |  | NOV-13 | DEC-16 | Case pending in Supreme Court.
2 | Lucknow - Bareilly (NKTL - TBCB) | S/C | 765 | 220 | 0 | 0 | 0 |  | NOV-13 | DEC-16 | Case pending in Supreme Court.
3 | Agra - Gurgaon (NKTL - TBCB) | D/C | 400 | 220 | 0 | 0 | 0 |  | NOV-13 | DEC-16 | Case pending in Supreme Court.
4 | Gurgaon - Gurgaon (PG) (NKTL - TBCB) | D/C | 400 | 20 | 0 | 0 | 0 |  | NOV-13 | DEC-16 | Case pending in Supreme Court.
5 | Sipat/Korba (PS)  Seoni (NKTL - TBCB) | S/C | 400 | 334 | 0 | 0 | 0 |  | NOV-13 | DEC-16 | Case pending in Supreme Court.
NSL NAGAPATNAM POWER PVT. LTD.(NSLNPPL)
1 | NSL TPP - Angul | D/C | 400 | 46 | 0 | 0 | 0 | 0 |  |  | Project Authority intimated that PGCIL yet to award construction of work.
2 | LILO of Kasang - Bhbaba at Tidong-I | D/C | 220 | 32 | 57 | 0 | 0 |  |  | DEC-22 | Being Executed by M/s Statkraft.
RELIANCE POWER TRANSMISSION LTD.(RPTL)
1 | Moti Khavdi TPP - Jam Nagar | D/C | 400
2 | Sohwal - Lucknow Line (TBCB-TTCL) | D/C | 400 | 176
3 | Tanda - Sohwal Line (TBCB-TTCL) | D/C | 400 | 173
RKM POWERGEN PVT. LIMITED(RKMPPL)
1 | LILO of Raigarh (Kotra) - Raipur at Uchpinda (Interim Arrangement) | D/C | 400 |  | 73 | 73 | 73 | 38.99 |  |  | Commissioned (Interim Arrangement). De-LILO activity completed.
Shekhawati Transmission Service Company Limited(SKHWTTSCL)
1 | Jhunjhunu - Nawalgarh line | S/C | 220 | 32 | 108 | 77 | 73 | 0 | FEB-15 | DEC-20 | court case pending, severe ROW problem, Railway crossing pending.Funds problem from PFC.
2 | Sikar - Nawalgarh line | S/C | 220 | 22 | 76 | 55 | 48 | 0 | FEB-15 | DEC-20 | court case pending, severe ROW problem, Railway crossing pending.Fund problem from PFC.
SIKKIM HYDRO POWER LIMITED(SHPL)
1 | LILO of one ckt of Legship - New Melli at Rangit-II | D/C | 220
South East UP Power Transmission Company Limited(SEUPPTCL)
1 | Mainpuri - Bara Ckt-I | S/C | 765 | 375 | 889 | 613 | 346 | 0 |  | JUN-17 | The project is at stand still pending of a time extension requested to UPPTCL in June 2015
2 | Mainpuri - Unnao (Quad) | S/C | 765 | 188 | 449 | 380 | 274 | 0 |  | JUL-17 | The project is at stand still pending of a time extension requested to UPPTCL in June 2015
3 | Bara - Karchana | D/C | 400 | 80 | 124 | 0 | 0 | 0 |  | JUN-16 | Karchana gantry not finalised. The project is at stand still pending of a time extension requested to UPPTCL in June 2015
4 | Gonda - Shahjanpur | D/C | 400 | 442 | 542 | 295 | 140 | 0 |  | DEC-17 | The project is at stand still pending of a time extension requested to UPPTCL in June 2015
5 | LILO of Obra - Sultanpur at Aurai | S/C | 400 | 1 | 5 | 0 | 0 | 0 |  | JUN-16 | The project is at stand still pending of a time extension requested to UPPTCL in June 2015
6 | LILO of Sarojini Nagar - Kursi RD at Sultanpur RD | D/C | 400 | 14 | 18 | 0 | 0 |  |  | JUL-16 | The project is at stand still pending of a time extension requested to UPPTCL in June 2015
7 | Rewa Road - Karchana | D/C | 400 | 58 | 102 | 0 | 0 |  |  | OCT-16 | Karchana gantry not defined. The project is at stand still pending of a time extension requested to UPPTCL in June 2015
8 | Tanda TPS Extn - Gonda | S/C | 400 | 100 | 241 | 97 | 54 | 0 |  | OCT-18 | "Work is standstill for more than a year due to poor financial health of SEUPPTCL, the transmission service provider, owned by M/s Isolux. The line is a part of TBCB project awarded to M/s Isolux. UPPTCL representative informed that GoUP is considering to take over transmission project and evaluation of completed work is under progress. Bids for valuers have been invited by M/s PFC. Valuation is under progress. Final decision will be taken after valuation."
STERLITE ENERGY LIMITED(SEL)
1 | Sterlite TPP - Jharsuguda (LILO-II to Jharsuguda) | D/C | 400 | 40 | 0 | 0 | 0 |  | NOV-16 |  | Transmission work not started yet. SEL will approach CEA for approval of continuing the LILO-II.
STERLITE GRID LTD.(SGL)
1 | Dharamjaygarh Pool section B - Raigarh (Tamnar) Pool line (G-TTPL-TBCB) | D/C | 765 | 140 | 178 | 70 | 27 | 0 | DEC-21 | DEC-21 | 1. Delay in grant of forest clearance for Diversion of 137.014 Ha of Forest land. Forest proposal has been forwarded by Govt of Chhattisgarh to Regional MoEFCC for consideration in upcoming REC Meeting. Secretary, MOEFCC support is required to clear the forest file. Timely approval will enable timely commencement and completion of balance works in the Project 2. Delay due to occurrence of Force Majeure (FM) event i.e. outbreak of COVID-19 and this FM event has been intimated to all LTTCs
2 | Khandwa Pool - Dhule (KTL - TBCB) | D/C | 765 | 379 | 492 | 476 | 475 | 350 | JUN-21 | JUN-21 | 1. Forest proposal for diverted route was discussed and recommended in the REC meeting held on 11.02.2021 and Stage-I clearance is awaited. 2. Approval for Sec-164 (diverted route) from CEA is awaited 3. A meeting was held on 12-02-2021 by the Committee being constituted by Ministry of Power under the chairmanship of Member (Power Systems), CEA and as directed by Committee, KTL had submitted the Undertaking on 17-02-2021 and the NOC was granted by Irrigation Dept on 23-02-2021
3 | Lakadia - Vadodara Transmission line | D/C | 765 | 658 |  |  |  |  | DEC-21
4 | LILO of one ckt. of Narendra (existing) - Narendra (New) quad line at Xeldem (G-TTPL-TBCB) | D/C | 400 | 0 | 233 | 2 | 0 |  |  | APR-22 | 1.Delay in getting forest and wildlife clearances. State Govt had returned the proposal to nodal officer seeking the details that whether the user agency is utilizing the corridor of existing defunct 110kV Ambewadi  Ponda line or not at possible extent. The user agency confirmed that they are utilizing the corridor of defunct 110kV line at the maximum possible extent. Therefore, support is required from PCCF / Nodal officer and Chief Wildlife Warden, Karnataka to recommend the proposal with mitigation measures 2. The progress is suffered due to petition filed by Goa Foundation in CEC constituted by Supreme court and High Court of Mumbai and Goa 3. The introduction of Guidelines being issued by District Collector, North Goa vide letter dated 06-11-2020 for payment of Additional Compensation towards damages in regards of Right of Way for transmission Line has consequently led to an escalation in the cost of the project and the same is covered under Article 12 of the TSA as CIL event
5 | Xeldem - Mapusa (quad) line (G-TTPL -TBCB) | D/C | 400 | 110 | 148 | 14 | 2 |  | OCT-21 | OCT-21 | 1. Delay due to occurrence of Force Majeure (FM) event i.e. outbreak of COVID-19 and this FM event has been intimated to all LTTCs 2.The progress is suffered due to petition filed by Goa Foundation in Central Empowered Committee (CEC) constituted by Supreme court and High Court of Mumbai and Goa 3. The introduction of Guidelines being issued by District Collector, North Goa vide letter dated 06-11-2020 for payment of Additional Compensation towards damages in regards of Right of Way for transmission Line has consequently led to an escalation in the cost of the project and the same is covered under Article 12 of the TSA as Change in law event
6 | Xeldem - Mapusa (quad) line (G-TTPL -TBCB) | D/C | 400 | 0 | 0 | 0 | 0
7 | Xeldem (Existing) - Xeldem (New) Transmission line | D/C | 220 | 40 |  |  |  |  | OCT-21
8 | AGTPP (NEEPCO) - P.K. Bari (TSECL) line (NER-II TL-TBCB) | D/C | 132 | 167 | 236 | 236 | 236 | 166.8 | MAR-20 | FEB-21 | Commissioned and declared under Commercial Operation (DOCO) w.e.f. 00:00 Hrs of 21-02-2021
9 | Biswanath Chariyalli (PG) - Itanagar (Zebra) line (NER-II TL-TBCB) | D/C | 132 | 134 | 211 | 211 | 207 | 126 | MAR-20 | MAR-21 | 1.The proposal for PLCC Carrier frequency has been submitted to Ministry of Communication (WPC Wing) and the approval is still awaited. Support required to expedite the same. The WPC Wing has informed that the Frequency allotment has been temporarily closed by MOC, therefore in the interest of timely completion of the project we have requested CEA to grant an approval for use of proposed frequenices otherwise the line cant be charged 2. The Additional Compensation has been paid for forest Land in the state of Arunachal Pradesh as being directed by Deputy commissioner, Papum Pare and Itanagar Districts. This is an additional cost to the project and the same is entitled to be covered under Article 12 of the TSA as Change in Law event
10 | LILO of one Ckt. of Biswanath Chariyalli (PG)- Itanagar (Zebra) line at Gohpur (AEGCL) (NER-II TL-TBCB) | D/C | 132 | 17 | 30 | 30 | 30 | 16 | MAR-20 | MAR-21 | 1.Non-finalization of terminal bays at Gohpur S/s by AEGCL for the termination of LILO line 2. The proposal for PLCC Carrier frequency has been submitted to Ministry of Communication (WPC Wing) and the approval is still awaited. Support required to expedite the same. The WPC Wing has informed that the Frequency allotment has been temporarily closed by MOC, therefore in the interest of timely completion of the project we have requested CEA to grant an approval for use of proposed frequenices otherwise the line cant be charged 3. The Additional Compensation has been paid for forest Land in the state of Arunachal Pradesh as being directed by Deputy commissioner, Papum Pare and Itanagar Districts. This is an additional cost to the project and the same is entitled to be covered under Article 12 of the TSA as Change in Law event
TALCHER TRANSMISSION CO. LTD.(TTCL)
1 | Behrampur - Gazuwaka (T-II TL -TBCB) | D/C | 400 | 290 | 0 | 0 | 0 |  | OCT-12 | SEP-13 | Case pending in Supreme Court.
2 | Talcher II - Behrampur (T-II TL - TBCB) | D/C | 400 | 220 | 0 | 0 | 0 |  | OCT-12 | SEP-13 | Case pending in Supreme Court.
3 | Talcher II - Rourkela (T-II TL - TBCB) | D/C | 400 | 161 | 0 | 0 | 0 |  | OCT-12 | SEP-13 | Case pending in Supreme Court.
TEESTA URJA LTD.(TUL)
1 | Teesta III - Kishanganj | D/C | 400 | 427 | 590 | 586 | 581 | 391.8 |  | OCT-18 | Teesta III  Rangpo (CKT-II) and Teesta III  Dikchu (Ckt 1(a)) Lines are in commercial operation from 16.01.2017 & 14.04.2017 respectively. Dikchu- Rangpo (Ckt 1 (b)) is energized on 30.06.2018 (i.e. trial operation for 24 hours) and could successfully complete the trial operation on 1st July 2018. 46.1 Kms line from Kishanganj Substation has been successfully energized for antitheft purpose. Re-Stringing works, in last span of 290-291 is under progress and back charging would be extended stretch by stretch on completion of re-stringing. RoW and Forest issues faced in Darjeeling distt.
TORRENT POWER LTD(TOR. POW. (UNOSUGEN))
1 | DGEN TPS - Bharuch/Dahej Pooling Station | D/C | 400
2 | DGEN - Vadodara (DGEN TL - TBCB) | D/C | 400 | [7 empty] | Work awarded to M/s Instalaciones. Inabemsa. Spian on May 2014. Route changed after survey observations.
3 | Sandila TPP - ATS not defind | D/C | 400
4 | Navseri - Bhasten (DGEN TL - TBCB) | D/C | 220 | [7 empty] | Work awarded to M/s Instalaciones. Inabemsa. Spian on May 2014. Route changed after survey observations.
VANDANA VIDYUT LTD.(VVL)
1 | Salora TPS - Dharamjaigarh (Korba) (PGCIL) Pooling Station | D/C | 400 | 60 | 84 |  |  |  |  | MAR-17 | Target Commissioning date will be provided after approval/receipet of loan from lenders.
VEMAGIRI TRANSMISSION SYSTEM LIMITED(VTSL)
1 | Khammam-Hyderabad Line-1 | D/C | 765 | 772 | [5 empty] | MAR-15
2 | Khammam - Hyderabad line -I | D/C | 765 | 410 |  |  |  |  | APR-15 |  | Bidding process to be taken up
3 | Vemagiri Pooling Station -Khammam Line -1 | D/C | 765 | 852 | [5 empty] | MAR-15
4 | Vemagiri Pooling Station - Khammam line -I | D/C | 765 | 455 |  |  |  |  | APR-15 |  | Bidding process to be taken up
VISA POWER LTD(VISA)
1 | Visa Power TPP - Raigarh Pooling Station | D/C | 400 | 26 | 37 | 33 | 26 | 0 |  | JUN-15 | Work is under Construction.